## Sheet1
Assignment ID | Activity ID | Project Name | Report Type | Region | Site ID | Site Name | Latitude | Longitude | Vendor | Date_planned | Date_completion | Batch | Status
10013 | 10013 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-18 |  | 2 | Pending
10038 | 10038 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
10063 | 10063 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-18 | 2016-10-01 | 2 | Verify
10113 | 10113 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB047 | Desa Lauk | 109.6195 | 2.0075 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
10138 | 10138 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-18 | 2016-09-18 | 2 | Verify
10188 | 10188 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
10213 | 10213 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
10263 | 10263 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-08-15 | 2016-08-18 | 1 | Verify
10288 | 10288 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-08-15 | 2016-08-18 | 1 | Verify
10313 | 10313 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-08-15 | 2016-08-27 | 1 | Verify
10338 | 10338 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
10363 | 10363 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
10388 | 10388 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
10413 | 10413 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-08-15 | 2016-09-07 | 1 | Verify
10438 | 10438 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-08-15 | 2016-09-24 | 1 | Verify
10538 | 10538 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-18 | 2016-10-02 | 2 | Verify
10563 | 10563 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-18 |  | 2 | Pending
10588 | 10588 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-18 |  | 2 | Pending
10613 | 10613 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-10-19 |  | 2 | Pending
10638 | 10638 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-10-31 |  | 2 | Pending
10663 | 10663 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-10-31 |  | 2 | Pending
10688 | 10688 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-25 |  | 3 | Pending
10713 | 10713 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2017-01-14 |  | 3 | Pending
10738 | 10738 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-11-01 |  | 2 | Pending
10763 | 10763 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2017-01-14 |  | 3 | Pending
10788 | 10788 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
10813 | 10813 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-10-27 |  | 3 | Pending
10838 | 10838 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2017-01-14 |  | 3 | Pending
10863 | 10863 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2017-01-14 |  | 3 | Pending
10888 | 10888 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2017-01-14 |  | 3 | Pending
10913 | 10913 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2017-01-14 |  | 3 | Pending
10938 | 10938 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2017-01-14 |  | 3 | Pending
10963 | 10963 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
10988 | 10988 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11013 | 11013 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
11038 | 11038 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-11-23 |  | 3 | Pending
11063 | 11063 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-11-06 |  | 4 | Pending
11088 | 11088 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
11113 | 11113 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11138 | 11138 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-10-26 |  | 3 | Pending
11163 | 11163 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-11-01 |  | 3 | Pending
11188 | 11188 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-11-03 |  | 3 | Pending
11213 | 11213 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-11-01 |  | 3 | Pending
11238 | 11238 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
11263 | 11263 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
11288 | 11288 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11313 | 11313 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11338 | 11338 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11363 | 11363 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11388 | 11388 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11413 | 11413 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11438 | 11438 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11463 | 11463 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11488 | 11488 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
11513 | 11513 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-11-10 |  | 4 | Pending
11538 | 11538 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-17 | 2016-09-05 | 2 | Verify
11563 | 11563 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-17 | 2016-09-06 | 2 | Verify
11588 | 11588 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-17 | 2016-09-08 | 2 | Verify
11613 | 11613 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-17 | 2016-09-27 | 2 | Verify
11638 | 11638 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-17 | 2016-09-27 | 2 | Verify
11663 | 11663 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-29 |  | 2 | Pending
11688 | 11688 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-29 |  | 2 | Pending
11713 | 11713 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-29 |  | 2 | Pending
11738 | 11738 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-29 |  | 2 | Pending
11763 | 11763 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-29 |  | 2 | Pending
11788 | 11788 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-29 |  | 2 | Pending
11813 | 11813 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-29 |  | 2 | Pending
11838 | 11838 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
11863 | 11863 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
11888 | 11888 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
11913 | 11913 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
11938 | 11938 | Commisioning | Implementation Report_BTS_Commisioning | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
11963 | 11963 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
11988 | 11988 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12013 | 12013 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12038 | 12038 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12063 | 12063 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12088 | 12088 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
12138 | 12138 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12163 | 12163 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12188 | 12188 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12213 | 12213 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12288 | 12288 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12313 | 12313 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12338 | 12338 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12363 | 12363 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12388 | 12388 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12438 | 12438 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12463 | 12463 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-10-12 |  | 2 | Pending
12513 | 12513 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-10-12 |  | 2 | Pending
12613 | 12613 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12638 | 12638 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12663 | 12663 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12688 | 12688 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12713 | 12713 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12738 | 12738 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12751 | 12751 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-17 | 2016-08-15 | 1 | Verify
12776 | 12776 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-17 | 2016-08-16 | 1 | Verify
12801 | 12801 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-17 | 2016-08-16 | 1 | Verify
12826 | 12826 | Commisioning | Implementation Report_BTS_Commisioning | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-10-06 |  | 2 | Pending
12851 | 12851 | Commisioning | Implementation Report_BTS_Commisioning | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12876 | 12876 | Commisioning | Implementation Report_BTS_Commisioning | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12901 | 12901 | Commisioning | Implementation Report_BTS_Commisioning | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12926 | 12926 | Commisioning | Implementation Report_BTS_Commisioning | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12951 | 12951 | Commisioning | Implementation Report_BTS_Commisioning | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-10-17 |  | 3 | Pending
12976 | 12976 | Commisioning | Implementation Report_BTS_Commisioning | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
13001 | 13001 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13026 | 13026 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13051 | 13051 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13076 | 13076 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13101 | 13101 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13126 | 13126 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13151 | 13151 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13176 | 13176 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
13201 | 13201 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13226 | 13226 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-12-11 |  | 4 | Pending
13251 | 13251 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-12-11 |  | 4 | Pending
13276 | 13276 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-12-11 |  | 4 | Pending
13301 | 13301 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-12-11 |  | 4 | Pending
13326 | 13326 | Commisioning | Implementation Report_BTS_Commisioning | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-12-11 |  | 4 | Pending
13351 | 13351 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
13376 | 13376 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
13401 | 13401 | Commisioning | Implementation Report_BTS_Commisioning | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13426 | 13426 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13451 | 13451 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13476 | 13476 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13501 | 13501 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13526 | 13526 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13551 | 13551 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13576 | 13576 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13601 | 13601 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13626 | 13626 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13651 | 13651 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13676 | 13676 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13701 | 13701 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13726 | 13726 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13751 | 13751 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13776 | 13776 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13801 | 13801 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13826 | 13826 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13851 | 13851 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13876 | 13876 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13901 | 13901 | Commisioning | Implementation Report_BTS_Commisioning | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13926 | 13926 | Commisioning | Implementation Report_BTS_Commisioning | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13951 | 13951 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13976 | 13976 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-11-26 |  | 4 | Pending
14001 | 14001 | Commisioning | Implementation Report_BTS_Commisioning | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-11-26 |  | 4 | Pending
10004 | 10004 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
10029 | 10029 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
10054 | 10054 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
10104 | 10104 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
10129 | 10129 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
10179 | 10179 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
10204 | 10204 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
10254 | 10254 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-07-30 | 2016-08-01 | 1 | Verify
10279 | 10279 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-07-30 | 2016-08-01 | 1 | Verify
10304 | 10304 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-07-30 | 2016-08-01 | 1 | Verify
10329 | 10329 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-09-29 |  | 3 | Pending
10354 | 10354 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
10379 | 10379 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-09-29 |  | 3 | Pending
10404 | 10404 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-07-30 | 2016-08-01 | 1 | Verify
10429 | 10429 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-07-30 | 2016-08-01 | 1 | Verify
10529 | 10529 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
10554 | 10554 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
10579 | 10579 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
10604 | 10604 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-10-02 |  | 2 | Pending
10629 | 10629 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-10-08 |  | 2 | Pending
10654 | 10654 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-10-08 |  | 2 | Pending
10679 | 10679 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-05 |  | 3 | Pending
10704 | 10704 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2016-11-13 |  | 3 | Pending
10729 | 10729 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-10-09 |  | 2 | Pending
10754 | 10754 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2016-11-13 |  | 3 | Pending
10779 | 10779 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
10804 | 10804 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-10-06 |  | 3 | Pending
10829 | 10829 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2016-11-13 |  | 3 | Pending
10854 | 10854 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2016-11-13 |  | 3 | Pending
10879 | 10879 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2016-11-13 |  | 3 | Pending
10904 | 10904 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2016-11-13 |  | 3 | Pending
10929 | 10929 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2016-11-13 |  | 3 | Pending
10954 | 10954 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-10-12 |  | 3 | Pending
10979 | 10979 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11004 | 11004 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
11029 | 11029 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11054 | 11054 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-10-11 |  | 4 | Pending
11079 | 11079 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
11104 | 11104 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-10-07 |  | 3 | Pending
11129 | 11129 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-10-06 |  | 3 | Pending
11154 | 11154 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11179 | 11179 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
11204 | 11204 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11229 | 11229 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11254 | 11254 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11279 | 11279 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11304 | 11304 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11329 | 11329 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11354 | 11354 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11379 | 11379 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11404 | 11404 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11429 | 11429 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-10-04 |  | 3 | Pending
11454 | 11454 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-10-07 |  | 3 | Pending
11479 | 11479 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-09-21 |  | 3 | Pending
11504 | 11504 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
11529 | 11529 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
11554 | 11554 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
11579 | 11579 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
11604 | 11604 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
11629 | 11629 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-05 |  | 2 | Pending
11654 | 11654 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-10 |  | 2 | Pending
11679 | 11679 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-10 |  | 2 | Pending
11704 | 11704 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-10 |  | 2 | Pending
11729 | 11729 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-10 |  | 2 | Pending
11754 | 11754 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-10 |  | 2 | Pending
11779 | 11779 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-10 |  | 2 | Pending
11804 | 11804 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-10 |  | 2 | Pending
11829 | 11829 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-09-21 |  | 3 | Pending
11854 | 11854 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-09-21 |  | 3 | Pending
11879 | 11879 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-09-21 |  | 3 | Pending
11904 | 11904 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-09-21 |  | 3 | Pending
11929 | 11929 | Delivery | Implementation Report_BTS_Delivery | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-09-21 |  | 3 | Pending
11954 | 11954 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
11979 | 11979 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
12004 | 12004 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
12029 | 12029 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
12054 | 12054 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
12079 | 12079 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
12129 | 12129 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
12154 | 12154 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
12179 | 12179 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
12204 | 12204 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
12279 | 12279 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
12304 | 12304 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
12329 | 12329 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
12354 | 12354 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
12379 | 12379 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
12429 | 12429 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-10-10 |  | 3 | Pending
12454 | 12454 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-09-19 |  | 2 | Pending
12504 | 12504 | Delivery | Implementation Report_BTS_Delivery | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-09-19 |  | 2 | Pending
12604 | 12604 | Delivery | Implementation Report_BTS_Delivery | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
12629 | 12629 | Delivery | Implementation Report_BTS_Delivery | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
12654 | 12654 | Delivery | Implementation Report_BTS_Delivery | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
12679 | 12679 | Delivery | Implementation Report_BTS_Delivery | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
12704 | 12704 | Delivery | Implementation Report_BTS_Delivery | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
12729 | 12729 | Delivery | Implementation Report_BTS_Delivery | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
12752 | 12752 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-01 | 2016-08-01 | 1 | Verify
12777 | 12777 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-01 | 2016-08-01 | 1 | Verify
12802 | 12802 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-01 | 2016-08-01 | 1 | Verify
12827 | 12827 | Delivery | Implementation Report_BTS_Delivery | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-09-13 |  | 2 | Pending
12852 | 12852 | Delivery | Implementation Report_BTS_Delivery | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
12877 | 12877 | Delivery | Implementation Report_BTS_Delivery | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
12902 | 12902 | Delivery | Implementation Report_BTS_Delivery | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
12927 | 12927 | Delivery | Implementation Report_BTS_Delivery | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
12952 | 12952 | Delivery | Implementation Report_BTS_Delivery | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-09-24 |  | 3 | Pending
12977 | 12977 | Delivery | Implementation Report_BTS_Delivery | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
13002 | 13002 | Delivery | Implementation Report_BTS_Delivery | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13027 | 13027 | Delivery | Implementation Report_BTS_Delivery | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13052 | 13052 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13077 | 13077 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13102 | 13102 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13127 | 13127 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13152 | 13152 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13177 | 13177 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
13202 | 13202 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13227 | 13227 | Delivery | Implementation Report_BTS_Delivery | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13252 | 13252 | Delivery | Implementation Report_BTS_Delivery | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13277 | 13277 | Delivery | Implementation Report_BTS_Delivery | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13302 | 13302 | Delivery | Implementation Report_BTS_Delivery | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13327 | 13327 | Delivery | Implementation Report_BTS_Delivery | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13352 | 13352 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13377 | 13377 | Delivery | Implementation Report_BTS_Delivery | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13402 | 13402 | Delivery | Implementation Report_BTS_Delivery | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13427 | 13427 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13452 | 13452 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13477 | 13477 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13502 | 13502 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13527 | 13527 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13552 | 13552 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13577 | 13577 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13602 | 13602 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13627 | 13627 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13652 | 13652 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13677 | 13677 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13702 | 13702 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13727 | 13727 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13752 | 13752 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13777 | 13777 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13802 | 13802 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13827 | 13827 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13852 | 13852 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13877 | 13877 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13902 | 13902 | Delivery | Implementation Report_BTS_Delivery | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13927 | 13927 | Delivery | Implementation Report_BTS_Delivery | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
13952 | 13952 | Delivery | Implementation Report_BTS_Delivery | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13977 | 13977 | Delivery | Implementation Report_BTS_Delivery | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
14002 | 14002 | Delivery | Implementation Report_BTS_Delivery | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-10-28 |  | 4 | Pending
10010 | 10010 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-17 |  | 2 | Pending
10035 | 10035 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
10060 | 10060 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-17 | 2016-10-01 | 2 | Verify
10110 | 10110 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
10135 | 10135 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-17 | 2016-09-18 | 2 | Verify
10185 | 10185 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
10210 | 10210 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
10260 | 10260 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-08-14 | 2016-08-16 | 1 | Verify
10285 | 10285 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-08-14 | 2016-08-16 | 1 | Verify
10310 | 10310 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-08-14 | 2016-08-18 | 1 | Verify
10335 | 10335 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-10-17 |  | 3 | Pending
10360 | 10360 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
10385 | 10385 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-10-17 |  | 3 | Pending
10410 | 10410 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-08-14 | 2016-09-08 | 1 | Verify
10435 | 10435 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-08-14 | 2016-09-24 | 1 | Verify
10535 | 10535 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-17 | 2016-10-02 | 2 | Verify
10560 | 10560 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-17 |  | 2 | Pending
10585 | 10585 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-17 |  | 2 | Pending
10610 | 10610 | Installation | Implementation Report_BTS_Installation | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-10-18 |  | 2 | Pending
10635 | 10635 | Installation | Implementation Report_BTS_Installation | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-10-30 |  | 2 | Pending
10660 | 10660 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-10-30 |  | 2 | Pending
10685 | 10685 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-24 |  | 3 | Pending
10710 | 10710 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2017-01-13 |  | 3 | Pending
10735 | 10735 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-10-31 |  | 2 | Pending
10760 | 10760 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2017-01-13 |  | 3 | Pending
10785 | 10785 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
10810 | 10810 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-10-26 |  | 3 | Pending
10835 | 10835 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2017-01-13 |  | 3 | Pending
10860 | 10860 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2017-01-13 |  | 3 | Pending
10885 | 10885 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2017-01-13 |  | 3 | Pending
10910 | 10910 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2017-01-13 |  | 3 | Pending
10935 | 10935 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2017-01-13 |  | 3 | Pending
10960 | 10960 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-11-04 |  | 3 | Pending
10985 | 10985 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11010 | 11010 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
11035 | 11035 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-11-22 |  | 3 | Pending
11060 | 11060 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-11-05 |  | 4 | Pending
11085 | 11085 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
11110 | 11110 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-10-27 |  | 3 | Pending
11135 | 11135 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-10-25 |  | 3 | Pending
11160 | 11160 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-10-31 |  | 3 | Pending
11185 | 11185 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11210 | 11210 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-10-31 |  | 3 | Pending
11235 | 11235 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
11260 | 11260 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
11285 | 11285 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-10-21 |  | 3 | Pending
11310 | 11310 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-10-21 |  | 3 | Pending
11335 | 11335 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-10-21 |  | 3 | Pending
11360 | 11360 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-10-21 |  | 3 | Pending
11385 | 11385 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-10-21 |  | 3 | Pending
11410 | 11410 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-10-21 |  | 3 | Pending
11435 | 11435 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
11460 | 11460 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-10-27 |  | 3 | Pending
11485 | 11485 | Installation | Implementation Report_BTS_Installation | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
11510 | 11510 | Installation | Implementation Report_BTS_Installation | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-11-09 |  | 4 | Pending
11535 | 11535 | Installation | Implementation Report_BTS_Installation | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-16 | 2016-09-05 | 2 | Verify
11560 | 11560 | Installation | Implementation Report_BTS_Installation | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-16 | 2016-09-06 | 2 | Verify
11585 | 11585 | Installation | Implementation Report_BTS_Installation | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-16 | 2016-09-08 | 2 | Verify
11610 | 11610 | Installation | Implementation Report_BTS_Installation | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-16 | 2016-09-27 | 2 | Verify
11635 | 11635 | Installation | Implementation Report_BTS_Installation | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-16 | 2016-09-27 | 2 | Verify
11660 | 11660 | Installation | Implementation Report_BTS_Installation | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-28 |  | 2 | Pending
11685 | 11685 | Installation | Implementation Report_BTS_Installation | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-28 |  | 2 | Pending
11710 | 11710 | Installation | Implementation Report_BTS_Installation | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-28 |  | 2 | Pending
11735 | 11735 | Installation | Implementation Report_BTS_Installation | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-28 |  | 2 | Pending
11760 | 11760 | Installation | Implementation Report_BTS_Installation | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-28 |  | 2 | Pending
11785 | 11785 | Installation | Implementation Report_BTS_Installation | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-28 |  | 2 | Pending
11810 | 11810 | Installation | Implementation Report_BTS_Installation | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-28 |  | 2 | Pending
11835 | 11835 | Installation | Implementation Report_BTS_Installation | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
11860 | 11860 | Installation | Implementation Report_BTS_Installation | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
11885 | 11885 | Installation | Implementation Report_BTS_Installation | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
11910 | 11910 | Installation | Implementation Report_BTS_Installation | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
11935 | 11935 | Installation | Implementation Report_BTS_Installation | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-10-11 |  | 3 | Pending
11960 | 11960 | Installation | Implementation Report_BTS_Installation | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
11985 | 11985 | Installation | Implementation Report_BTS_Installation | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12010 | 12010 | Installation | Implementation Report_BTS_Installation | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12035 | 12035 | Installation | Implementation Report_BTS_Installation | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12060 | 12060 | Installation | Implementation Report_BTS_Installation | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12085 | 12085 | Installation | Implementation Report_BTS_Installation | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-11-26 |  | 4 | Pending
12135 | 12135 | Installation | Implementation Report_BTS_Installation | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12160 | 12160 | Installation | Implementation Report_BTS_Installation | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12185 | 12185 | Installation | Implementation Report_BTS_Installation | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12210 | 12210 | Installation | Implementation Report_BTS_Installation | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12285 | 12285 | Installation | Implementation Report_BTS_Installation | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12310 | 12310 | Installation | Implementation Report_BTS_Installation | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12335 | 12335 | Installation | Implementation Report_BTS_Installation | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12360 | 12360 | Installation | Implementation Report_BTS_Installation | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12385 | 12385 | Installation | Implementation Report_BTS_Installation | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12435 | 12435 | Installation | Implementation Report_BTS_Installation | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12460 | 12460 | Installation | Implementation Report_BTS_Installation | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-10-11 |  | 2 | Pending
12510 | 12510 | Installation | Implementation Report_BTS_Installation | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-10-11 |  | 2 | Pending
12610 | 12610 | Installation | Implementation Report_BTS_Installation | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12635 | 12635 | Installation | Implementation Report_BTS_Installation | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12660 | 12660 | Installation | Implementation Report_BTS_Installation | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12685 | 12685 | Installation | Implementation Report_BTS_Installation | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12710 | 12710 | Installation | Implementation Report_BTS_Installation | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12735 | 12735 | Installation | Implementation Report_BTS_Installation | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12753 | 12753 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-16 | 2016-08-16 | 1 | Verify
12778 | 12778 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-16 | 2016-08-16 | 1 | Verify
12803 | 12803 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-16 | 2016-08-16 | 1 | Verify
12828 | 12828 | Installation | Implementation Report_BTS_Installation | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-10-05 |  | 2 | Pending
12853 | 12853 | Installation | Implementation Report_BTS_Installation | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12878 | 12878 | Installation | Implementation Report_BTS_Installation | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12903 | 12903 | Installation | Implementation Report_BTS_Installation | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12928 | 12928 | Installation | Implementation Report_BTS_Installation | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12953 | 12953 | Installation | Implementation Report_BTS_Installation | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-10-16 |  | 3 | Pending
12978 | 12978 | Installation | Implementation Report_BTS_Installation | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
13003 | 13003 | Installation | Implementation Report_BTS_Installation | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13028 | 13028 | Installation | Implementation Report_BTS_Installation | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13053 | 13053 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13078 | 13078 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13103 | 13103 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13128 | 13128 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13153 | 13153 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13178 | 13178 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
13203 | 13203 | Installation | Implementation Report_BTS_Installation | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13228 | 13228 | Installation | Implementation Report_BTS_Installation | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-12-10 |  | 4 | Pending
13253 | 13253 | Installation | Implementation Report_BTS_Installation | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-12-10 |  | 4 | Pending
13278 | 13278 | Installation | Implementation Report_BTS_Installation | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-12-10 |  | 4 | Pending
13303 | 13303 | Installation | Implementation Report_BTS_Installation | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-12-10 |  | 4 | Pending
13328 | 13328 | Installation | Implementation Report_BTS_Installation | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-12-10 |  | 4 | Pending
13353 | 13353 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13378 | 13378 | Installation | Implementation Report_BTS_Installation | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13403 | 13403 | Installation | Implementation Report_BTS_Installation | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13428 | 13428 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
13453 | 13453 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
13478 | 13478 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
13503 | 13503 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
13528 | 13528 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
13553 | 13553 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13578 | 13578 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13603 | 13603 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13628 | 13628 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13653 | 13653 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13678 | 13678 | Installation | Implementation Report_BTS_Installation | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13703 | 13703 | Installation | Implementation Report_BTS_Installation | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13728 | 13728 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13753 | 13753 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13778 | 13778 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13803 | 13803 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13828 | 13828 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13853 | 13853 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13878 | 13878 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13903 | 13903 | Installation | Implementation Report_BTS_Installation | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13928 | 13928 | Installation | Implementation Report_BTS_Installation | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13953 | 13953 | Installation | Implementation Report_BTS_Installation | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-12-16 |  | 4 | Pending
13978 | 13978 | Installation | Implementation Report_BTS_Installation | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-11-25 |  | 4 | Pending
14003 | 14003 | Installation | Implementation Report_BTS_Installation | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-11-25 |  | 4 | Pending
10016 | 10016 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-19 |  | 2 | Pending
10041 | 10041 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
10066 | 10066 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-19 | 2016-10-01 | 2 | Verify
10116 | 10116 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
10141 | 10141 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-19 | 2016-09-18 | 2 | Verify
10191 | 10191 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
10216 | 10216 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
10266 | 10266 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-08-16 | 2016-08-19 | 1 | Verify
10291 | 10291 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-08-16 | 2016-08-19 | 1 | Verify
10316 | 10316 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-08-16 | 2016-08-28 | 1 | Verify
10341 | 10341 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
10366 | 10366 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
10391 | 10391 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
10416 | 10416 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-08-16 | 2016-09-08 | 1 | Verify
10441 | 10441 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-08-16 | 2016-09-25 | 1 | Verify
10541 | 10541 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-19 | 2016-10-02 | 2 | Verify
10566 | 10566 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-19 |  | 2 | Pending
10591 | 10591 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-19 |  | 2 | Pending
10616 | 10616 | Integration | Implementation Report_BTS_Integration | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-10-20 |  | 2 | Pending
10641 | 10641 | Integration | Implementation Report_BTS_Integration | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-11-01 |  | 2 | Pending
10666 | 10666 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-11-01 |  | 2 | Pending
10691 | 10691 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-26 |  | 3 | Pending
10716 | 10716 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2017-01-15 |  | 3 | Pending
10741 | 10741 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-11-02 |  | 2 | Pending
10766 | 10766 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2017-01-15 |  | 3 | Pending
10791 | 10791 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
10816 | 10816 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10841 | 10841 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2017-01-15 |  | 3 | Pending
10866 | 10866 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2017-01-15 |  | 3 | Pending
10891 | 10891 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2017-01-15 |  | 3 | Pending
10916 | 10916 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2017-01-15 |  | 3 | Pending
10941 | 10941 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2017-01-15 |  | 3 | Pending
10966 | 10966 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
10991 | 10991 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-10-24 |  | 3 | Pending
11016 | 11016 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
11041 | 11041 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-11-24 |  | 3 | Pending
11066 | 11066 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-11-07 |  | 4 | Pending
11091 | 11091 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
11116 | 11116 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-10-29 |  | 3 | Pending
11141 | 11141 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-10-27 |  | 3 | Pending
11166 | 11166 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11191 | 11191 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-11-04 |  | 3 | Pending
11216 | 11216 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11241 | 11241 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
11266 | 11266 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
11291 | 11291 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11316 | 11316 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11341 | 11341 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11366 | 11366 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11391 | 11391 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11416 | 11416 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11441 | 11441 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-10-24 |  | 3 | Pending
11466 | 11466 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-10-29 |  | 3 | Pending
11491 | 11491 | Integration | Implementation Report_BTS_Integration | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11516 | 11516 | Integration | Implementation Report_BTS_Integration | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-11-11 |  | 4 | Pending
11541 | 11541 | Integration | Implementation Report_BTS_Integration | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-18 | 2016-09-05 | 2 | Verify
11566 | 11566 | Integration | Implementation Report_BTS_Integration | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-18 | 2016-09-07 | 2 | Verify
11591 | 11591 | Integration | Implementation Report_BTS_Integration | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-18 | 2016-09-08 | 2 | Verify
11616 | 11616 | Integration | Implementation Report_BTS_Integration | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-18 | 2016-09-27 | 2 | Verify
11641 | 11641 | Integration | Implementation Report_BTS_Integration | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-18 | 2016-09-27 | 2 | Verify
11666 | 11666 | Integration | Implementation Report_BTS_Integration | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-30 |  | 2 | Pending
11691 | 11691 | Integration | Implementation Report_BTS_Integration | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-30 |  | 2 | Pending
11716 | 11716 | Integration | Implementation Report_BTS_Integration | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-30 |  | 2 | Pending
11741 | 11741 | Integration | Implementation Report_BTS_Integration | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-30 |  | 2 | Pending
11766 | 11766 | Integration | Implementation Report_BTS_Integration | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-30 |  | 2 | Pending
11791 | 11791 | Integration | Implementation Report_BTS_Integration | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-30 |  | 2 | Pending
11816 | 11816 | Integration | Implementation Report_BTS_Integration | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-30 |  | 2 | Pending
11841 | 11841 | Integration | Implementation Report_BTS_Integration | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11866 | 11866 | Integration | Implementation Report_BTS_Integration | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11891 | 11891 | Integration | Implementation Report_BTS_Integration | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11916 | 11916 | Integration | Implementation Report_BTS_Integration | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11941 | 11941 | Integration | Implementation Report_BTS_Integration | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-10-13 |  | 3 | Pending
11966 | 11966 | Integration | Implementation Report_BTS_Integration | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
11991 | 11991 | Integration | Implementation Report_BTS_Integration | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12016 | 12016 | Integration | Implementation Report_BTS_Integration | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12041 | 12041 | Integration | Implementation Report_BTS_Integration | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12066 | 12066 | Integration | Implementation Report_BTS_Integration | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12091 | 12091 | Integration | Implementation Report_BTS_Integration | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-11-28 |  | 4 | Pending
12141 | 12141 | Integration | Implementation Report_BTS_Integration | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
12166 | 12166 | Integration | Implementation Report_BTS_Integration | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12191 | 12191 | Integration | Implementation Report_BTS_Integration | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12216 | 12216 | Integration | Implementation Report_BTS_Integration | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
12291 | 12291 | Integration | Implementation Report_BTS_Integration | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12316 | 12316 | Integration | Implementation Report_BTS_Integration | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12341 | 12341 | Integration | Implementation Report_BTS_Integration | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12366 | 12366 | Integration | Implementation Report_BTS_Integration | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12391 | 12391 | Integration | Implementation Report_BTS_Integration | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-11-10 |  | 3 | Pending
12441 | 12441 | Integration | Implementation Report_BTS_Integration | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-11-09 |  | 3 | Pending
12466 | 12466 | Integration | Implementation Report_BTS_Integration | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-10-13 |  | 2 | Pending
12516 | 12516 | Integration | Implementation Report_BTS_Integration | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-10-13 |  | 2 | Pending
12616 | 12616 | Integration | Implementation Report_BTS_Integration | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
12641 | 12641 | Integration | Implementation Report_BTS_Integration | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
12666 | 12666 | Integration | Implementation Report_BTS_Integration | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
12691 | 12691 | Integration | Implementation Report_BTS_Integration | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
12716 | 12716 | Integration | Implementation Report_BTS_Integration | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
12741 | 12741 | Integration | Implementation Report_BTS_Integration | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
12754 | 12754 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-18 | 2016-08-16 | 1 | Verify
12779 | 12779 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-18 | 2016-08-18 | 1 | Verify
12804 | 12804 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-18 | 2016-08-18 | 1 | Verify
12829 | 12829 | Integration | Implementation Report_BTS_Integration | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-10-07 |  | 2 | Pending
12854 | 12854 | Integration | Implementation Report_BTS_Integration | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12879 | 12879 | Integration | Implementation Report_BTS_Integration | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12904 | 12904 | Integration | Implementation Report_BTS_Integration | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12929 | 12929 | Integration | Implementation Report_BTS_Integration | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12954 | 12954 | Integration | Implementation Report_BTS_Integration | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
12979 | 12979 | Integration | Implementation Report_BTS_Integration | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
13004 | 13004 | Integration | Implementation Report_BTS_Integration | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13029 | 13029 | Integration | Implementation Report_BTS_Integration | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13054 | 13054 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13079 | 13079 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13104 | 13104 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13129 | 13129 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13154 | 13154 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13179 | 13179 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-11-12 |  | 3 | Pending
13204 | 13204 | Integration | Implementation Report_BTS_Integration | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13229 | 13229 | Integration | Implementation Report_BTS_Integration | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13254 | 13254 | Integration | Implementation Report_BTS_Integration | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13279 | 13279 | Integration | Implementation Report_BTS_Integration | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13304 | 13304 | Integration | Implementation Report_BTS_Integration | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13329 | 13329 | Integration | Implementation Report_BTS_Integration | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13354 | 13354 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13379 | 13379 | Integration | Implementation Report_BTS_Integration | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13404 | 13404 | Integration | Implementation Report_BTS_Integration | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13429 | 13429 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13454 | 13454 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13479 | 13479 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13504 | 13504 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13529 | 13529 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13554 | 13554 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13579 | 13579 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13604 | 13604 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13629 | 13629 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13654 | 13654 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13679 | 13679 | Integration | Implementation Report_BTS_Integration | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13704 | 13704 | Integration | Implementation Report_BTS_Integration | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13729 | 13729 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13754 | 13754 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13779 | 13779 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13804 | 13804 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13829 | 13829 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13854 | 13854 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13879 | 13879 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13904 | 13904 | Integration | Implementation Report_BTS_Integration | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13929 | 13929 | Integration | Implementation Report_BTS_Integration | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13954 | 13954 | Integration | Implementation Report_BTS_Integration | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-12-18 |  | 4 | Pending
13979 | 13979 | Integration | Implementation Report_BTS_Integration | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
14004 | 14004 | Integration | Implementation Report_BTS_Integration | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
10007 | 10007 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-15 |  | 2 | Pending
10032 | 10032 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
10057 | 10057 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-15 | 2016-09-28 | 2 | Verify
10107 | 10107 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
10132 | 10132 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-15 | 2016-09-15 | 2 | Verify
10182 | 10182 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-11-10 |  | 4 | Pending
10207 | 10207 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-11-10 |  | 4 | Pending
10257 | 10257 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-08-13 | 2016-08-13 | 1 | Verify
10282 | 10282 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-08-13 | 2016-08-13 | 1 | Verify
10307 | 10307 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-08-13 | 2016-08-13 | 1 | Verify
10332 | 10332 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-10-15 |  | 3 | Pending
10357 | 10357 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-11-11 |  | 4 | Pending
10382 | 10382 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-10-15 |  | 3 | Pending
10407 | 10407 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-08-13 | 2016-08-13 | 1 | Verify
10432 | 10432 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-08-13 | 2016-09-16 | 1 | Verify
10532 | 10532 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-15 | 2016-09-27 | 2 | Verify
10557 | 10557 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-15 |  | 2 | Pending
10582 | 10582 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-15 |  | 2 | Pending
10607 | 10607 | MOS | Implementation Report_BTS_MOS | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-10-16 |  | 2 | Pending
10632 | 10632 | MOS | Implementation Report_BTS_MOS | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-10-28 |  | 2 | Pending
10657 | 10657 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-10-28 |  | 2 | Pending
10682 | 10682 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-22 |  | 3 | Pending
10707 | 10707 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2017-01-11 |  | 3 | Pending
10732 | 10732 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-10-29 |  | 2 | Pending
10757 | 10757 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2017-01-11 |  | 3 | Pending
10782 | 10782 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
10807 | 10807 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-10-24 |  | 3 | Pending
10832 | 10832 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2017-01-11 |  | 3 | Pending
10857 | 10857 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2017-01-11 |  | 3 | Pending
10882 | 10882 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2017-01-11 |  | 3 | Pending
10907 | 10907 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2017-01-11 |  | 3 | Pending
10932 | 10932 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2017-01-11 |  | 3 | Pending
10957 | 10957 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10982 | 10982 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-10-20 |  | 3 | Pending
11007 | 11007 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
11032 | 11032 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-11-20 |  | 3 | Pending
11057 | 11057 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-11-03 |  | 4 | Pending
11082 | 11082 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
11107 | 11107 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-10-25 |  | 3 | Pending
11132 | 11132 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
11157 | 11157 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-10-29 |  | 3 | Pending
11182 | 11182 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-10-31 |  | 3 | Pending
11207 | 11207 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-10-29 |  | 3 | Pending
11232 | 11232 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
11257 | 11257 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
11282 | 11282 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
11307 | 11307 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
11332 | 11332 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
11357 | 11357 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
11382 | 11382 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
11407 | 11407 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
11432 | 11432 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-10-20 |  | 3 | Pending
11457 | 11457 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-10-25 |  | 3 | Pending
11482 | 11482 | MOS | Implementation Report_BTS_MOS | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11507 | 11507 | MOS | Implementation Report_BTS_MOS | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-11-07 |  | 4 | Pending
11532 | 11532 | MOS | Implementation Report_BTS_MOS | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-14 | 2016-10-01 | 2 | Verify
11557 | 11557 | MOS | Implementation Report_BTS_MOS | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-14 | 2016-10-01 | 2 | Verify
11582 | 11582 | MOS | Implementation Report_BTS_MOS | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-14 | 2016-10-01 | 2 | Verify
11607 | 11607 | MOS | Implementation Report_BTS_MOS | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-14 | 2016-09-25 | 2 | Verify
11632 | 11632 | MOS | Implementation Report_BTS_MOS | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-14 | 2016-09-25 | 2 | Verify
11657 | 11657 | MOS | Implementation Report_BTS_MOS | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
11682 | 11682 | MOS | Implementation Report_BTS_MOS | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
11707 | 11707 | MOS | Implementation Report_BTS_MOS | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
11732 | 11732 | MOS | Implementation Report_BTS_MOS | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
11757 | 11757 | MOS | Implementation Report_BTS_MOS | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
11782 | 11782 | MOS | Implementation Report_BTS_MOS | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
11807 | 11807 | MOS | Implementation Report_BTS_MOS | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
11832 | 11832 | MOS | Implementation Report_BTS_MOS | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11857 | 11857 | MOS | Implementation Report_BTS_MOS | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11882 | 11882 | MOS | Implementation Report_BTS_MOS | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11907 | 11907 | MOS | Implementation Report_BTS_MOS | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11932 | 11932 | MOS | Implementation Report_BTS_MOS | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-10-09 |  | 3 | Pending
11957 | 11957 | MOS | Implementation Report_BTS_MOS | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
11982 | 11982 | MOS | Implementation Report_BTS_MOS | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12007 | 12007 | MOS | Implementation Report_BTS_MOS | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12032 | 12032 | MOS | Implementation Report_BTS_MOS | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12057 | 12057 | MOS | Implementation Report_BTS_MOS | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12082 | 12082 | MOS | Implementation Report_BTS_MOS | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
12132 | 12132 | MOS | Implementation Report_BTS_MOS | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-11-07 |  | 3 | Pending
12157 | 12157 | MOS | Implementation Report_BTS_MOS | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-11-04 |  | 3 | Pending
12182 | 12182 | MOS | Implementation Report_BTS_MOS | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-11-03 |  | 3 | Pending
12207 | 12207 | MOS | Implementation Report_BTS_MOS | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12282 | 12282 | MOS | Implementation Report_BTS_MOS | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12307 | 12307 | MOS | Implementation Report_BTS_MOS | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12332 | 12332 | MOS | Implementation Report_BTS_MOS | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12357 | 12357 | MOS | Implementation Report_BTS_MOS | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12382 | 12382 | MOS | Implementation Report_BTS_MOS | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-11-06 |  | 3 | Pending
12432 | 12432 | MOS | Implementation Report_BTS_MOS | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-11-05 |  | 3 | Pending
12457 | 12457 | MOS | Implementation Report_BTS_MOS | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-10-09 |  | 2 | Pending
12507 | 12507 | MOS | Implementation Report_BTS_MOS | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-10-09 |  | 2 | Pending
12607 | 12607 | MOS | Implementation Report_BTS_MOS | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12632 | 12632 | MOS | Implementation Report_BTS_MOS | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12657 | 12657 | MOS | Implementation Report_BTS_MOS | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12682 | 12682 | MOS | Implementation Report_BTS_MOS | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12707 | 12707 | MOS | Implementation Report_BTS_MOS | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12732 | 12732 | MOS | Implementation Report_BTS_MOS | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
12755 | 12755 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-15 | 2016-08-15 | 1 | Verify
12780 | 12780 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-15 | 2016-08-15 | 1 | Verify
12805 | 12805 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-15 | 2016-08-15 | 1 | Verify
12830 | 12830 | MOS | Implementation Report_BTS_MOS | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-10-03 |  | 2 | Pending
12855 | 12855 | MOS | Implementation Report_BTS_MOS | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-11-03 |  | 3 | Pending
12880 | 12880 | MOS | Implementation Report_BTS_MOS | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-11-03 |  | 3 | Pending
12905 | 12905 | MOS | Implementation Report_BTS_MOS | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-11-03 |  | 3 | Pending
12930 | 12930 | MOS | Implementation Report_BTS_MOS | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-11-03 |  | 3 | Pending
12955 | 12955 | MOS | Implementation Report_BTS_MOS | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
12980 | 12980 | MOS | Implementation Report_BTS_MOS | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-11-03 |  | 3 | Pending
13005 | 13005 | MOS | Implementation Report_BTS_MOS | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13030 | 13030 | MOS | Implementation Report_BTS_MOS | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13055 | 13055 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13080 | 13080 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13105 | 13105 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13130 | 13130 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13155 | 13155 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13180 | 13180 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-11-08 |  | 3 | Pending
13205 | 13205 | MOS | Implementation Report_BTS_MOS | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-11-19 |  | 4 | Pending
13230 | 13230 | MOS | Implementation Report_BTS_MOS | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-12-08 |  | 4 | Pending
13255 | 13255 | MOS | Implementation Report_BTS_MOS | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-12-08 |  | 4 | Pending
13280 | 13280 | MOS | Implementation Report_BTS_MOS | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-12-08 |  | 4 | Pending
13305 | 13305 | MOS | Implementation Report_BTS_MOS | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-12-08 |  | 4 | Pending
13330 | 13330 | MOS | Implementation Report_BTS_MOS | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-12-08 |  | 4 | Pending
13355 | 13355 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-11-11 |  | 4 | Pending
13380 | 13380 | MOS | Implementation Report_BTS_MOS | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-11-11 |  | 4 | Pending
13405 | 13405 | MOS | Implementation Report_BTS_MOS | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13430 | 13430 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
13455 | 13455 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
13480 | 13480 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
13505 | 13505 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
13530 | 13530 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
13555 | 13555 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13580 | 13580 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13605 | 13605 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13630 | 13630 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13655 | 13655 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13680 | 13680 | MOS | Implementation Report_BTS_MOS | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-11-13 |  | 4 | Pending
13705 | 13705 | MOS | Implementation Report_BTS_MOS | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13730 | 13730 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13755 | 13755 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13780 | 13780 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13805 | 13805 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13830 | 13830 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13855 | 13855 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13880 | 13880 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13905 | 13905 | MOS | Implementation Report_BTS_MOS | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13930 | 13930 | MOS | Implementation Report_BTS_MOS | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-11-18 |  | 4 | Pending
13955 | 13955 | MOS | Implementation Report_BTS_MOS | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-12-14 |  | 4 | Pending
13980 | 13980 | MOS | Implementation Report_BTS_MOS | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
14005 | 14005 | MOS | Implementation Report_BTS_MOS | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
10011 | 10011 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-10-03 |  | 2 | Pending
10036 | 10036 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-27 |  | 4 | Pending
10061 | 10061 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-10-03 | 2016-10-01 | 2 | Verify
10111 | 10111 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-27 |  | 4 | Pending
10136 | 10136 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-29 | 2016-09-18 | 2 | Verify
10186 | 10186 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-25 |  | 4 | Pending
10211 | 10211 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-25 |  | 4 | Pending
10261 | 10261 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-22 | 2016-08-18 | 1 | Verify
10286 | 10286 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-22 | 2016-08-18 | 1 | Verify
10311 | 10311 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-08-22 | 2016-08-28 | 1 | Verify
10336 | 10336 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-30 |  | 3 | Pending
10361 | 10361 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-26 |  | 4 | Pending
10386 | 10386 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-30 |  | 3 | Pending
10411 | 10411 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-08-22 | 2016-09-07 | 1 | Verify
10436 | 10436 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-08-22 | 2016-09-24 | 1 | Verify
10536 | 10536 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-10-03 | 2016-10-02 | 2 | Verify
10561 | 10561 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-10-06 |  | 2 | Pending
10586 | 10586 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-10-06 |  | 2 | Pending
10611 | 10611 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-31 |  | 2 | Pending
10636 | 10636 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-11-12 |  | 2 | Pending
10661 | 10661 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-11-12 |  | 2 | Pending
10686 | 10686 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-11-06 |  | 3 | Pending
10711 | 10711 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2017-01-26 |  | 3 | Pending
10736 | 10736 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-11-13 |  | 2 | Pending
10761 | 10761 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2017-01-26 |  | 3 | Pending
10786 | 10786 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-21 |  | 3 | Pending
10811 | 10811 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-11-08 |  | 3 | Pending
10836 | 10836 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2017-01-26 |  | 3 | Pending
10861 | 10861 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2017-01-26 |  | 3 | Pending
10886 | 10886 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2017-01-26 |  | 3 | Pending
10911 | 10911 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2017-01-26 |  | 3 | Pending
10936 | 10936 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2017-01-26 |  | 3 | Pending
10961 | 10961 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-17 |  | 3 | Pending
10986 | 10986 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-11-04 |  | 3 | Pending
11011 | 11011 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-12-05 |  | 4 | Pending
11036 | 11036 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-18 |  | 3 | Pending
11061 | 11061 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-12-05 |  | 4 | Pending
11086 | 11086 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-12-05 |  | 4 | Pending
11111 | 11111 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-11-09 |  | 3 | Pending
11136 | 11136 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-11-07 |  | 3 | Pending
11161 | 11161 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-11-13 |  | 3 | Pending
11186 | 11186 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-11-15 |  | 3 | Pending
11211 | 11211 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-11-13 |  | 3 | Pending
11236 | 11236 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-22 |  | 3 | Pending
11261 | 11261 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-22 |  | 3 | Pending
11286 | 11286 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-11-03 |  | 3 | Pending
11311 | 11311 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-11-03 |  | 3 | Pending
11336 | 11336 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-11-03 |  | 3 | Pending
11361 | 11361 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-11-03 |  | 3 | Pending
11386 | 11386 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-11-03 |  | 3 | Pending
11411 | 11411 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-11-03 |  | 3 | Pending
11436 | 11436 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-11-04 |  | 3 | Pending
11461 | 11461 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-11-09 |  | 3 | Pending
11486 | 11486 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-10-24 |  | 3 | Pending
11511 | 11511 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
11536 | 11536 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-09-09 | 2016-09-05 | 2 | Verify
11561 | 11561 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-09-09 | 2016-09-06 | 2 | Verify
11586 | 11586 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-09-09 | 2016-09-08 | 2 | Verify
11611 | 11611 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-09-09 | 2016-09-27 | 2 | Verify
11636 | 11636 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-09-09 | 2016-09-27 | 2 | Verify
11661 | 11661 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-10-13 |  | 2 | Pending
11686 | 11686 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-10-13 |  | 2 | Pending
11711 | 11711 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-10-13 |  | 2 | Pending
11736 | 11736 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-10-13 |  | 2 | Pending
11761 | 11761 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-10-13 |  | 2 | Pending
11786 | 11786 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-10-13 |  | 2 | Pending
11811 | 11811 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-10-13 |  | 2 | Pending
11836 | 11836 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-10-26 |  | 3 | Pending
11861 | 11861 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-10-26 |  | 3 | Pending
11886 | 11886 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-10-26 |  | 3 | Pending
11911 | 11911 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-10-26 |  | 3 | Pending
11936 | 11936 | Commisioning | Implementation Report_Tower and Power_Commisioning | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-10-26 |  | 3 | Pending
11961 | 11961 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-20 |  | 3 | Pending
11986 | 11986 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-20 |  | 3 | Pending
12011 | 12011 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-20 |  | 3 | Pending
12036 | 12036 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-20 |  | 3 | Pending
12061 | 12061 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-20 |  | 3 | Pending
12086 | 12086 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-30 |  | 4 | Pending
12136 | 12136 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-22 |  | 3 | Pending
12161 | 12161 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-19 |  | 3 | Pending
12186 | 12186 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-18 |  | 3 | Pending
12211 | 12211 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-23 |  | 3 | Pending
12286 | 12286 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-20 |  | 3 | Pending
12311 | 12311 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-21 |  | 3 | Pending
12336 | 12336 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-21 |  | 3 | Pending
12361 | 12361 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-20 |  | 3 | Pending
12386 | 12386 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-21 |  | 3 | Pending
12436 | 12436 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-20 |  | 3 | Pending
12461 | 12461 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-10 |  | 2 | Pending
12511 | 12511 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-10 |  | 2 | Pending
12611 | 12611 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-23 |  | 3 | Pending
12636 | 12636 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-23 |  | 3 | Pending
12661 | 12661 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-23 |  | 3 | Pending
12686 | 12686 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-23 |  | 3 | Pending
12711 | 12711 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-23 |  | 3 | Pending
12736 | 12736 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-23 |  | 3 | Pending
12756 | 12756 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-15 | 2016-08-15 | 1 | Verify
12781 | 12781 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-16 | 2016-08-16 | 1 | Verify
12806 | 12806 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-16 | 2016-08-16 | 1 | Verify
12831 | 12831 | Commisioning | Implementation Report_Tower and Power_Commisioning | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-10-04 |  | 2 | Pending
12856 | 12856 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-11-18 |  | 3 | Pending
12881 | 12881 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-11-18 |  | 3 | Pending
12906 | 12906 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-11-18 |  | 3 | Pending
12931 | 12931 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-11-18 |  | 3 | Pending
12956 | 12956 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-29 |  | 3 | Pending
12981 | 12981 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-11-18 |  | 3 | Pending
13006 | 13006 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-23 |  | 3 | Pending
13031 | 13031 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-23 |  | 3 | Pending
13056 | 13056 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-11-23 |  | 3 | Pending
13081 | 13081 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-11-23 |  | 3 | Pending
13106 | 13106 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-11-23 |  | 3 | Pending
13131 | 13131 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-11-23 |  | 3 | Pending
13156 | 13156 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-11-23 |  | 3 | Pending
13181 | 13181 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-11-23 |  | 3 | Pending
13206 | 13206 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13231 | 13231 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-23 |  | 4 | Pending
13256 | 13256 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-23 |  | 4 | Pending
13281 | 13281 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-23 |  | 4 | Pending
13306 | 13306 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-23 |  | 4 | Pending
13331 | 13331 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-23 |  | 4 | Pending
13356 | 13356 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13381 | 13381 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13406 | 13406 | Commisioning | Implementation Report_Tower and Power_Commisioning | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 4 | Verify
13431 | 13431 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13456 | 13456 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13481 | 13481 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13506 | 13506 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13531 | 13531 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13556 | 13556 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13581 | 13581 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13606 | 13606 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13631 | 13631 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13656 | 13656 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13681 | 13681 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13706 | 13706 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13731 | 13731 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13756 | 13756 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13781 | 13781 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13806 | 13806 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13831 | 13831 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13856 | 13856 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13881 | 13881 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13906 | 13906 | Commisioning | Implementation Report_Tower and Power_Commisioning | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13931 | 13931 | Commisioning | Implementation Report_Tower and Power_Commisioning | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-12-24 |  | 4 | Pending
13956 | 13956 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-12-08 |  | 4 | Pending
13981 | 13981 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-12-08 |  | 4 | Pending
14006 | 14006 | Commisioning | Implementation Report_Tower and Power_Commisioning | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-12-08 |  | 4 | Pending
10002 | 10002 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-09-04 | 2016-08-22 | 2 | Verify
10027 | 10027 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-10-28 |  | 4 | Pending
10052 | 10052 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-09-04 | 2016-08-22 | 2 | Verify
10102 | 10102 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-10-28 |  | 4 | Pending
10127 | 10127 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-02 | 2016-08-22 | 2 | Verify
10177 | 10177 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-10-28 |  | 4 | Pending
10202 | 10202 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-10-28 |  | 4 | Pending
10252 | 10252 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-07-26 | 2016-07-26 | 1 | Verify
10277 | 10277 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-07-26 | 2016-07-26 | 1 | Verify
10302 | 10302 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-07-26 | 2016-07-26 | 1 | Verify
10327 | 10327 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-09-29 | 2016-09-15 | 3 | Verify
10352 | 10352 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-10-28 |  | 4 | Pending
10377 | 10377 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-09-29 | 2016-09-15 | 3 | Verify
10402 | 10402 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-07-26 | 2016-07-26 | 1 | Verify
10427 | 10427 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-07-26 | 2016-07-26 | 1 | Verify
10527 | 10527 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-09-04 | 2016-08-22 | 2 | Verify
10552 | 10552 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-09-05 | 2016-08-22 | 2 | Verify
10577 | 10577 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-09-05 | 2016-08-22 | 2 | Verify
10602 | 10602 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-02 | 2016-09-23 | 2 | Verify
10627 | 10627 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-10-08 | 2016-09-20 | 2 | Verify
10652 | 10652 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-10-08 | 2016-09-20 | 2 | Verify
10677 | 10677 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-10-05 | 2016-09-20 | 3 | Verify
10702 | 10702 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2016-11-13 | 2016-09-15 | 3 | Verify
10727 | 10727 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-10-09 | 2016-09-15 | 2 | Verify
10752 | 10752 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2016-11-13 | 2016-09-15 | 3 | Verify
10777 | 10777 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-10-12 | 2016-10-03 | 3 | Verify
10802 | 10802 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-10-06 | 2016-09-20 | 3 | Verify
10827 | 10827 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2016-11-13 | 2016-09-15 | 3 | Verify
10852 | 10852 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2016-11-13 | 2016-09-15 | 3 | Verify
10877 | 10877 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2016-11-13 | 2016-09-15 | 3 | Verify
10902 | 10902 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2016-11-13 | 2016-09-15 | 3 | Verify
10927 | 10927 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2016-11-13 | 2016-09-15 | 3 | Verify
10952 | 10952 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-10-12 | 2016-10-03 | 3 | Verify
10977 | 10977 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-10-04 |  | 3 | Pending
11002 | 11002 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-10-28 |  | 4 | Pending
11027 | 11027 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-10-11 |  | 3 | Pending
11052 | 11052 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-10-28 |  | 4 | Pending
11077 | 11077 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-10-28 |  | 4 | Pending
11102 | 11102 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-10-07 |  | 3 | Pending
11127 | 11127 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-10-06 |  | 3 | Pending
11152 | 11152 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-10-09 |  | 3 | Pending
11177 | 11177 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-10-10 |  | 3 | Pending
11202 | 11202 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-10-09 |  | 3 | Pending
11227 | 11227 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-10-13 |  | 3 | Pending
11252 | 11252 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-10-13 |  | 3 | Pending
11277 | 11277 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-10-04 |  | 3 | Pending
11302 | 11302 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-10-04 |  | 3 | Pending
11327 | 11327 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-10-04 |  | 3 | Pending
11352 | 11352 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-10-04 |  | 3 | Pending
11377 | 11377 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-10-04 |  | 3 | Pending
11402 | 11402 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-10-04 |  | 3 | Pending
11427 | 11427 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-10-04 |  | 3 | Pending
11452 | 11452 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-10-07 |  | 3 | Pending
11477 | 11477 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-09-21 | 2016-09-03 | 3 | Verify
11502 | 11502 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
11527 | 11527 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-08-21 | 2016-08-08 | 2 | Verify
11552 | 11552 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-08-21 | 2016-08-08 | 2 | Verify
11577 | 11577 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-08-21 | 2016-08-08 | 2 | Verify
11602 | 11602 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-08-21 | 2016-08-08 | 2 | Verify
11627 | 11627 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-08-21 | 2016-08-08 | 2 | Verify
11652 | 11652 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-09-10 | 2016-08-24 | 2 | Verify
11677 | 11677 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-09-10 | 2016-08-24 | 2 | Verify
11702 | 11702 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-09-10 | 2016-08-24 | 2 | Verify
11727 | 11727 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-09-10 | 2016-08-24 | 2 | Verify
11752 | 11752 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-09-10 | 2016-08-24 | 2 | Verify
11777 | 11777 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-09-10 | 2016-08-24 | 2 | Verify
11802 | 11802 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-09-10 | 2016-08-24 | 2 | Verify
11827 | 11827 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-09-21 | 2016-09-03 | 3 | Verify
11852 | 11852 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-09-21 | 2016-09-03 | 3 | Verify
11877 | 11877 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-09-21 | 2016-09-03 | 3 | Verify
11902 | 11902 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-09-21 | 2016-09-03 | 3 | Verify
11927 | 11927 | Delivery | Implementation Report_Tower and Power_Delivery | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-09-21 | 2016-09-03 | 3 | Verify
11952 | 11952 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-10-10 | 2016-09-21 | 3 | Verify
11977 | 11977 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-10-10 | 2016-09-21 | 3 | Verify
12002 | 12002 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-10-10 | 2016-09-21 | 3 | Verify
12027 | 12027 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-10-10 | 2016-09-21 | 3 | Verify
12052 | 12052 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-10-10 | 2016-09-21 | 3 | Verify
12077 | 12077 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-11-18 |  | 4 | Pending
12127 | 12127 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-10-11 |  | 3 | Pending
12152 | 12152 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-10-11 |  | 3 | Pending
12177 | 12177 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-10-09 |  | 3 | Pending
12202 | 12202 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-10-11 |  | 3 | Pending
12277 | 12277 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-10-10 | 2016-09-24 | 3 | Verify
12302 | 12302 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-10-11 | 2016-09-24 | 3 | Verify
12327 | 12327 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-10-11 | 2016-09-24 | 3 | Verify
12352 | 12352 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-10-10 | 2016-09-24 | 3 | Verify
12377 | 12377 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-10-11 | 2016-09-24 | 3 | Verify
12427 | 12427 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-10-10 | 2016-09-24 | 3 | Verify
12452 | 12452 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-09-19 | 2016-09-24 | 2 | Verify
12502 | 12502 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-09-19 | 2016-09-24 | 2 | Verify
12602 | 12602 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-10-13 |  | 3 | Pending
12627 | 12627 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-10-13 |  | 3 | Pending
12652 | 12652 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-10-13 |  | 3 | Pending
12677 | 12677 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-10-13 |  | 3 | Pending
12702 | 12702 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-10-13 |  | 3 | Pending
12727 | 12727 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-10-13 |  | 3 | Pending
12757 | 12757 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12782 | 12782 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12807 | 12807 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12832 | 12832 | Delivery | Implementation Report_Tower and Power_Delivery | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-09-13 | 2016-09-15 | 2 | Verify
12857 | 12857 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-10-09 |  | 3 | Pending
12882 | 12882 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-10-09 |  | 3 | Pending
12907 | 12907 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-10-09 |  | 3 | Pending
12932 | 12932 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-10-09 |  | 3 | Pending
12957 | 12957 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-09-24 |  | 3 | Pending
12982 | 12982 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-10-09 |  | 3 | Pending
13007 | 13007 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-10-13 |  | 3 | Pending
13032 | 13032 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-10-13 |  | 3 | Pending
13057 | 13057 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-10-13 |  | 3 | Pending
13082 | 13082 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-10-13 |  | 3 | Pending
13107 | 13107 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-10-13 |  | 3 | Pending
13132 | 13132 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-10-13 |  | 3 | Pending
13157 | 13157 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-10-13 |  | 3 | Pending
13182 | 13182 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-10-13 |  | 3 | Pending
13207 | 13207 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13232 | 13232 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-11-18 |  | 4 | Pending
13257 | 13257 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-11-18 |  | 4 | Pending
13282 | 13282 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-11-18 |  | 4 | Pending
13307 | 13307 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-11-18 |  | 4 | Pending
13332 | 13332 | Delivery | Implementation Report_Tower and Power_Delivery | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-11-18 |  | 4 | Pending
13357 | 13357 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13382 | 13382 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13407 | 13407 | Delivery | Implementation Report_Tower and Power_Delivery | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 4 | Verify
13432 | 13432 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13457 | 13457 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13482 | 13482 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13507 | 13507 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13532 | 13532 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13557 | 13557 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13582 | 13582 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13607 | 13607 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13632 | 13632 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13657 | 13657 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13682 | 13682 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13707 | 13707 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13732 | 13732 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13757 | 13757 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13782 | 13782 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13807 | 13807 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13832 | 13832 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13857 | 13857 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13882 | 13882 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13907 | 13907 | Delivery | Implementation Report_Tower and Power_Delivery | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
13932 | 13932 | Delivery | Implementation Report_Tower and Power_Delivery | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-11-18 |  | 4 | Pending
13957 | 13957 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-10-28 |  | 4 | Pending
13982 | 13982 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-10-28 |  | 4 | Pending
14007 | 14007 | Delivery | Implementation Report_Tower and Power_Delivery | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-10-28 |  | 4 | Pending
10008 | 10008 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-10-02 |  | 2 | Pending
10033 | 10033 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-26 |  | 4 | Pending
10058 | 10058 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-10-02 | 2016-10-01 | 2 | Verify
10108 | 10108 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-26 |  | 4 | Pending
10133 | 10133 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-28 | 2016-09-18 | 2 | Verify
10183 | 10183 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-24 |  | 4 | Pending
10208 | 10208 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-24 |  | 4 | Pending
10258 | 10258 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-21 | 2016-08-16 | 1 | Verify
10283 | 10283 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-21 | 2016-08-16 | 1 | Verify
10308 | 10308 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-08-21 | 2016-08-27 | 1 | Verify
10333 | 10333 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-29 |  | 3 | Pending
10358 | 10358 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-25 |  | 4 | Pending
10383 | 10383 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-29 |  | 3 | Pending
10408 | 10408 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-08-21 | 2016-09-07 | 1 | Verify
10433 | 10433 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-08-21 | 2016-09-22 | 1 | Verify
10533 | 10533 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-10-02 | 2016-10-02 | 2 | Verify
10558 | 10558 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-10-05 |  | 2 | Pending
10583 | 10583 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-10-05 |  | 2 | Pending
10608 | 10608 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-30 |  | 2 | Pending
10633 | 10633 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-11-11 |  | 2 | Pending
10658 | 10658 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-11-11 |  | 2 | Pending
10683 | 10683 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-11-05 |  | 3 | Pending
10708 | 10708 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2017-01-25 |  | 3 | Pending
10733 | 10733 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-11-12 |  | 2 | Pending
10758 | 10758 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2017-01-25 |  | 3 | Pending
10783 | 10783 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-20 |  | 3 | Pending
10808 | 10808 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-11-07 |  | 3 | Pending
10833 | 10833 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2017-01-25 |  | 3 | Pending
10858 | 10858 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2017-01-25 |  | 3 | Pending
10883 | 10883 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2017-01-25 |  | 3 | Pending
10908 | 10908 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2017-01-25 |  | 3 | Pending
10933 | 10933 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2017-01-25 |  | 3 | Pending
10958 | 10958 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-16 |  | 3 | Pending
10983 | 10983 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-11-03 |  | 3 | Pending
11008 | 11008 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-12-04 |  | 4 | Pending
11033 | 11033 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-17 |  | 3 | Pending
11058 | 11058 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-12-04 |  | 4 | Pending
11083 | 11083 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-12-04 |  | 4 | Pending
11108 | 11108 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-11-08 |  | 3 | Pending
11133 | 11133 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-11-06 |  | 3 | Pending
11158 | 11158 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-11-12 |  | 3 | Pending
11183 | 11183 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-11-14 |  | 3 | Pending
11208 | 11208 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-11-12 |  | 3 | Pending
11233 | 11233 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-21 |  | 3 | Pending
11258 | 11258 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-21 |  | 3 | Pending
11283 | 11283 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-11-02 |  | 3 | Pending
11308 | 11308 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-11-02 |  | 3 | Pending
11333 | 11333 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-11-02 |  | 3 | Pending
11358 | 11358 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-11-02 |  | 3 | Pending
11383 | 11383 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-11-02 |  | 3 | Pending
11408 | 11408 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-11-02 |  | 3 | Pending
11433 | 11433 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-11-03 |  | 3 | Pending
11458 | 11458 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-11-08 |  | 3 | Pending
11483 | 11483 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-10-23 |  | 3 | Pending
11508 | 11508 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
11533 | 11533 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-09-08 | 2016-10-05 | 2 | Verify
11558 | 11558 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-09-08 | 2016-10-06 | 2 | Verify
11583 | 11583 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-09-08 | 2016-10-08 | 2 | Verify
11608 | 11608 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-09-08 | 2016-09-27 | 2 | Verify
11633 | 11633 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-09-08 | 2016-09-27 | 2 | Verify
11658 | 11658 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-10-12 |  | 2 | Pending
11683 | 11683 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-10-12 |  | 2 | Pending
11708 | 11708 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-10-12 |  | 2 | Pending
11733 | 11733 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-10-12 |  | 2 | Pending
11758 | 11758 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-10-12 |  | 2 | Pending
11783 | 11783 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-10-12 |  | 2 | Pending
11808 | 11808 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-10-12 |  | 2 | Pending
11833 | 11833 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-10-25 |  | 3 | Pending
11858 | 11858 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-10-25 |  | 3 | Pending
11883 | 11883 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-10-25 |  | 3 | Pending
11908 | 11908 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-10-25 |  | 3 | Pending
11933 | 11933 | Installation | Implementation Report_Tower and Power_Installation | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-10-25 |  | 3 | Pending
11958 | 11958 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-19 |  | 3 | Pending
11983 | 11983 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-19 |  | 3 | Pending
12008 | 12008 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-19 |  | 3 | Pending
12033 | 12033 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-19 |  | 3 | Pending
12058 | 12058 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-19 |  | 3 | Pending
12083 | 12083 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-29 |  | 4 | Pending
12133 | 12133 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-21 |  | 3 | Pending
12158 | 12158 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-18 |  | 3 | Pending
12183 | 12183 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-17 |  | 3 | Pending
12208 | 12208 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-22 |  | 3 | Pending
12283 | 12283 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-19 |  | 3 | Pending
12308 | 12308 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-20 |  | 3 | Pending
12333 | 12333 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-20 |  | 3 | Pending
12358 | 12358 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-19 |  | 3 | Pending
12383 | 12383 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-20 |  | 3 | Pending
12433 | 12433 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-19 |  | 3 | Pending
12458 | 12458 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-09 |  | 2 | Pending
12508 | 12508 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-09 |  | 2 | Pending
12608 | 12608 | Installation | Implementation Report_Tower and Power_Installation | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-22 |  | 3 | Pending
12633 | 12633 | Installation | Implementation Report_Tower and Power_Installation | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-22 |  | 3 | Pending
12658 | 12658 | Installation | Implementation Report_Tower and Power_Installation | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-22 |  | 3 | Pending
12683 | 12683 | Installation | Implementation Report_Tower and Power_Installation | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-22 |  | 3 | Pending
12708 | 12708 | Installation | Implementation Report_Tower and Power_Installation | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-22 |  | 3 | Pending
12733 | 12733 | Installation | Implementation Report_Tower and Power_Installation | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-22 |  | 3 | Pending
12758 | 12758 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12783 | 12783 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12808 | 12808 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12833 | 12833 | Installation | Implementation Report_Tower and Power_Installation | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-10-03 |  | 2 | Pending
12858 | 12858 | Installation | Implementation Report_Tower and Power_Installation | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-11-17 |  | 3 | Pending
12883 | 12883 | Installation | Implementation Report_Tower and Power_Installation | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-11-17 |  | 3 | Pending
12908 | 12908 | Installation | Implementation Report_Tower and Power_Installation | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-11-17 |  | 3 | Pending
12933 | 12933 | Installation | Implementation Report_Tower and Power_Installation | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-11-17 |  | 3 | Pending
12958 | 12958 | Installation | Implementation Report_Tower and Power_Installation | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-28 |  | 3 | Pending
12983 | 12983 | Installation | Implementation Report_Tower and Power_Installation | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-11-17 |  | 3 | Pending
13008 | 13008 | Installation | Implementation Report_Tower and Power_Installation | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-22 |  | 3 | Pending
13033 | 13033 | Installation | Implementation Report_Tower and Power_Installation | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-22 |  | 3 | Pending
13058 | 13058 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-11-22 |  | 3 | Pending
13083 | 13083 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-11-22 |  | 3 | Pending
13108 | 13108 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-11-22 |  | 3 | Pending
13133 | 13133 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-11-22 |  | 3 | Pending
13158 | 13158 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-11-22 |  | 3 | Pending
13183 | 13183 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-11-22 |  | 3 | Pending
13208 | 13208 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-12-03 |  | 4 | Pending
13233 | 13233 | Installation | Implementation Report_Tower and Power_Installation | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-22 |  | 4 | Pending
13258 | 13258 | Installation | Implementation Report_Tower and Power_Installation | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-22 |  | 4 | Pending
13283 | 13283 | Installation | Implementation Report_Tower and Power_Installation | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-22 |  | 4 | Pending
13308 | 13308 | Installation | Implementation Report_Tower and Power_Installation | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-22 |  | 4 | Pending
13333 | 13333 | Installation | Implementation Report_Tower and Power_Installation | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-22 |  | 4 | Pending
13358 | 13358 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13383 | 13383 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13408 | 13408 | Installation | Implementation Report_Tower and Power_Installation | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 4 | Verify
13433 | 13433 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-26 |  | 4 | Pending
13458 | 13458 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-26 |  | 4 | Pending
13483 | 13483 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-26 |  | 4 | Pending
13508 | 13508 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-26 |  | 4 | Pending
13533 | 13533 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-26 |  | 4 | Pending
13558 | 13558 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13583 | 13583 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13608 | 13608 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13633 | 13633 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13658 | 13658 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13683 | 13683 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13708 | 13708 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13733 | 13733 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13758 | 13758 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13783 | 13783 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13808 | 13808 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13833 | 13833 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13858 | 13858 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13883 | 13883 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13908 | 13908 | Installation | Implementation Report_Tower and Power_Installation | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-12-04 |  | 4 | Pending
13933 | 13933 | Installation | Implementation Report_Tower and Power_Installation | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-12-23 |  | 4 | Pending
13958 | 13958 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-12-07 |  | 4 | Pending
13983 | 13983 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-12-07 |  | 4 | Pending
14008 | 14008 | Installation | Implementation Report_Tower and Power_Installation | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-12-07 |  | 4 | Pending
10014 | 10014 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-10-04 |  | 2 | Pending
10039 | 10039 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-28 |  | 4 | Pending
10064 | 10064 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-10-04 | 2016-10-01 | 2 | Verify
10114 | 10114 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-28 |  | 4 | Pending
10139 | 10139 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-30 | 2016-09-18 | 2 | Verify
10189 | 10189 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-26 |  | 4 | Pending
10214 | 10214 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-26 |  | 4 | Pending
10264 | 10264 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-23 |  | 1 | Pending
10289 | 10289 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-23 |  | 1 | Pending
10314 | 10314 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-08-23 |  | 1 | Pending
10339 | 10339 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-31 |  | 3 | Pending
10364 | 10364 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-27 |  | 4 | Pending
10389 | 10389 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-31 |  | 3 | Pending
10414 | 10414 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-08-23 |  | 1 | Pending
10439 | 10439 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-08-23 |  | 1 | Pending
10539 | 10539 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-10-04 | 2016-10-02 | 2 | Verify
10564 | 10564 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-10-07 |  | 2 | Pending
10589 | 10589 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-10-07 |  | 2 | Pending
10614 | 10614 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-11-01 |  | 2 | Pending
10639 | 10639 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-11-13 |  | 2 | Pending
10664 | 10664 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-11-13 |  | 2 | Pending
10689 | 10689 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-11-07 |  | 3 | Pending
10714 | 10714 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2017-01-27 |  | 3 | Pending
10739 | 10739 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-11-14 |  | 2 | Pending
10764 | 10764 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2017-01-27 |  | 3 | Pending
10789 | 10789 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-22 |  | 3 | Pending
10814 | 10814 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-11-09 |  | 3 | Pending
10839 | 10839 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2017-01-27 |  | 3 | Pending
10864 | 10864 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2017-01-27 |  | 3 | Pending
10889 | 10889 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2017-01-27 |  | 3 | Pending
10914 | 10914 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2017-01-27 |  | 3 | Pending
10939 | 10939 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2017-01-27 |  | 3 | Pending
10964 | 10964 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-18 |  | 3 | Pending
10989 | 10989 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-11-05 |  | 3 | Pending
11014 | 11014 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-12-06 |  | 4 | Pending
11039 | 11039 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-19 |  | 3 | Pending
11064 | 11064 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-12-06 |  | 4 | Pending
11089 | 11089 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-12-06 |  | 4 | Pending
11114 | 11114 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-11-10 |  | 3 | Pending
11139 | 11139 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-11-08 |  | 3 | Pending
11164 | 11164 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-11-14 |  | 3 | Pending
11189 | 11189 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-11-16 |  | 3 | Pending
11214 | 11214 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-11-14 |  | 3 | Pending
11239 | 11239 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-23 |  | 3 | Pending
11264 | 11264 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-23 |  | 3 | Pending
11289 | 11289 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-11-04 |  | 3 | Pending
11314 | 11314 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-11-04 |  | 3 | Pending
11339 | 11339 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-11-04 |  | 3 | Pending
11364 | 11364 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-11-04 |  | 3 | Pending
11389 | 11389 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-11-04 |  | 3 | Pending
11414 | 11414 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-11-04 |  | 3 | Pending
11439 | 11439 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-11-05 |  | 3 | Pending
11464 | 11464 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-11-10 |  | 3 | Pending
11489 | 11489 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-10-25 |  | 3 | Pending
11514 | 11514 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
11539 | 11539 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-09-10 | 2016-09-05 | 2 | Verify
11564 | 11564 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-09-10 | 2016-09-06 | 2 | Verify
11589 | 11589 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-09-10 | 2016-09-08 | 2 | Verify
11614 | 11614 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-09-10 | 2016-09-27 | 2 | Verify
11639 | 11639 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-09-10 | 2016-09-27 | 2 | Verify
11664 | 11664 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-10-14 |  | 2 | Pending
11689 | 11689 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-10-14 |  | 2 | Pending
11714 | 11714 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-10-14 |  | 2 | Pending
11739 | 11739 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-10-14 |  | 2 | Pending
11764 | 11764 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-10-14 |  | 2 | Pending
11789 | 11789 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-10-14 |  | 2 | Pending
11814 | 11814 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-10-14 |  | 2 | Pending
11839 | 11839 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-10-27 |  | 3 | Pending
11864 | 11864 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-10-27 |  | 3 | Pending
11889 | 11889 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-10-27 |  | 3 | Pending
11914 | 11914 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-10-27 |  | 3 | Pending
11939 | 11939 | Integration | Implementation Report_Tower and Power_Integration | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-10-27 |  | 3 | Pending
11964 | 11964 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-21 |  | 3 | Pending
11989 | 11989 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-21 |  | 3 | Pending
12014 | 12014 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-21 |  | 3 | Pending
12039 | 12039 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-21 |  | 3 | Pending
12064 | 12064 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-21 |  | 3 | Pending
12089 | 12089 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-31 |  | 4 | Pending
12139 | 12139 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-23 |  | 3 | Pending
12164 | 12164 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-20 |  | 3 | Pending
12189 | 12189 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-19 |  | 3 | Pending
12214 | 12214 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-24 |  | 3 | Pending
12289 | 12289 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-21 |  | 3 | Pending
12314 | 12314 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-22 |  | 3 | Pending
12339 | 12339 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-22 |  | 3 | Pending
12364 | 12364 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-21 |  | 3 | Pending
12389 | 12389 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-22 |  | 3 | Pending
12439 | 12439 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-21 |  | 3 | Pending
12464 | 12464 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-11 |  | 2 | Pending
12514 | 12514 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-11 |  | 2 | Pending
12614 | 12614 | Integration | Implementation Report_Tower and Power_Integration | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-24 |  | 3 | Pending
12639 | 12639 | Integration | Implementation Report_Tower and Power_Integration | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-24 |  | 3 | Pending
12664 | 12664 | Integration | Implementation Report_Tower and Power_Integration | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-24 |  | 3 | Pending
12689 | 12689 | Integration | Implementation Report_Tower and Power_Integration | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-24 |  | 3 | Pending
12714 | 12714 | Integration | Implementation Report_Tower and Power_Integration | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-24 |  | 3 | Pending
12739 | 12739 | Integration | Implementation Report_Tower and Power_Integration | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-24 |  | 3 | Pending
12759 | 12759 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-16 | 2016-08-16 | 1 | Verify
12784 | 12784 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12809 | 12809 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12834 | 12834 | Integration | Implementation Report_Tower and Power_Integration | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-10-05 |  | 2 | Pending
12859 | 12859 | Integration | Implementation Report_Tower and Power_Integration | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-11-19 |  | 3 | Pending
12884 | 12884 | Integration | Implementation Report_Tower and Power_Integration | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-11-19 |  | 3 | Pending
12909 | 12909 | Integration | Implementation Report_Tower and Power_Integration | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-11-19 |  | 3 | Pending
12934 | 12934 | Integration | Implementation Report_Tower and Power_Integration | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-11-19 |  | 3 | Pending
12959 | 12959 | Integration | Implementation Report_Tower and Power_Integration | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-30 |  | 3 | Pending
12984 | 12984 | Integration | Implementation Report_Tower and Power_Integration | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-11-19 |  | 3 | Pending
13009 | 13009 | Integration | Implementation Report_Tower and Power_Integration | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-24 |  | 3 | Pending
13034 | 13034 | Integration | Implementation Report_Tower and Power_Integration | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-24 |  | 3 | Pending
13059 | 13059 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-11-24 |  | 3 | Pending
13084 | 13084 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-11-24 |  | 3 | Pending
13109 | 13109 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-11-24 |  | 3 | Pending
13134 | 13134 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-11-24 |  | 3 | Pending
13159 | 13159 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-11-24 |  | 3 | Pending
13184 | 13184 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-11-24 |  | 3 | Pending
13209 | 13209 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-12-05 |  | 4 | Pending
13234 | 13234 | Integration | Implementation Report_Tower and Power_Integration | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-24 |  | 4 | Pending
13259 | 13259 | Integration | Implementation Report_Tower and Power_Integration | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-24 |  | 4 | Pending
13284 | 13284 | Integration | Implementation Report_Tower and Power_Integration | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-24 |  | 4 | Pending
13309 | 13309 | Integration | Implementation Report_Tower and Power_Integration | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-24 |  | 4 | Pending
13334 | 13334 | Integration | Implementation Report_Tower and Power_Integration | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-24 |  | 4 | Pending
13359 | 13359 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13384 | 13384 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13409 | 13409 | Integration | Implementation Report_Tower and Power_Integration | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 4 | Verify
13434 | 13434 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13459 | 13459 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13484 | 13484 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13509 | 13509 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13534 | 13534 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13559 | 13559 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13584 | 13584 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13609 | 13609 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13634 | 13634 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13659 | 13659 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13684 | 13684 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13709 | 13709 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13734 | 13734 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13759 | 13759 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13784 | 13784 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13809 | 13809 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13834 | 13834 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13859 | 13859 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13884 | 13884 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13909 | 13909 | Integration | Implementation Report_Tower and Power_Integration | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-12-06 |  | 4 | Pending
13934 | 13934 | Integration | Implementation Report_Tower and Power_Integration | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-12-25 |  | 4 | Pending
13959 | 13959 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-12-09 |  | 4 | Pending
13984 | 13984 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-12-09 |  | 4 | Pending
14009 | 14009 | Integration | Implementation Report_Tower and Power_Integration | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-12-09 |  | 4 | Pending
10005 | 10005 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-09-18 | 2016-09-08 | 2 | Verify
10030 | 10030 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-12 |  | 4 | Pending
10055 | 10055 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-09-18 | 2016-09-08 | 2 | Verify
10105 | 10105 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-12 |  | 4 | Pending
10130 | 10130 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-14 | 2016-09-07 | 2 | Verify
10180 | 10180 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-10 |  | 4 | Pending
10205 | 10205 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-10 |  | 4 | Pending
10255 | 10255 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-09 | 2016-08-15 | 1 | Verify
10280 | 10280 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-09 | 2016-08-15 | 1 | Verify
10305 | 10305 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-08-09 | 2016-08-15 | 1 | Verify
10330 | 10330 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-15 |  | 3 | Pending
10355 | 10355 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-11 |  | 4 | Pending
10380 | 10380 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-15 |  | 3 | Pending
10405 | 10405 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-08-09 | 2016-09-07 | 1 | Verify
10430 | 10430 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-08-09 | 2016-09-16 | 1 | Verify
10530 | 10530 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-09-18 | 2016-09-08 | 2 | Verify
10555 | 10555 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-09-20 | 2016-09-19 | 2 | Verify
10580 | 10580 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-09-20 | 2016-09-19 | 2 | Verify
10605 | 10605 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-16 |  | 2 | Pending
10630 | 10630 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-10-28 |  | 2 | Pending
10655 | 10655 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-10-28 |  | 2 | Pending
10680 | 10680 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-10-22 |  | 3 | Pending
10705 | 10705 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2017-01-11 |  | 3 | Pending
10730 | 10730 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-10-29 |  | 2 | Pending
10755 | 10755 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2017-01-11 |  | 3 | Pending
10780 | 10780 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-06 |  | 3 | Pending
10805 | 10805 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-10-24 |  | 3 | Pending
10830 | 10830 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2017-01-11 |  | 3 | Pending
10855 | 10855 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2017-01-11 |  | 3 | Pending
10880 | 10880 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2017-01-11 |  | 3 | Pending
10905 | 10905 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2017-01-11 |  | 3 | Pending
10930 | 10930 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2017-01-11 |  | 3 | Pending
10955 | 10955 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-02 |  | 3 | Pending
10980 | 10980 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-10-20 |  | 3 | Pending
11005 | 11005 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-11-20 |  | 4 | Pending
11030 | 11030 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-03 |  | 3 | Pending
11055 | 11055 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-11-20 |  | 4 | Pending
11080 | 11080 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-11-20 |  | 4 | Pending
11105 | 11105 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-10-25 |  | 3 | Pending
11130 | 11130 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-10-23 |  | 3 | Pending
11155 | 11155 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-10-29 |  | 3 | Pending
11180 | 11180 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-10-31 |  | 3 | Pending
11205 | 11205 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-10-29 |  | 3 | Pending
11230 | 11230 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-07 |  | 3 | Pending
11255 | 11255 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-07 |  | 3 | Pending
11280 | 11280 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-10-19 |  | 3 | Pending
11305 | 11305 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-10-19 |  | 3 | Pending
11330 | 11330 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-10-19 |  | 3 | Pending
11355 | 11355 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-10-19 |  | 3 | Pending
11380 | 11380 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-10-19 |  | 3 | Pending
11405 | 11405 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-10-19 |  | 3 | Pending
11430 | 11430 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-10-20 |  | 3 | Pending
11455 | 11455 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-10-25 |  | 3 | Pending
11480 | 11480 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-10-09 |  | 3 | Pending
11505 | 11505 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
11530 | 11530 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-08-30 | 2016-08-20 | 2 | Verify
11555 | 11555 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-08-30 | 2016-08-20 | 2 | Verify
11580 | 11580 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-08-30 | 2016-08-20 | 2 | Verify
11605 | 11605 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-08-30 | 2016-08-21 | 2 | Verify
11630 | 11630 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-08-30 | 2016-08-21 | 2 | Verify
11655 | 11655 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-09-26 | 2016-08-19 | 2 | Verify
11680 | 11680 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-09-26 | 2016-08-19 | 2 | Verify
11705 | 11705 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-09-26 | 2016-08-19 | 2 | Verify
11730 | 11730 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-09-26 |  | 2 | Pending
11755 | 11755 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-09-26 |  | 2 | Pending
11780 | 11780 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-09-26 | 2016-10-02 | 2 | Verify
11805 | 11805 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-09-26 | 2016-08-19 | 2 | Verify
11830 | 11830 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-10-09 |  | 3 | Pending
11855 | 11855 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-10-09 |  | 3 | Pending
11880 | 11880 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-10-09 |  | 3 | Pending
11905 | 11905 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-10-09 |  | 3 | Pending
11930 | 11930 | MOS | Implementation Report_Tower and Power_MOS | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-10-09 |  | 3 | Pending
11955 | 11955 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-05 |  | 3 | Pending
11980 | 11980 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-05 |  | 3 | Pending
12005 | 12005 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-05 |  | 3 | Pending
12030 | 12030 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-05 |  | 3 | Pending
12055 | 12055 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-05 |  | 3 | Pending
12080 | 12080 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-15 |  | 4 | Pending
12130 | 12130 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-07 |  | 3 | Pending
12155 | 12155 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-04 |  | 3 | Pending
12180 | 12180 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-03 |  | 3 | Pending
12205 | 12205 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-08 |  | 3 | Pending
12280 | 12280 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-05 |  | 3 | Pending
12305 | 12305 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-06 |  | 3 | Pending
12330 | 12330 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-06 |  | 3 | Pending
12355 | 12355 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-05 |  | 3 | Pending
12380 | 12380 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-06 |  | 3 | Pending
12430 | 12430 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-05 |  | 3 | Pending
12455 | 12455 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-09 |  | 2 | Pending
12505 | 12505 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-09 |  | 2 | Pending
12605 | 12605 | MOS | Implementation Report_Tower and Power_MOS | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-08 |  | 3 | Pending
12630 | 12630 | MOS | Implementation Report_Tower and Power_MOS | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-08 |  | 3 | Pending
12655 | 12655 | MOS | Implementation Report_Tower and Power_MOS | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-08 |  | 3 | Pending
12680 | 12680 | MOS | Implementation Report_Tower and Power_MOS | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-08 |  | 3 | Pending
12705 | 12705 | MOS | Implementation Report_Tower and Power_MOS | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-08 |  | 3 | Pending
12730 | 12730 | MOS | Implementation Report_Tower and Power_MOS | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-08 |  | 3 | Pending
12760 | 12760 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12785 | 12785 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12810 | 12810 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 1 | Verify
12835 | 12835 | MOS | Implementation Report_Tower and Power_MOS | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-10-03 |  | 2 | Pending
12860 | 12860 | MOS | Implementation Report_Tower and Power_MOS | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-11-03 |  | 3 | Pending
12885 | 12885 | MOS | Implementation Report_Tower and Power_MOS | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-11-03 |  | 3 | Pending
12910 | 12910 | MOS | Implementation Report_Tower and Power_MOS | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-11-03 |  | 3 | Pending
12935 | 12935 | MOS | Implementation Report_Tower and Power_MOS | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-11-03 |  | 3 | Pending
12960 | 12960 | MOS | Implementation Report_Tower and Power_MOS | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-14 |  | 3 | Pending
12985 | 12985 | MOS | Implementation Report_Tower and Power_MOS | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-11-03 |  | 3 | Pending
13010 | 13010 | MOS | Implementation Report_Tower and Power_MOS | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-08 |  | 3 | Pending
13035 | 13035 | MOS | Implementation Report_Tower and Power_MOS | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-08 |  | 3 | Pending
13060 | 13060 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-11-08 |  | 3 | Pending
13085 | 13085 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-11-08 |  | 3 | Pending
13110 | 13110 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-11-08 |  | 3 | Pending
13135 | 13135 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-11-08 |  | 3 | Pending
13160 | 13160 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-11-08 |  | 3 | Pending
13185 | 13185 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-11-08 |  | 3 | Pending
13210 | 13210 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-11-19 |  | 4 | Pending
13235 | 13235 | MOS | Implementation Report_Tower and Power_MOS | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-08 |  | 4 | Pending
13260 | 13260 | MOS | Implementation Report_Tower and Power_MOS | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-08 |  | 4 | Pending
13285 | 13285 | MOS | Implementation Report_Tower and Power_MOS | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-08 |  | 4 | Pending
13310 | 13310 | MOS | Implementation Report_Tower and Power_MOS | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-08 |  | 4 | Pending
13335 | 13335 | MOS | Implementation Report_Tower and Power_MOS | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-08 |  | 4 | Pending
13360 | 13360 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13385 | 13385 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-08-01 | 2016-08-01 | 4 | Verify
13410 | 13410 | MOS | Implementation Report_Tower and Power_MOS | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-08-01 | 2016-08-01 | 4 | Verify
13435 | 13435 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-12 |  | 4 | Pending
13460 | 13460 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-12 |  | 4 | Pending
13485 | 13485 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-12 |  | 4 | Pending
13510 | 13510 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-12 |  | 4 | Pending
13535 | 13535 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-12 |  | 4 | Pending
13560 | 13560 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-13 |  | 4 | Pending
13585 | 13585 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-13 |  | 4 | Pending
13610 | 13610 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-13 |  | 4 | Pending
13635 | 13635 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-13 |  | 4 | Pending
13660 | 13660 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-13 |  | 4 | Pending
13685 | 13685 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-13 |  | 4 | Pending
13710 | 13710 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13735 | 13735 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13760 | 13760 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13785 | 13785 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13810 | 13810 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13835 | 13835 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13860 | 13860 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13885 | 13885 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13910 | 13910 | MOS | Implementation Report_Tower and Power_MOS | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-11-20 |  | 4 | Pending
13935 | 13935 | MOS | Implementation Report_Tower and Power_MOS | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-12-09 |  | 4 | Pending
13960 | 13960 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-11-23 |  | 4 | Pending
13985 | 13985 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-11-23 |  | 4 | Pending
14010 | 14010 | MOS | Implementation Report_Tower and Power_MOS | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-11-23 |  | 4 | Pending
10012 | 10012 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | AJN | 2016-09-18 |  | 2 | Pending
10037 | 10037 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | LA | 2016-11-15 |  | 4 | Pending
10062 | 10062 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | AJN | 2016-09-18 | 2016-10-01 | 2 | Verify
10112 | 10112 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | LA | 2016-11-15 |  | 4 | Pending
10137 | 10137 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | AJN | 2016-09-18 | 2016-09-18 | 2 | Verify
10187 | 10187 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | AJN | 2016-11-13 |  | 4 | Pending
10212 | 10212 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | AJN | 2016-11-13 |  | 4 | Pending
10262 | 10262 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | DTP | 2016-08-12 | 2016-08-18 | 1 | Verify
10287 | 10287 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | DTP | 2016-08-12 | 2016-08-18 | 1 | Verify
10312 | 10312 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | AJN | 2016-08-12 | 2016-08-27 | 1 | Verify
10337 | 10337 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | AJN | 2016-10-18 |  | 3 | Pending
10362 | 10362 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | AJN | 2016-11-14 |  | 4 | Pending
10387 | 10387 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | AJN | 2016-10-18 |  | 3 | Pending
10412 | 10412 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | AJN | 2016-08-12 | 2016-09-07 | 1 | Verify
10437 | 10437 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | AJN | 2016-08-12 | 2016-09-24 | 1 | Verify
10537 | 10537 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | AJN | 2016-09-18 | 2016-10-02 | 2 | Verify
10562 | 10562 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | AJN | 2016-09-18 |  | 2 | Pending
10587 | 10587 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | AJN | 2016-09-18 |  | 2 | Pending
10612 | 10612 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOM | 2016-10-19 |  | 2 | Pending
10637 | 10637 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOM | 2016-10-31 |  | 2 | Pending
10662 | 10662 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOM | 2016-10-31 |  | 2 | Pending
10687 | 10687 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | IPT | 2016-10-25 |  | 3 | Pending
10712 | 10712 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | LA | 2017-01-14 |  | 3 | Pending
10737 | 10737 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOM | 2016-11-01 |  | 2 | Pending
10762 | 10762 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | LA | 2017-01-14 |  | 3 | Pending
10787 | 10787 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | IPT | 2016-11-09 |  | 3 | Pending
10812 | 10812 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | IPT | 2016-10-27 |  | 3 | Pending
10837 | 10837 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | LA | 2017-01-14 |  | 3 | Pending
10862 | 10862 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | LA | 2017-01-14 |  | 3 | Pending
10887 | 10887 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | LA | 2017-01-14 |  | 3 | Pending
10912 | 10912 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | LA | 2017-01-14 |  | 3 | Pending
10937 | 10937 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | LA | 2017-01-14 |  | 3 | Pending
10962 | 10962 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | IPT | 2016-11-05 |  | 3 | Pending
10987 | 10987 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | LA | 2016-10-23 |  | 3 | Pending
11012 | 11012 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | LA | 2016-11-23 |  | 4 | Pending
11037 | 11037 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | LA | 2016-11-23 |  | 3 | Pending
11062 | 11062 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | IPT | 2016-11-06 |  | 4 | Pending
11087 | 11087 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | IPT | 2016-11-23 |  | 4 | Pending
11112 | 11112 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | IPT | 2016-10-28 |  | 3 | Pending
11137 | 11137 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | AJN | 2016-10-26 |  | 3 | Pending
11162 | 11162 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | AJN | 2016-11-01 |  | 3 | Pending
11187 | 11187 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | IPT | 2016-11-03 |  | 3 | Pending
11212 | 11212 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | IPT | 2016-11-01 |  | 3 | Pending
11237 | 11237 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | IPT | 2016-11-10 |  | 3 | Pending
11262 | 11262 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | IPT | 2016-11-10 |  | 3 | Pending
11287 | 11287 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | AJN | 2016-10-22 |  | 3 | Pending
11312 | 11312 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | AJN | 2016-10-22 |  | 3 | Pending
11337 | 11337 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | AJN | 2016-10-22 |  | 3 | Pending
11362 | 11362 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | AJN | 2016-10-22 |  | 3 | Pending
11387 | 11387 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | IPT | 2016-10-22 |  | 3 | Pending
11412 | 11412 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | IPT | 2016-10-22 |  | 3 | Pending
11437 | 11437 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | IPT | 2016-10-23 |  | 3 | Pending
11462 | 11462 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | AJN | 2016-10-28 |  | 3 | Pending
11487 | 11487 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | MMP | 2016-10-12 |  | 3 | Pending
11512 | 11512 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | MMP | 2016-11-10 |  | 4 | Pending
11537 | 11537 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | AJN | 2016-09-17 | 2016-09-05 | 2 | Verify
11562 | 11562 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | AJN | 2016-09-17 | 2016-09-06 | 2 | Verify
11587 | 11587 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | AJN | 2016-09-17 | 2016-09-08 | 2 | Verify
11612 | 11612 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | AJN | 2016-09-17 | 2016-09-27 | 2 | Verify
11637 | 11637 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | AJN | 2016-09-17 | 2016-09-27 | 2 | Verify
11662 | 11662 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOM | 2016-09-29 |  | 2 | Pending
11687 | 11687 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | IPT | 2016-09-29 |  | 2 | Pending
11712 | 11712 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOM | 2016-09-29 |  | 2 | Pending
11737 | 11737 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | IPT | 2016-09-29 |  | 2 | Pending
11762 | 11762 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | IPT | 2016-09-29 |  | 2 | Pending
11787 | 11787 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | IPT | 2016-09-29 |  | 2 | Pending
11812 | 11812 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | IPT | 2016-09-29 |  | 2 | Pending
11837 | 11837 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | MMP | 2016-10-12 |  | 3 | Pending
11862 | 11862 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | MMP | 2016-10-12 |  | 3 | Pending
11887 | 11887 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | MMP | 2016-10-12 |  | 3 | Pending
11912 | 11912 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | MMP | 2016-10-12 |  | 3 | Pending
11937 | 11937 | Commisioning | Implementation Report_VSAT_Commisioning | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | MMP | 2016-10-12 |  | 3 | Pending
11962 | 11962 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | IPT | 2016-11-08 |  | 3 | Pending
11987 | 11987 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | IPT | 2016-11-08 |  | 3 | Pending
12012 | 12012 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | AJN | 2016-11-08 |  | 3 | Pending
12037 | 12037 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | AJN | 2016-11-08 |  | 3 | Pending
12062 | 12062 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | AJN | 2016-11-08 |  | 3 | Pending
12087 | 12087 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | AJN | 2016-11-27 |  | 4 | Pending
12137 | 12137 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | IPT | 2016-11-10 |  | 3 | Pending
12162 | 12162 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | IPT | 2016-11-07 |  | 3 | Pending
12187 | 12187 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | IPT | 2016-11-06 |  | 3 | Pending
12212 | 12212 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | IPT | 2016-11-11 |  | 3 | Pending
12287 | 12287 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | AJN | 2016-11-08 |  | 3 | Pending
12312 | 12312 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | AJN | 2016-11-09 |  | 3 | Pending
12337 | 12337 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | AJN | 2016-11-09 |  | 3 | Pending
12362 | 12362 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | AJN | 2016-11-08 |  | 3 | Pending
12387 | 12387 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | AJN | 2016-11-09 |  | 3 | Pending
12437 | 12437 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | AJN | 2016-11-08 |  | 3 | Pending
12462 | 12462 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOM | 2016-10-12 |  | 2 | Pending
12512 | 12512 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOM | 2016-10-12 |  | 2 | Pending
12612 | 12612 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | MMP | 2016-11-11 |  | 3 | Pending
12637 | 12637 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | MMP | 2016-11-11 |  | 3 | Pending
12662 | 12662 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | MMP | 2016-11-11 |  | 3 | Pending
12687 | 12687 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | MMP | 2016-11-11 |  | 3 | Pending
12712 | 12712 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | MMP | 2016-11-11 |  | 3 | Pending
12737 | 12737 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | MMP | 2016-11-11 |  | 3 | Pending
12761 | 12761 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | MMP | 2016-08-18 | 2016-08-15 | 1 | Verify
12786 | 12786 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | MMP | 2016-08-18 | 2016-08-16 | 1 | Verify
12811 | 12811 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | MMP | 2016-08-18 | 2016-08-16 | 1 | Verify
12836 | 12836 | Commisioning | Implementation Report_VSAT_Commisioning | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | AJN | 2016-10-06 |  | 2 | Pending
12861 | 12861 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | MMP | 2016-11-06 |  | 3 | Pending
12886 | 12886 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | MMP | 2016-11-06 |  | 3 | Pending
12911 | 12911 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | MMP | 2016-11-06 |  | 3 | Pending
12936 | 12936 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | MMP | 2016-11-06 |  | 3 | Pending
12961 | 12961 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | IPT | 2016-10-17 |  | 3 | Pending
12986 | 12986 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | MMP | 2016-11-06 |  | 3 | Pending
13011 | 13011 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | MMP | 2016-11-11 |  | 3 | Pending
13036 | 13036 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | MMP | 2016-11-11 |  | 3 | Pending
13061 | 13061 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | MMP | 2016-11-11 |  | 3 | Pending
13086 | 13086 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | MMP | 2016-11-11 |  | 3 | Pending
13111 | 13111 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | MMP | 2016-11-11 |  | 3 | Pending
13136 | 13136 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | MMP | 2016-11-11 |  | 3 | Pending
13161 | 13161 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | MMP | 2016-11-11 |  | 3 | Pending
13186 | 13186 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | MMP | 2016-11-11 |  | 3 | Pending
13211 | 13211 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13236 | 13236 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | MMP | 2016-12-11 |  | 4 | Pending
13261 | 13261 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | MMP | 2016-12-11 |  | 4 | Pending
13286 | 13286 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | MMP | 2016-12-11 |  | 4 | Pending
13311 | 13311 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | MMP | 2016-12-11 |  | 4 | Pending
13336 | 13336 | Commisioning | Implementation Report_VSAT_Commisioning | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | MMP | 2016-12-11 |  | 4 | Pending
13361 | 13361 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-11-14 |  | 4 | Pending
13386 | 13386 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-11-14 |  | 4 | Pending
13411 | 13411 | Commisioning | Implementation Report_VSAT_Commisioning | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13436 | 13436 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13461 | 13461 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13486 | 13486 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13511 | 13511 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13536 | 13536 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13561 | 13561 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13586 | 13586 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13611 | 13611 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13636 | 13636 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13661 | 13661 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13686 | 13686 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13711 | 13711 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13736 | 13736 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13761 | 13761 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13786 | 13786 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13811 | 13811 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13836 | 13836 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13861 | 13861 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13886 | 13886 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13911 | 13911 | Commisioning | Implementation Report_VSAT_Commisioning | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13936 | 13936 | Commisioning | Implementation Report_VSAT_Commisioning | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13961 | 13961 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-12-17 |  | 4 | Pending
13986 | 13986 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-11-26 |  | 4 | Pending
14011 | 14011 | Commisioning | Implementation Report_VSAT_Commisioning | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-11-26 |  | 4 | Pending
10003 | 10003 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | AJN | 2016-09-05 | 2016-08-25 | 2 | Verify
10028 | 10028 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | LA | 2016-10-28 |  | 4 | Pending
10053 | 10053 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | AJN | 2016-09-05 | 2016-08-25 | 2 | Verify
10103 | 10103 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | LA | 2016-10-28 |  | 4 | Pending
10128 | 10128 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | AJN | 2016-09-05 | 2016-08-25 | 2 | Verify
10178 | 10178 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | AJN | 2016-10-28 |  | 4 | Pending
10203 | 10203 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | AJN | 2016-10-28 |  | 4 | Pending
10253 | 10253 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | DTP | 2016-07-26 | 2016-07-30 | 1 | Verify
10278 | 10278 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | DTP | 2016-07-26 | 2016-07-30 | 1 | Verify
10303 | 10303 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | AJN | 2016-07-26 | 2016-07-26 | 1 | Verify
10328 | 10328 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | AJN | 2016-09-29 | 2016-09-19 | 3 | Verify
10353 | 10353 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | AJN | 2016-10-28 |  | 4 | Pending
10378 | 10378 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | AJN | 2016-09-29 | 2016-09-19 | 3 | Verify
10403 | 10403 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | AJN | 2016-07-26 | 2016-07-26 | 1 | Verify
10428 | 10428 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | AJN | 2016-07-26 | 2016-07-26 | 1 | Verify
10528 | 10528 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | AJN | 2016-09-05 | 2016-08-25 | 2 | Verify
10553 | 10553 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | AJN | 2016-09-05 | 2016-08-25 | 2 | Verify
10578 | 10578 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | AJN | 2016-09-05 | 2016-08-25 | 2 | Verify
10603 | 10603 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOM | 2016-10-02 |  | 2 | Pending
10628 | 10628 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOM | 2016-10-08 |  | 2 | Pending
10653 | 10653 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOM | 2016-10-08 |  | 2 | Pending
10678 | 10678 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | IPT | 2016-10-05 |  | 3 | Pending
10703 | 10703 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | LA | 2016-11-13 |  | 3 | Pending
10728 | 10728 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOM | 2016-10-09 | 2016-10-03 | 2 | Verify
10753 | 10753 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | LA | 2016-11-13 |  | 3 | Pending
10778 | 10778 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | IPT | 2016-10-12 |  | 3 | Pending
10803 | 10803 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | IPT | 2016-10-06 |  | 3 | Pending
10828 | 10828 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | LA | 2016-11-13 |  | 3 | Pending
10853 | 10853 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | LA | 2016-11-13 |  | 3 | Pending
10878 | 10878 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | LA | 2016-11-13 |  | 3 | Pending
10903 | 10903 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | LA | 2016-11-13 |  | 3 | Pending
10928 | 10928 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | LA | 2016-11-13 |  | 3 | Pending
10953 | 10953 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | IPT | 2016-10-12 |  | 3 | Pending
10978 | 10978 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | LA | 2016-10-04 |  | 3 | Pending
11003 | 11003 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | LA | 2016-10-28 |  | 4 | Pending
11028 | 11028 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | LA | 2016-10-28 |  | 3 | Pending
11053 | 11053 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | IPT | 2016-10-11 |  | 4 | Pending
11078 | 11078 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | IPT | 2016-10-28 |  | 4 | Pending
11103 | 11103 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | IPT | 2016-10-07 |  | 3 | Pending
11128 | 11128 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | AJN | 2016-10-06 |  | 3 | Pending
11153 | 11153 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | AJN | 2016-10-09 |  | 3 | Pending
11178 | 11178 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | IPT | 2016-10-10 |  | 3 | Pending
11203 | 11203 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | IPT | 2016-10-09 |  | 3 | Pending
11228 | 11228 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | IPT | 2016-10-13 |  | 3 | Pending
11253 | 11253 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | IPT | 2016-10-13 |  | 3 | Pending
11278 | 11278 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | AJN | 2016-10-04 |  | 3 | Pending
11303 | 11303 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | AJN | 2016-10-04 |  | 3 | Pending
11328 | 11328 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | AJN | 2016-10-04 |  | 3 | Pending
11353 | 11353 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | AJN | 2016-10-04 |  | 3 | Pending
11378 | 11378 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | IPT | 2016-10-04 |  | 3 | Pending
11403 | 11403 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | IPT | 2016-10-04 |  | 3 | Pending
11428 | 11428 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | IPT | 2016-10-04 |  | 3 | Pending
11453 | 11453 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | AJN | 2016-10-07 |  | 3 | Pending
11478 | 11478 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | MMP | 2016-09-21 |  | 3 | Pending
11503 | 11503 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | MMP | 2016-10-28 |  | 4 | Pending
11528 | 11528 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | AJN | 2016-09-05 | 2016-08-13 | 2 | Verify
11553 | 11553 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | AJN | 2016-09-05 | 2016-08-13 | 2 | Verify
11578 | 11578 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | AJN | 2016-09-05 | 2016-08-13 | 2 | Verify
11603 | 11603 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | AJN | 2016-09-05 | 2016-08-13 | 2 | Verify
11628 | 11628 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | AJN | 2016-09-05 | 2016-08-13 | 2 | Verify
11653 | 11653 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOM | 2016-09-10 |  | 2 | Pending
11678 | 11678 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | IPT | 2016-09-10 |  | 2 | Pending
11703 | 11703 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOM | 2016-09-10 |  | 2 | Pending
11728 | 11728 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | IPT | 2016-09-10 |  | 2 | Pending
11753 | 11753 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | IPT | 2016-09-10 |  | 2 | Pending
11778 | 11778 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | IPT | 2016-09-10 |  | 2 | Pending
11803 | 11803 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | IPT | 2016-09-10 |  | 2 | Pending
11828 | 11828 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | MMP | 2016-09-21 |  | 3 | Pending
11853 | 11853 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | MMP | 2016-09-21 |  | 3 | Pending
11878 | 11878 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | MMP | 2016-09-21 |  | 3 | Pending
11903 | 11903 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | MMP | 2016-09-21 |  | 3 | Pending
11928 | 11928 | Delivery | Implementation Report_VSAT_Delivery | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | MMP | 2016-09-21 |  | 3 | Pending
11953 | 11953 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | IPT | 2016-10-10 |  | 3 | Pending
11978 | 11978 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | IPT | 2016-10-10 |  | 3 | Pending
12003 | 12003 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | AJN | 2016-10-10 |  | 3 | Pending
12028 | 12028 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | AJN | 2016-10-10 |  | 3 | Pending
12053 | 12053 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | AJN | 2016-10-10 |  | 3 | Pending
12078 | 12078 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | AJN | 2016-10-28 |  | 4 | Pending
12128 | 12128 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | IPT | 2016-10-11 |  | 3 | Pending
12153 | 12153 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | IPT | 2016-10-11 |  | 3 | Pending
12178 | 12178 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | IPT | 2016-10-09 |  | 3 | Pending
12203 | 12203 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | IPT | 2016-10-11 |  | 3 | Pending
12278 | 12278 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | AJN | 2016-10-10 |  | 3 | Pending
12303 | 12303 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | AJN | 2016-10-11 |  | 3 | Pending
12328 | 12328 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | AJN | 2016-10-11 |  | 3 | Pending
12353 | 12353 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | AJN | 2016-10-10 |  | 3 | Pending
12378 | 12378 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | AJN | 2016-10-11 |  | 3 | Pending
12428 | 12428 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | AJN | 2016-10-10 |  | 3 | Pending
12453 | 12453 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOM | 2016-09-19 |  | 2 | Pending
12503 | 12503 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOM | 2016-09-19 |  | 2 | Pending
12603 | 12603 | Delivery | Implementation Report_VSAT_Delivery | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | MMP | 2016-10-13 |  | 3 | Pending
12628 | 12628 | Delivery | Implementation Report_VSAT_Delivery | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | MMP | 2016-10-13 |  | 3 | Pending
12653 | 12653 | Delivery | Implementation Report_VSAT_Delivery | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | MMP | 2016-10-13 |  | 3 | Pending
12678 | 12678 | Delivery | Implementation Report_VSAT_Delivery | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | MMP | 2016-10-13 |  | 3 | Pending
12703 | 12703 | Delivery | Implementation Report_VSAT_Delivery | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | MMP | 2016-10-13 |  | 3 | Pending
12728 | 12728 | Delivery | Implementation Report_VSAT_Delivery | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | MMP | 2016-10-13 |  | 3 | Pending
12762 | 12762 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | MMP | 2016-08-01 | 2016-08-01 | 1 | Verify
12787 | 12787 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | MMP | 2016-08-01 | 2016-08-01 | 1 | Verify
12812 | 12812 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | MMP | 2016-08-01 | 2016-08-01 | 1 | Verify
12837 | 12837 | Delivery | Implementation Report_VSAT_Delivery | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | AJN | 2016-09-13 | 2016-09-19 | 2 | Verify
12862 | 12862 | Delivery | Implementation Report_VSAT_Delivery | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | MMP | 2016-10-09 |  | 3 | Pending
12887 | 12887 | Delivery | Implementation Report_VSAT_Delivery | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | MMP | 2016-10-09 |  | 3 | Pending
12912 | 12912 | Delivery | Implementation Report_VSAT_Delivery | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | MMP | 2016-10-09 |  | 3 | Pending
12937 | 12937 | Delivery | Implementation Report_VSAT_Delivery | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | MMP | 2016-10-09 |  | 3 | Pending
12962 | 12962 | Delivery | Implementation Report_VSAT_Delivery | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | IPT | 2016-09-24 |  | 3 | Pending
12987 | 12987 | Delivery | Implementation Report_VSAT_Delivery | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | MMP | 2016-10-09 |  | 3 | Pending
13012 | 13012 | Delivery | Implementation Report_VSAT_Delivery | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | MMP | 2016-10-13 |  | 3 | Pending
13037 | 13037 | Delivery | Implementation Report_VSAT_Delivery | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | MMP | 2016-10-13 |  | 3 | Pending
13062 | 13062 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | MMP | 2016-10-13 |  | 3 | Pending
13087 | 13087 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | MMP | 2016-10-13 |  | 3 | Pending
13112 | 13112 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | MMP | 2016-10-13 |  | 3 | Pending
13137 | 13137 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | MMP | 2016-10-13 |  | 3 | Pending
13162 | 13162 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | MMP | 2016-10-13 |  | 3 | Pending
13187 | 13187 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | MMP | 2016-10-13 |  | 3 | Pending
13212 | 13212 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13237 | 13237 | Delivery | Implementation Report_VSAT_Delivery | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | MMP | 2016-11-18 |  | 4 | Pending
13262 | 13262 | Delivery | Implementation Report_VSAT_Delivery | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | MMP | 2016-11-18 |  | 4 | Pending
13287 | 13287 | Delivery | Implementation Report_VSAT_Delivery | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | MMP | 2016-11-18 |  | 4 | Pending
13312 | 13312 | Delivery | Implementation Report_VSAT_Delivery | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | MMP | 2016-11-18 |  | 4 | Pending
13337 | 13337 | Delivery | Implementation Report_VSAT_Delivery | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | MMP | 2016-11-18 |  | 4 | Pending
13362 | 13362 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13387 | 13387 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13412 | 13412 | Delivery | Implementation Report_VSAT_Delivery | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-11-18 |  | 4 | Pending
13437 | 13437 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13462 | 13462 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13487 | 13487 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13512 | 13512 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13537 | 13537 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13562 | 13562 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13587 | 13587 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13612 | 13612 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13637 | 13637 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13662 | 13662 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13687 | 13687 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13712 | 13712 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13737 | 13737 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13762 | 13762 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13787 | 13787 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13812 | 13812 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13837 | 13837 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13862 | 13862 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13887 | 13887 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13912 | 13912 | Delivery | Implementation Report_VSAT_Delivery | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13937 | 13937 | Delivery | Implementation Report_VSAT_Delivery | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
13962 | 13962 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-11-18 |  | 4 | Pending
13987 | 13987 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-10-28 |  | 4 | Pending
14012 | 14012 | Delivery | Implementation Report_VSAT_Delivery | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-10-28 |  | 4 | Pending
10009 | 10009 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | AJN | 2016-09-17 |  | 2 | Pending
10034 | 10034 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | LA | 2016-11-14 |  | 4 | Pending
10059 | 10059 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | AJN | 2016-09-17 | 2016-10-01 | 2 | Verify
10109 | 10109 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | LA | 2016-11-14 |  | 4 | Pending
10134 | 10134 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | AJN | 2016-09-17 | 2016-09-18 | 2 | Verify
10184 | 10184 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | AJN | 2016-11-12 |  | 4 | Pending
10209 | 10209 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | AJN | 2016-11-12 |  | 4 | Pending
10259 | 10259 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | DTP | 2016-08-11 | 2016-08-18 | 1 | Verify
10284 | 10284 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | DTP | 2016-08-11 | 2016-08-18 | 1 | Verify
10309 | 10309 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | AJN | 2016-08-11 | 2016-08-18 | 1 | Verify
10334 | 10334 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | AJN | 2016-10-17 |  | 3 | Pending
10359 | 10359 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | AJN | 2016-11-13 |  | 4 | Pending
10384 | 10384 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | AJN | 2016-10-17 |  | 3 | Pending
10409 | 10409 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | AJN | 2016-08-11 | 2016-09-08 | 1 | Verify
10434 | 10434 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | AJN | 2016-08-11 | 2016-09-24 | 1 | Verify
10534 | 10534 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | AJN | 2016-09-17 | 2016-10-02 | 2 | Verify
10559 | 10559 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | AJN | 2016-09-17 |  | 2 | Pending
10584 | 10584 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | AJN | 2016-09-17 |  | 2 | Pending
10609 | 10609 | Installation | Implementation Report_VSAT_Installation | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOM | 2016-10-18 |  | 2 | Pending
10634 | 10634 | Installation | Implementation Report_VSAT_Installation | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOM | 2016-10-30 |  | 2 | Pending
10659 | 10659 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOM | 2016-10-30 |  | 2 | Pending
10684 | 10684 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | IPT | 2016-10-24 |  | 3 | Pending
10709 | 10709 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | LA | 2017-01-13 |  | 3 | Pending
10734 | 10734 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOM | 2016-10-31 |  | 2 | Pending
10759 | 10759 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | LA | 2017-01-13 |  | 3 | Pending
10784 | 10784 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | IPT | 2016-11-08 |  | 3 | Pending
10809 | 10809 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | IPT | 2016-10-26 |  | 3 | Pending
10834 | 10834 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | LA | 2017-01-13 |  | 3 | Pending
10859 | 10859 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | LA | 2017-01-13 |  | 3 | Pending
10884 | 10884 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | LA | 2017-01-13 |  | 3 | Pending
10909 | 10909 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | LA | 2017-01-13 |  | 3 | Pending
10934 | 10934 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | LA | 2017-01-13 |  | 3 | Pending
10959 | 10959 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | IPT | 2016-11-04 |  | 3 | Pending
10984 | 10984 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | LA | 2016-10-22 |  | 3 | Pending
11009 | 11009 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | LA | 2016-11-22 |  | 4 | Pending
11034 | 11034 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | LA | 2016-11-22 |  | 3 | Pending
11059 | 11059 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | IPT | 2016-11-05 |  | 4 | Pending
11084 | 11084 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | IPT | 2016-11-22 |  | 4 | Pending
11109 | 11109 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | IPT | 2016-10-27 |  | 3 | Pending
11134 | 11134 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | AJN | 2016-10-25 |  | 3 | Pending
11159 | 11159 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | AJN | 2016-10-31 |  | 3 | Pending
11184 | 11184 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | IPT | 2016-11-02 |  | 3 | Pending
11209 | 11209 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | IPT | 2016-10-31 |  | 3 | Pending
11234 | 11234 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | IPT | 2016-11-09 |  | 3 | Pending
11259 | 11259 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | IPT | 2016-11-09 |  | 3 | Pending
11284 | 11284 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | AJN | 2016-10-21 |  | 3 | Pending
11309 | 11309 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | AJN | 2016-10-21 |  | 3 | Pending
11334 | 11334 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | AJN | 2016-10-21 |  | 3 | Pending
11359 | 11359 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | AJN | 2016-10-21 |  | 3 | Pending
11384 | 11384 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | IPT | 2016-10-21 |  | 3 | Pending
11409 | 11409 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | IPT | 2016-10-21 |  | 3 | Pending
11434 | 11434 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | IPT | 2016-10-22 |  | 3 | Pending
11459 | 11459 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | AJN | 2016-10-27 |  | 3 | Pending
11484 | 11484 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | MMP | 2016-10-11 |  | 3 | Pending
11509 | 11509 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | MMP | 2016-11-09 |  | 4 | Pending
11534 | 11534 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | AJN | 2016-09-16 | 2016-09-05 | 2 | Verify
11559 | 11559 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | AJN | 2016-09-16 | 2016-10-06 | 2 | Verify
11584 | 11584 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | AJN | 2016-09-16 | 2016-10-08 | 2 | Verify
11609 | 11609 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | AJN | 2016-09-16 | 2016-09-27 | 2 | Verify
11634 | 11634 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | AJN | 2016-09-16 | 2016-09-27 | 2 | Verify
11659 | 11659 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOM | 2016-09-28 |  | 2 | Pending
11684 | 11684 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | IPT | 2016-09-28 |  | 2 | Pending
11709 | 11709 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOM | 2016-09-28 |  | 2 | Pending
11734 | 11734 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | IPT | 2016-09-28 |  | 2 | Pending
11759 | 11759 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | IPT | 2016-09-28 |  | 2 | Pending
11784 | 11784 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | IPT | 2016-09-28 |  | 2 | Pending
11809 | 11809 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | IPT | 2016-09-28 |  | 2 | Pending
11834 | 11834 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | MMP | 2016-10-11 |  | 3 | Pending
11859 | 11859 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | MMP | 2016-10-11 |  | 3 | Pending
11884 | 11884 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | MMP | 2016-10-11 |  | 3 | Pending
11909 | 11909 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | MMP | 2016-10-11 |  | 3 | Pending
11934 | 11934 | Installation | Implementation Report_VSAT_Installation | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | MMP | 2016-10-11 |  | 3 | Pending
11959 | 11959 | Installation | Implementation Report_VSAT_Installation | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | IPT | 2016-11-07 |  | 3 | Pending
11984 | 11984 | Installation | Implementation Report_VSAT_Installation | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | IPT | 2016-11-07 |  | 3 | Pending
12009 | 12009 | Installation | Implementation Report_VSAT_Installation | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | AJN | 2016-11-07 |  | 3 | Pending
12034 | 12034 | Installation | Implementation Report_VSAT_Installation | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | AJN | 2016-11-07 |  | 3 | Pending
12059 | 12059 | Installation | Implementation Report_VSAT_Installation | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | AJN | 2016-11-07 |  | 3 | Pending
12084 | 12084 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | AJN | 2016-11-26 |  | 4 | Pending
12134 | 12134 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | IPT | 2016-11-09 |  | 3 | Pending
12159 | 12159 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | IPT | 2016-11-06 |  | 3 | Pending
12184 | 12184 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | IPT | 2016-11-05 |  | 3 | Pending
12209 | 12209 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | IPT | 2016-11-10 |  | 3 | Pending
12284 | 12284 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | AJN | 2016-11-07 |  | 3 | Pending
12309 | 12309 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | AJN | 2016-11-08 |  | 3 | Pending
12334 | 12334 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | AJN | 2016-11-08 |  | 3 | Pending
12359 | 12359 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | AJN | 2016-11-07 |  | 3 | Pending
12384 | 12384 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | AJN | 2016-11-08 |  | 3 | Pending
12434 | 12434 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | AJN | 2016-11-07 |  | 3 | Pending
12459 | 12459 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOM | 2016-10-11 |  | 2 | Pending
12509 | 12509 | Installation | Implementation Report_VSAT_Installation | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOM | 2016-10-11 |  | 2 | Pending
12609 | 12609 | Installation | Implementation Report_VSAT_Installation | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | MMP | 2016-11-10 |  | 3 | Pending
12634 | 12634 | Installation | Implementation Report_VSAT_Installation | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | MMP | 2016-11-10 |  | 3 | Pending
12659 | 12659 | Installation | Implementation Report_VSAT_Installation | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | MMP | 2016-11-10 |  | 3 | Pending
12684 | 12684 | Installation | Implementation Report_VSAT_Installation | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | MMP | 2016-11-10 |  | 3 | Pending
12709 | 12709 | Installation | Implementation Report_VSAT_Installation | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | MMP | 2016-11-10 |  | 3 | Pending
12734 | 12734 | Installation | Implementation Report_VSAT_Installation | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | MMP | 2016-11-10 |  | 3 | Pending
12763 | 12763 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | MMP | 2016-08-17 | 2016-08-15 | 1 | Verify
12788 | 12788 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | MMP | 2016-08-17 | 2016-08-15 | 1 | Verify
12813 | 12813 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | MMP | 2016-08-17 | 2016-08-15 | 1 | Verify
12838 | 12838 | Installation | Implementation Report_VSAT_Installation | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | AJN | 2016-10-05 |  | 2 | Pending
12863 | 12863 | Installation | Implementation Report_VSAT_Installation | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | MMP | 2016-11-05 |  | 3 | Pending
12888 | 12888 | Installation | Implementation Report_VSAT_Installation | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | MMP | 2016-11-05 |  | 3 | Pending
12913 | 12913 | Installation | Implementation Report_VSAT_Installation | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | MMP | 2016-11-05 |  | 3 | Pending
12938 | 12938 | Installation | Implementation Report_VSAT_Installation | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | MMP | 2016-11-05 |  | 3 | Pending
12963 | 12963 | Installation | Implementation Report_VSAT_Installation | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | IPT | 2016-10-16 |  | 3 | Pending
12988 | 12988 | Installation | Implementation Report_VSAT_Installation | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | MMP | 2016-11-05 |  | 3 | Pending
13013 | 13013 | Installation | Implementation Report_VSAT_Installation | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | MMP | 2016-11-10 |  | 3 | Pending
13038 | 13038 | Installation | Implementation Report_VSAT_Installation | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | MMP | 2016-11-10 |  | 3 | Pending
13063 | 13063 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | MMP | 2016-11-10 |  | 3 | Pending
13088 | 13088 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | MMP | 2016-11-10 |  | 3 | Pending
13113 | 13113 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | MMP | 2016-11-10 |  | 3 | Pending
13138 | 13138 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | MMP | 2016-11-10 |  | 3 | Pending
13163 | 13163 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | MMP | 2016-11-10 |  | 3 | Pending
13188 | 13188 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | MMP | 2016-11-10 |  | 3 | Pending
13213 | 13213 | Installation | Implementation Report_VSAT_Installation | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13238 | 13238 | Installation | Implementation Report_VSAT_Installation | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | MMP | 2016-12-10 |  | 4 | Pending
13263 | 13263 | Installation | Implementation Report_VSAT_Installation | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | MMP | 2016-12-10 |  | 4 | Pending
13288 | 13288 | Installation | Implementation Report_VSAT_Installation | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | MMP | 2016-12-10 |  | 4 | Pending
13313 | 13313 | Installation | Implementation Report_VSAT_Installation | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | MMP | 2016-12-10 |  | 4 | Pending
13338 | 13338 | Installation | Implementation Report_VSAT_Installation | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | MMP | 2016-12-10 |  | 4 | Pending
13363 | 13363 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13388 | 13388 | Installation | Implementation Report_VSAT_Installation | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13413 | 13413 | Installation | Implementation Report_VSAT_Installation | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13438 | 13438 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-11-14 |  | 4 | Pending
13463 | 13463 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-11-14 |  | 4 | Pending
13488 | 13488 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-11-14 |  | 4 | Pending
13513 | 13513 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-11-14 |  | 4 | Pending
13538 | 13538 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-11-14 |  | 4 | Pending
13563 | 13563 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13588 | 13588 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13613 | 13613 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13638 | 13638 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13663 | 13663 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13688 | 13688 | Installation | Implementation Report_VSAT_Installation | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13713 | 13713 | Installation | Implementation Report_VSAT_Installation | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13738 | 13738 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13763 | 13763 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13788 | 13788 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13813 | 13813 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13838 | 13838 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13863 | 13863 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13888 | 13888 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13913 | 13913 | Installation | Implementation Report_VSAT_Installation | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13938 | 13938 | Installation | Implementation Report_VSAT_Installation | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13963 | 13963 | Installation | Implementation Report_VSAT_Installation | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-12-16 |  | 4 | Pending
13988 | 13988 | Installation | Implementation Report_VSAT_Installation | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-11-25 |  | 4 | Pending
14013 | 14013 | Installation | Implementation Report_VSAT_Installation | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-11-25 |  | 4 | Pending
10015 | 10015 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | AJN | 2016-09-19 |  | 2 | Pending
10040 | 10040 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | LA | 2016-11-16 |  | 4 | Pending
10065 | 10065 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | AJN | 2016-09-19 | 2016-10-01 | 2 | Verify
10115 | 10115 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | LA | 2016-11-16 |  | 4 | Pending
10140 | 10140 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | AJN | 2016-09-19 | 2016-09-29 | 2 | Verify
10190 | 10190 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | AJN | 2016-11-14 |  | 4 | Pending
10215 | 10215 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | AJN | 2016-11-14 |  | 4 | Pending
10265 | 10265 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | DTP | 2016-08-13 | 2016-08-19 | 1 | Verify
10290 | 10290 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | DTP | 2016-08-13 | 2016-08-19 | 1 | Verify
10315 | 10315 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | AJN | 2016-08-13 | 2016-08-18 | 1 | Verify
10340 | 10340 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | AJN | 2016-10-19 |  | 3 | Pending
10365 | 10365 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | AJN | 2016-11-15 |  | 4 | Pending
10390 | 10390 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | AJN | 2016-10-19 |  | 3 | Pending
10415 | 10415 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | AJN | 2016-08-13 | 2016-09-08 | 1 | Verify
10440 | 10440 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | AJN | 2016-08-13 | 2016-09-24 | 1 | Verify
10540 | 10540 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | AJN | 2016-09-19 | 2016-10-03 | 2 | Verify
10565 | 10565 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | AJN | 2016-09-19 |  | 2 | Pending
10590 | 10590 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | AJN | 2016-09-19 |  | 2 | Pending
10615 | 10615 | Integration | Implementation Report_VSAT_Integration | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOM | 2016-10-20 |  | 2 | Pending
10640 | 10640 | Integration | Implementation Report_VSAT_Integration | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOM | 2016-11-01 |  | 2 | Pending
10665 | 10665 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOM | 2016-11-01 |  | 2 | Pending
10690 | 10690 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | IPT | 2016-10-26 |  | 3 | Pending
10715 | 10715 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | LA | 2017-01-15 |  | 3 | Pending
10740 | 10740 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOM | 2016-11-02 |  | 2 | Pending
10765 | 10765 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | LA | 2017-01-15 |  | 3 | Pending
10790 | 10790 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | IPT | 2016-11-10 |  | 3 | Pending
10815 | 10815 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | IPT | 2016-10-28 |  | 3 | Pending
10840 | 10840 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | LA | 2017-01-15 |  | 3 | Pending
10865 | 10865 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | LA | 2017-01-15 |  | 3 | Pending
10890 | 10890 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | LA | 2017-01-15 |  | 3 | Pending
10915 | 10915 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | LA | 2017-01-15 |  | 3 | Pending
10940 | 10940 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | LA | 2017-01-15 |  | 3 | Pending
10965 | 10965 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | IPT | 2016-11-06 |  | 3 | Pending
10990 | 10990 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | LA | 2016-10-24 |  | 3 | Pending
11015 | 11015 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | LA | 2016-11-24 |  | 4 | Pending
11040 | 11040 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | LA | 2016-11-24 |  | 3 | Pending
11065 | 11065 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | IPT | 2016-11-07 |  | 4 | Pending
11090 | 11090 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | IPT | 2016-11-24 |  | 4 | Pending
11115 | 11115 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | IPT | 2016-10-29 |  | 3 | Pending
11140 | 11140 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | AJN | 2016-10-27 |  | 3 | Pending
11165 | 11165 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | AJN | 2016-11-02 |  | 3 | Pending
11190 | 11190 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | IPT | 2016-11-04 |  | 3 | Pending
11215 | 11215 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | IPT | 2016-11-02 |  | 3 | Pending
11240 | 11240 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | IPT | 2016-11-11 |  | 3 | Pending
11265 | 11265 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | IPT | 2016-11-11 |  | 3 | Pending
11290 | 11290 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | AJN | 2016-10-23 |  | 3 | Pending
11315 | 11315 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | AJN | 2016-10-23 |  | 3 | Pending
11340 | 11340 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | AJN | 2016-10-23 |  | 3 | Pending
11365 | 11365 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | AJN | 2016-10-23 |  | 3 | Pending
11390 | 11390 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | IPT | 2016-10-23 |  | 3 | Pending
11415 | 11415 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | IPT | 2016-10-23 |  | 3 | Pending
11440 | 11440 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | IPT | 2016-10-24 |  | 3 | Pending
11465 | 11465 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | AJN | 2016-10-29 |  | 3 | Pending
11490 | 11490 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | MMP | 2016-10-13 |  | 3 | Pending
11515 | 11515 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | MMP | 2016-11-11 |  | 4 | Pending
11540 | 11540 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | AJN | 2016-09-18 | 2016-09-04 | 2 | Verify
11565 | 11565 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | AJN | 2016-09-18 | 2016-09-08 | 2 | Verify
11590 | 11590 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | AJN | 2016-09-18 | 2016-09-09 | 2 | Verify
11615 | 11615 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | AJN | 2016-09-18 | 2016-09-19 | 2 | Verify
11640 | 11640 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | AJN | 2016-09-18 | 2016-09-26 | 2 | Verify
11665 | 11665 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOM | 2016-09-30 |  | 2 | Pending
11690 | 11690 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | IPT | 2016-09-30 |  | 2 | Pending
11715 | 11715 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOM | 2016-09-30 |  | 2 | Pending
11740 | 11740 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | IPT | 2016-09-30 |  | 2 | Pending
11765 | 11765 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | IPT | 2016-09-30 |  | 2 | Pending
11790 | 11790 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | IPT | 2016-09-30 |  | 2 | Pending
11815 | 11815 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | IPT | 2016-09-30 |  | 2 | Pending
11840 | 11840 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | MMP | 2016-10-13 |  | 3 | Pending
11865 | 11865 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | MMP | 2016-10-13 |  | 3 | Pending
11890 | 11890 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | MMP | 2016-10-13 |  | 3 | Pending
11915 | 11915 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | MMP | 2016-10-13 |  | 3 | Pending
11940 | 11940 | Integration | Implementation Report_VSAT_Integration | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | MMP | 2016-10-13 |  | 3 | Pending
11965 | 11965 | Integration | Implementation Report_VSAT_Integration | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | IPT | 2016-11-09 |  | 3 | Pending
11990 | 11990 | Integration | Implementation Report_VSAT_Integration | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | IPT | 2016-11-09 |  | 3 | Pending
12015 | 12015 | Integration | Implementation Report_VSAT_Integration | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | AJN | 2016-11-09 |  | 3 | Pending
12040 | 12040 | Integration | Implementation Report_VSAT_Integration | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | AJN | 2016-11-09 |  | 3 | Pending
12065 | 12065 | Integration | Implementation Report_VSAT_Integration | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | AJN | 2016-11-09 |  | 3 | Pending
12090 | 12090 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | AJN | 2016-11-28 |  | 4 | Pending
12140 | 12140 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | IPT | 2016-11-11 |  | 3 | Pending
12165 | 12165 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | IPT | 2016-11-08 |  | 3 | Pending
12190 | 12190 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | IPT | 2016-11-07 |  | 3 | Pending
12215 | 12215 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | IPT | 2016-11-12 |  | 3 | Pending
12290 | 12290 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | AJN | 2016-11-09 |  | 3 | Pending
12315 | 12315 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | AJN | 2016-11-10 |  | 3 | Pending
12340 | 12340 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | AJN | 2016-11-10 |  | 3 | Pending
12365 | 12365 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | AJN | 2016-11-09 |  | 3 | Pending
12390 | 12390 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | AJN | 2016-11-10 |  | 3 | Pending
12440 | 12440 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | AJN | 2016-11-09 |  | 3 | Pending
12465 | 12465 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOM | 2016-10-13 |  | 2 | Pending
12515 | 12515 | Integration | Implementation Report_VSAT_Integration | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOM | 2016-10-13 |  | 2 | Pending
12615 | 12615 | Integration | Implementation Report_VSAT_Integration | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | MMP | 2016-11-12 |  | 3 | Pending
12640 | 12640 | Integration | Implementation Report_VSAT_Integration | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | MMP | 2016-11-12 |  | 3 | Pending
12665 | 12665 | Integration | Implementation Report_VSAT_Integration | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | MMP | 2016-11-12 |  | 3 | Pending
12690 | 12690 | Integration | Implementation Report_VSAT_Integration | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | MMP | 2016-11-12 |  | 3 | Pending
12715 | 12715 | Integration | Implementation Report_VSAT_Integration | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | MMP | 2016-11-12 |  | 3 | Pending
12740 | 12740 | Integration | Implementation Report_VSAT_Integration | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | MMP | 2016-11-12 |  | 3 | Pending
12764 | 12764 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | MMP | 2016-08-19 | 2016-08-16 | 1 | Verify
12789 | 12789 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | MMP | 2016-08-19 | 2016-08-18 | 1 | Verify
12814 | 12814 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | MMP | 2016-08-19 | 2016-08-18 | 1 | Verify
12839 | 12839 | Integration | Implementation Report_VSAT_Integration | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | AJN | 2016-10-07 |  | 2 | Pending
12864 | 12864 | Integration | Implementation Report_VSAT_Integration | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | MMP | 2016-11-07 |  | 3 | Pending
12889 | 12889 | Integration | Implementation Report_VSAT_Integration | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | MMP | 2016-11-07 |  | 3 | Pending
12914 | 12914 | Integration | Implementation Report_VSAT_Integration | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | MMP | 2016-11-07 |  | 3 | Pending
12939 | 12939 | Integration | Implementation Report_VSAT_Integration | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | MMP | 2016-11-07 |  | 3 | Pending
12964 | 12964 | Integration | Implementation Report_VSAT_Integration | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | IPT | 2016-10-18 |  | 3 | Pending
12989 | 12989 | Integration | Implementation Report_VSAT_Integration | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | MMP | 2016-11-07 |  | 3 | Pending
13014 | 13014 | Integration | Implementation Report_VSAT_Integration | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | MMP | 2016-11-12 |  | 3 | Pending
13039 | 13039 | Integration | Implementation Report_VSAT_Integration | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | MMP | 2016-11-12 |  | 3 | Pending
13064 | 13064 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | MMP | 2016-11-12 |  | 3 | Pending
13089 | 13089 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | MMP | 2016-11-12 |  | 3 | Pending
13114 | 13114 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | MMP | 2016-11-12 |  | 3 | Pending
13139 | 13139 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | MMP | 2016-11-12 |  | 3 | Pending
13164 | 13164 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | MMP | 2016-11-12 |  | 3 | Pending
13189 | 13189 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | MMP | 2016-11-12 |  | 3 | Pending
13214 | 13214 | Integration | Implementation Report_VSAT_Integration | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
13239 | 13239 | Integration | Implementation Report_VSAT_Integration | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | MMP | 2016-12-12 |  | 4 | Pending
13264 | 13264 | Integration | Implementation Report_VSAT_Integration | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | MMP | 2016-12-12 |  | 4 | Pending
13289 | 13289 | Integration | Implementation Report_VSAT_Integration | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | MMP | 2016-12-12 |  | 4 | Pending
13314 | 13314 | Integration | Implementation Report_VSAT_Integration | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | MMP | 2016-12-12 |  | 4 | Pending
13339 | 13339 | Integration | Implementation Report_VSAT_Integration | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | MMP | 2016-12-12 |  | 4 | Pending
13364 | 13364 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13389 | 13389 | Integration | Implementation Report_VSAT_Integration | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-11-15 |  | 4 | Pending
13414 | 13414 | Integration | Implementation Report_VSAT_Integration | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13439 | 13439 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13464 | 13464 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13489 | 13489 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13514 | 13514 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13539 | 13539 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-11-16 |  | 4 | Pending
13564 | 13564 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-11-17 |  | 4 | Pending
13589 | 13589 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-11-17 |  | 4 | Pending
13614 | 13614 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-11-17 |  | 4 | Pending
13639 | 13639 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-11-17 |  | 4 | Pending
13664 | 13664 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-11-17 |  | 4 | Pending
13689 | 13689 | Integration | Implementation Report_VSAT_Integration | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-11-17 |  | 4 | Pending
13714 | 13714 | Integration | Implementation Report_VSAT_Integration | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13739 | 13739 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13764 | 13764 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13789 | 13789 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13814 | 13814 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13839 | 13839 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13864 | 13864 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13889 | 13889 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13914 | 13914 | Integration | Implementation Report_VSAT_Integration | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-11-24 |  | 4 | Pending
13939 | 13939 | Integration | Implementation Report_VSAT_Integration | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13964 | 13964 | Integration | Implementation Report_VSAT_Integration | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-12-18 |  | 4 | Pending
13989 | 13989 | Integration | Implementation Report_VSAT_Integration | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-11-27 |  | 4 | Pending
14014 | 14014 | Integration | Implementation Report_VSAT_Integration | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-11-27 |  | 4 | Pending
10006 | 10006 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | AJN | 2016-09-15 | 2016-09-07 | 2 | Verify
10031 | 10031 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | LA | 2016-11-12 |  | 4 | Pending
10056 | 10056 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | AJN | 2016-09-15 | 2016-09-07 | 2 | Verify
10106 | 10106 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | LA | 2016-11-12 |  | 4 | Pending
10131 | 10131 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | AJN | 2016-09-15 | 2016-09-07 | 2 | Verify
10181 | 10181 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | AJN | 2016-11-10 |  | 4 | Pending
10206 | 10206 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | AJN | 2016-11-10 |  | 4 | Pending
10256 | 10256 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | DTP | 2016-08-09 | 2016-08-15 | 1 | Verify
10281 | 10281 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | DTP | 2016-08-09 | 2016-08-15 | 1 | Verify
10306 | 10306 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | AJN | 2016-08-09 | 2016-08-11 | 1 | Verify
10331 | 10331 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | AJN | 2016-10-15 | 2016-09-29 | 3 | Verify
10356 | 10356 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | AJN | 2016-11-11 |  | 4 | Pending
10381 | 10381 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | AJN | 2016-10-15 | 2016-09-29 | 3 | Verify
10406 | 10406 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | AJN | 2016-08-09 | 2016-08-25 | 1 | Verify
10431 | 10431 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | AJN | 2016-08-09 | 2016-09-12 | 1 | Verify
10531 | 10531 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | AJN | 2016-09-15 | 2016-09-07 | 2 | Verify
10556 | 10556 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | AJN | 2016-09-15 | 2016-09-09 | 2 | Verify
10581 | 10581 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | AJN | 2016-09-15 | 2016-09-09 | 2 | Verify
10606 | 10606 | MOS | Implementation Report_VSAT_MOS | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOM | 2016-10-16 |  | 2 | Pending
10631 | 10631 | MOS | Implementation Report_VSAT_MOS | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOM | 2016-10-28 |  | 2 | Pending
10656 | 10656 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOM | 2016-10-28 |  | 2 | Pending
10681 | 10681 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | IPT | 2016-10-22 |  | 3 | Pending
10706 | 10706 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | LA | 2017-01-11 |  | 3 | Pending
10731 | 10731 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOM | 2016-10-29 |  | 2 | Pending
10756 | 10756 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | LA | 2017-01-11 |  | 3 | Pending
10781 | 10781 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | IPT | 2016-11-06 |  | 3 | Pending
10806 | 10806 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | IPT | 2016-10-24 |  | 3 | Pending
10831 | 10831 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | LA | 2017-01-11 |  | 3 | Pending
10856 | 10856 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | LA | 2017-01-11 |  | 3 | Pending
10881 | 10881 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | LA | 2017-01-11 |  | 3 | Pending
10906 | 10906 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | LA | 2017-01-11 |  | 3 | Pending
10931 | 10931 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | LA | 2017-01-11 |  | 3 | Pending
10956 | 10956 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | IPT | 2016-11-02 |  | 3 | Pending
10981 | 10981 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | LA | 2016-10-20 |  | 3 | Pending
11006 | 11006 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | LA | 2016-11-20 |  | 4 | Pending
11031 | 11031 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | LA | 2016-11-20 |  | 3 | Pending
11056 | 11056 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | IPT | 2016-11-03 |  | 4 | Pending
11081 | 11081 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | IPT | 2016-11-20 |  | 4 | Pending
11106 | 11106 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | IPT | 2016-10-25 |  | 3 | Pending
11131 | 11131 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | AJN | 2016-10-23 |  | 3 | Pending
11156 | 11156 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | AJN | 2016-10-29 |  | 3 | Pending
11181 | 11181 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | IPT | 2016-10-31 |  | 3 | Pending
11206 | 11206 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | IPT | 2016-10-29 |  | 3 | Pending
11231 | 11231 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | IPT | 2016-11-07 |  | 3 | Pending
11256 | 11256 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | IPT | 2016-11-07 |  | 3 | Pending
11281 | 11281 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | AJN | 2016-10-19 |  | 3 | Pending
11306 | 11306 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | AJN | 2016-10-19 |  | 3 | Pending
11331 | 11331 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | AJN | 2016-10-19 |  | 3 | Pending
11356 | 11356 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | AJN | 2016-10-19 |  | 3 | Pending
11381 | 11381 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | IPT | 2016-10-19 |  | 3 | Pending
11406 | 11406 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | IPT | 2016-10-19 |  | 3 | Pending
11431 | 11431 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | IPT | 2016-10-20 |  | 3 | Pending
11456 | 11456 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | AJN | 2016-10-25 |  | 3 | Pending
11481 | 11481 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | MMP | 2016-10-09 |  | 3 | Pending
11506 | 11506 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | MMP | 2016-11-07 |  | 4 | Pending
11531 | 11531 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | AJN | 2016-09-14 | 2016-08-27 | 2 | Verify
11556 | 11556 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | AJN | 2016-09-14 | 2016-08-27 | 2 | Verify
11581 | 11581 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | AJN | 2016-09-14 | 2016-08-27 | 2 | Verify
11606 | 11606 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | AJN | 2016-09-14 | 2016-08-27 | 2 | Verify
11631 | 11631 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | AJN | 2016-09-14 | 2016-08-27 | 2 | Verify
11656 | 11656 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOM | 2016-09-26 |  | 2 | Pending
11681 | 11681 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | IPT | 2016-09-26 |  | 2 | Pending
11706 | 11706 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOM | 2016-09-26 |  | 2 | Pending
11731 | 11731 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | IPT | 2016-09-26 |  | 2 | Pending
11756 | 11756 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | IPT | 2016-09-26 |  | 2 | Pending
11781 | 11781 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | IPT | 2016-09-26 |  | 2 | Pending
11806 | 11806 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | IPT | 2016-09-26 |  | 2 | Pending
11831 | 11831 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | MMP | 2016-10-09 |  | 3 | Pending
11856 | 11856 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | MMP | 2016-10-09 |  | 3 | Pending
11881 | 11881 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | MMP | 2016-10-09 |  | 3 | Pending
11906 | 11906 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | MMP | 2016-10-09 |  | 3 | Pending
11931 | 11931 | MOS | Implementation Report_VSAT_MOS | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | MMP | 2016-10-09 |  | 3 | Pending
11956 | 11956 | MOS | Implementation Report_VSAT_MOS | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | IPT | 2016-11-05 |  | 3 | Pending
11981 | 11981 | MOS | Implementation Report_VSAT_MOS | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | IPT | 2016-11-05 |  | 3 | Pending
12006 | 12006 | MOS | Implementation Report_VSAT_MOS | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | AJN | 2016-11-05 |  | 3 | Pending
12031 | 12031 | MOS | Implementation Report_VSAT_MOS | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | AJN | 2016-11-05 |  | 3 | Pending
12056 | 12056 | MOS | Implementation Report_VSAT_MOS | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | AJN | 2016-11-05 |  | 3 | Pending
12081 | 12081 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | AJN | 2016-11-24 |  | 4 | Pending
12131 | 12131 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | IPT | 2016-11-07 |  | 3 | Pending
12156 | 12156 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | IPT | 2016-11-04 |  | 3 | Pending
12181 | 12181 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | IPT | 2016-11-03 |  | 3 | Pending
12206 | 12206 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | IPT | 2016-11-08 |  | 3 | Pending
12281 | 12281 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | AJN | 2016-11-05 |  | 3 | Pending
12306 | 12306 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | AJN | 2016-11-06 |  | 3 | Pending
12331 | 12331 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | AJN | 2016-11-06 |  | 3 | Pending
12356 | 12356 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | AJN | 2016-11-05 |  | 3 | Pending
12381 | 12381 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | AJN | 2016-11-06 |  | 3 | Pending
12431 | 12431 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | AJN | 2016-11-05 |  | 3 | Pending
12456 | 12456 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOM | 2016-10-09 |  | 2 | Pending
12506 | 12506 | MOS | Implementation Report_VSAT_MOS | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOM | 2016-10-09 |  | 2 | Pending
12606 | 12606 | MOS | Implementation Report_VSAT_MOS | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | MMP | 2016-11-08 |  | 3 | Pending
12631 | 12631 | MOS | Implementation Report_VSAT_MOS | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | MMP | 2016-11-08 |  | 3 | Pending
12656 | 12656 | MOS | Implementation Report_VSAT_MOS | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | MMP | 2016-11-08 |  | 3 | Pending
12681 | 12681 | MOS | Implementation Report_VSAT_MOS | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | MMP | 2016-11-08 |  | 3 | Pending
12706 | 12706 | MOS | Implementation Report_VSAT_MOS | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | MMP | 2016-11-08 |  | 3 | Pending
12731 | 12731 | MOS | Implementation Report_VSAT_MOS | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | MMP | 2016-11-08 |  | 3 | Pending
12765 | 12765 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | MMP | 2016-08-15 | 2016-08-12 | 1 | Verify
12790 | 12790 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | MMP | 2016-08-15 | 2016-08-12 | 1 | Verify
12815 | 12815 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | MMP | 2016-08-15 | 2016-08-12 | 1 | Verify
12840 | 12840 | MOS | Implementation Report_VSAT_MOS | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | AJN | 2016-10-03 |  | 2 | Pending
12865 | 12865 | MOS | Implementation Report_VSAT_MOS | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | MMP | 2016-11-03 |  | 3 | Pending
12890 | 12890 | MOS | Implementation Report_VSAT_MOS | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | MMP | 2016-11-03 |  | 3 | Pending
12915 | 12915 | MOS | Implementation Report_VSAT_MOS | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | MMP | 2016-11-03 |  | 3 | Pending
12940 | 12940 | MOS | Implementation Report_VSAT_MOS | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | MMP | 2016-11-03 |  | 3 | Pending
12965 | 12965 | MOS | Implementation Report_VSAT_MOS | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | IPT | 2016-10-14 |  | 3 | Pending
12990 | 12990 | MOS | Implementation Report_VSAT_MOS | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | MMP | 2016-11-03 |  | 3 | Pending
13015 | 13015 | MOS | Implementation Report_VSAT_MOS | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | MMP | 2016-11-08 |  | 3 | Pending
13040 | 13040 | MOS | Implementation Report_VSAT_MOS | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | MMP | 2016-11-08 |  | 3 | Pending
13065 | 13065 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | MMP | 2016-11-08 |  | 3 | Pending
13090 | 13090 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | MMP | 2016-11-08 |  | 3 | Pending
13115 | 13115 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | MMP | 2016-11-08 |  | 3 | Pending
13140 | 13140 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | MMP | 2016-11-08 |  | 3 | Pending
13165 | 13165 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | MMP | 2016-11-08 |  | 3 | Pending
13190 | 13190 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | MMP | 2016-11-08 |  | 3 | Pending
13215 | 13215 | MOS | Implementation Report_VSAT_MOS | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-11-19 |  | 4 | Pending
13240 | 13240 | MOS | Implementation Report_VSAT_MOS | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | MMP | 2016-12-08 |  | 4 | Pending
13265 | 13265 | MOS | Implementation Report_VSAT_MOS | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | MMP | 2016-12-08 |  | 4 | Pending
13290 | 13290 | MOS | Implementation Report_VSAT_MOS | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | MMP | 2016-12-08 |  | 4 | Pending
13315 | 13315 | MOS | Implementation Report_VSAT_MOS | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | MMP | 2016-12-08 |  | 4 | Pending
13340 | 13340 | MOS | Implementation Report_VSAT_MOS | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | MMP | 2016-12-08 |  | 4 | Pending
13365 | 13365 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-11-11 |  | 4 | Pending
13390 | 13390 | MOS | Implementation Report_VSAT_MOS | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-11-11 |  | 4 | Pending
13415 | 13415 | MOS | Implementation Report_VSAT_MOS | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-11-18 |  | 4 | Pending
13440 | 13440 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-11-12 |  | 4 | Pending
13465 | 13465 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-11-12 |  | 4 | Pending
13490 | 13490 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-11-12 |  | 4 | Pending
13515 | 13515 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-11-12 |  | 4 | Pending
13540 | 13540 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-11-12 |  | 4 | Pending
13565 | 13565 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13590 | 13590 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13615 | 13615 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13640 | 13640 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13665 | 13665 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13690 | 13690 | MOS | Implementation Report_VSAT_MOS | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-11-13 |  | 4 | Pending
13715 | 13715 | MOS | Implementation Report_VSAT_MOS | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13740 | 13740 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13765 | 13765 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13790 | 13790 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13815 | 13815 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13840 | 13840 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13865 | 13865 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13890 | 13890 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13915 | 13915 | MOS | Implementation Report_VSAT_MOS | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13940 | 13940 | MOS | Implementation Report_VSAT_MOS | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-11-18 |  | 4 | Pending
13965 | 13965 | MOS | Implementation Report_VSAT_MOS | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-12-14 |  | 4 | Pending
13990 | 13990 | MOS | Implementation Report_VSAT_MOS | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-11-23 |  | 4 | Pending
14015 | 14015 | MOS | Implementation Report_VSAT_MOS | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-11-23 |  | 4 | Pending
10017 | 10017 | On Air | On Air | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-18 |  | 2 | Pending
10042 | 10042 | On Air | On Air | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
10067 | 10067 | On Air | On Air | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-18 | 2016-10-02 | 2 | Verify
10117 | 10117 | On Air | On Air | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
10142 | 10142 | On Air | On Air | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-18 | 2016-09-29 | 2 | Verify
10192 | 10192 | On Air | On Air | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
10217 | 10217 | On Air | On Air | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-11-14 |  | 4 | Pending
10267 | 10267 | On Air | On Air | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-08-19 | 2016-08-19 | 1 | Verify
10292 | 10292 | On Air | On Air | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-08-19 | 2016-08-19 | 1 | Verify
10317 | 10317 | On Air | On Air | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-08-28 | 2016-08-28 | 1 | Verify
10342 | 10342 | On Air | On Air | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
10367 | 10367 | On Air | On Air | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
10392 | 10392 | On Air | On Air | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
10417 | 10417 | On Air | On Air | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-09-07 | 2016-09-08 | 1 | Verify
10442 | 10442 | On Air | On Air | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-09-16 | 2016-09-25 | 1 | Verify
10542 | 10542 | On Air | On Air | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-18 | 2016-10-03 | 2 | Verify
10567 | 10567 | On Air | On Air | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-18 |  | 2 | Pending
10592 | 10592 | On Air | On Air | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-18 |  | 2 | Pending
10617 | 10617 | On Air | On Air | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
10642 | 10642 | On Air | On Air | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
10667 | 10667 | On Air | On Air | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
10692 | 10692 | On Air | On Air | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-26 |  | 3 | Pending
10717 | 10717 | On Air | On Air | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10742 | 10742 | On Air | On Air | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
10767 | 10767 | On Air | On Air | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10792 | 10792 | On Air | On Air | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10817 | 10817 | On Air | On Air | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10842 | 10842 | On Air | On Air | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10867 | 10867 | On Air | On Air | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10892 | 10892 | On Air | On Air | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10917 | 10917 | On Air | On Air | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10942 | 10942 | On Air | On Air | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10967 | 10967 | On Air | On Air | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
10992 | 10992 | On Air | On Air | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11017 | 11017 | On Air | On Air | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
11042 | 11042 | On Air | On Air | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-11-24 |  | 3 | Pending
11067 | 11067 | On Air | On Air | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-11-07 |  | 4 | Pending
11092 | 11092 | On Air | On Air | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
11117 | 11117 | On Air | On Air | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11142 | 11142 | On Air | On Air | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11167 | 11167 | On Air | On Air | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11192 | 11192 | On Air | On Air | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11217 | 11217 | On Air | On Air | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11242 | 11242 | On Air | On Air | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
11267 | 11267 | On Air | On Air | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-11-11 |  | 3 | Pending
11292 | 11292 | On Air | On Air | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11317 | 11317 | On Air | On Air | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11342 | 11342 | On Air | On Air | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11367 | 11367 | On Air | On Air | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11392 | 11392 | On Air | On Air | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11417 | 11417 | On Air | On Air | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11442 | 11442 | On Air | On Air | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11467 | 11467 | On Air | On Air | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11492 | 11492 | On Air | On Air | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11517 | 11517 | On Air | On Air | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-11-11 |  | 4 | Pending
11542 | 11542 | On Air | On Air | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-01 | 2016-09-05 | 2 | Verify
11567 | 11567 | On Air | On Air | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-01 | 2016-09-08 | 2 | Verify
11592 | 11592 | On Air | On Air | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-01 | 2016-09-09 | 2 | Verify
11617 | 11617 | On Air | On Air | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-01 | 2016-09-28 | 2 | Verify
11642 | 11642 | On Air | On Air | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-01 | 2016-09-28 | 2 | Verify
11667 | 11667 | On Air | On Air | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
11692 | 11692 | On Air | On Air | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
11717 | 11717 | On Air | On Air | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
11742 | 11742 | On Air | On Air | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
11767 | 11767 | On Air | On Air | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
11792 | 11792 | On Air | On Air | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
11817 | 11817 | On Air | On Air | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
11842 | 11842 | On Air | On Air | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11867 | 11867 | On Air | On Air | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11892 | 11892 | On Air | On Air | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11917 | 11917 | On Air | On Air | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11942 | 11942 | On Air | On Air | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11967 | 11967 | On Air | On Air | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
11992 | 11992 | On Air | On Air | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12017 | 12017 | On Air | On Air | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12042 | 12042 | On Air | On Air | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12067 | 12067 | On Air | On Air | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12092 | 12092 | On Air | On Air | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-11-28 |  | 4 | Pending
12142 | 12142 | On Air | On Air | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12167 | 12167 | On Air | On Air | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12192 | 12192 | On Air | On Air | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12217 | 12217 | On Air | On Air | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12292 | 12292 | On Air | On Air | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12317 | 12317 | On Air | On Air | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12342 | 12342 | On Air | On Air | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12367 | 12367 | On Air | On Air | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12392 | 12392 | On Air | On Air | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12442 | 12442 | On Air | On Air | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12467 | 12467 | On Air | On Air | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
12517 | 12517 | On Air | On Air | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-09-26 |  | 2 | Pending
12617 | 12617 | On Air | On Air | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12642 | 12642 | On Air | On Air | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12667 | 12667 | On Air | On Air | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12692 | 12692 | On Air | On Air | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12717 | 12717 | On Air | On Air | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12742 | 12742 | On Air | On Air | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
12766 | 12766 | On Air | On Air | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-16 | 2016-08-16 | 1 | Verify
12791 | 12791 | On Air | On Air | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-17 | 2016-08-17 | 1 | Verify
12816 | 12816 | On Air | On Air | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-17 | 2016-08-17 | 1 | Verify
12841 | 12841 | On Air | On Air | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-09-22 |  | 2 | Pending
12866 | 12866 | On Air | On Air | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
12891 | 12891 | On Air | On Air | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
12916 | 12916 | On Air | On Air | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
12941 | 12941 | On Air | On Air | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
12966 | 12966 | On Air | On Air | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
12991 | 12991 | On Air | On Air | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-10-18 |  | 3 | Pending
13016 | 13016 | On Air | On Air | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
13041 | 13041 | On Air | On Air | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-10-28 |  | 3 | Pending
13066 | 13066 | On Air | On Air | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
13091 | 13091 | On Air | On Air | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
13116 | 13116 | On Air | On Air | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
13141 | 13141 | On Air | On Air | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
13166 | 13166 | On Air | On Air | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
13191 | 13191 | On Air | On Air | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-10-14 |  | 3 | Pending
13216 | 13216 | On Air | On Air | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-11-23 |  | 4 | Pending
13241 | 13241 | On Air | On Air | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13266 | 13266 | On Air | On Air | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13291 | 13291 | On Air | On Air | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13316 | 13316 | On Air | On Air | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13341 | 13341 | On Air | On Air | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-12-12 |  | 4 | Pending
13366 | 13366 | On Air | On Air | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13391 | 13391 | On Air | On Air | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-11-15 |  | 4 | Pending
13416 | 13416 | On Air | On Air | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13441 | 13441 | On Air | On Air | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13466 | 13466 | On Air | On Air | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13491 | 13491 | On Air | On Air | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13516 | 13516 | On Air | On Air | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13541 | 13541 | On Air | On Air | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
13566 | 13566 | On Air | On Air | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13591 | 13591 | On Air | On Air | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13616 | 13616 | On Air | On Air | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13641 | 13641 | On Air | On Air | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13666 | 13666 | On Air | On Air | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13691 | 13691 | On Air | On Air | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-11-17 |  | 4 | Pending
13716 | 13716 | On Air | On Air | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13741 | 13741 | On Air | On Air | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13766 | 13766 | On Air | On Air | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13791 | 13791 | On Air | On Air | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13816 | 13816 | On Air | On Air | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13841 | 13841 | On Air | On Air | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13866 | 13866 | On Air | On Air | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13891 | 13891 | On Air | On Air | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13916 | 13916 | On Air | On Air | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-11-24 |  | 4 | Pending
13941 | 13941 | On Air | On Air | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13966 | 13966 | On Air | On Air | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-12-18 |  | 4 | Pending
13991 | 13991 | On Air | On Air | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
14016 | 14016 | On Air | On Air | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
10021 | 10021 | ATP | PAT BTS | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10046 | 10046 | ATP | PAT BTS | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
10071 | 10071 | ATP | PAT BTS | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10121 | 10121 | ATP | PAT BTS | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
10146 | 10146 | ATP | PAT BTS | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10196 | 10196 | ATP | PAT BTS | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-11-19 |  | 4 | Pending
10221 | 10221 | ATP | PAT BTS | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-11-19 |  | 4 | Pending
10271 | 10271 | ATP | PAT BTS | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-08-27 | 2016-09-19 | 1 | Verify
10296 | 10296 | ATP | PAT BTS | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-08-27 | 2016-09-19 | 1 | Verify
10321 | 10321 | ATP | PAT BTS | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-09-05 | 2016-09-19 | 1 | Verify
10346 | 10346 | ATP | PAT BTS | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
10371 | 10371 | ATP | PAT BTS | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
10396 | 10396 | ATP | PAT BTS | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
10421 | 10421 | ATP | PAT BTS | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-09-15 |  | 1 | Pending
10446 | 10446 | ATP | PAT BTS | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-09-25 |  | 1 | Pending
10546 | 10546 | ATP | PAT BTS | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10571 | 10571 | ATP | PAT BTS | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10596 | 10596 | ATP | PAT BTS | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10621 | 10621 | ATP | PAT BTS | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10646 | 10646 | ATP | PAT BTS | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10671 | 10671 | ATP | PAT BTS | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10696 | 10696 | ATP | PAT BTS | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-31 |  | 3 | Pending
10721 | 10721 | ATP | PAT BTS | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10746 | 10746 | ATP | PAT BTS | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10771 | 10771 | ATP | PAT BTS | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10796 | 10796 | ATP | PAT BTS | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10821 | 10821 | ATP | PAT BTS | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10846 | 10846 | ATP | PAT BTS | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10871 | 10871 | ATP | PAT BTS | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10896 | 10896 | ATP | PAT BTS | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10921 | 10921 | ATP | PAT BTS | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10946 | 10946 | ATP | PAT BTS | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10971 | 10971 | ATP | PAT BTS | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10996 | 10996 | ATP | PAT BTS | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11021 | 11021 | ATP | PAT BTS | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
11046 | 11046 | ATP | PAT BTS | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-11-29 |  | 3 | Pending
11071 | 11071 | ATP | PAT BTS | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
11096 | 11096 | ATP | PAT BTS | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
11121 | 11121 | ATP | PAT BTS | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11146 | 11146 | ATP | PAT BTS | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11171 | 11171 | ATP | PAT BTS | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11196 | 11196 | ATP | PAT BTS | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11221 | 11221 | ATP | PAT BTS | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11246 | 11246 | ATP | PAT BTS | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-11-16 |  | 3 | Pending
11271 | 11271 | ATP | PAT BTS | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-11-16 |  | 3 | Pending
11296 | 11296 | ATP | PAT BTS | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11321 | 11321 | ATP | PAT BTS | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11346 | 11346 | ATP | PAT BTS | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11371 | 11371 | ATP | PAT BTS | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11396 | 11396 | ATP | PAT BTS | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11421 | 11421 | ATP | PAT BTS | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11446 | 11446 | ATP | PAT BTS | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11471 | 11471 | ATP | PAT BTS | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11496 | 11496 | ATP | PAT BTS | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11521 | 11521 | ATP | PAT BTS | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
11546 | 11546 | ATP | PAT BTS | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11571 | 11571 | ATP | PAT BTS | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11596 | 11596 | ATP | PAT BTS | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11621 | 11621 | ATP | PAT BTS | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11646 | 11646 | ATP | PAT BTS | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11671 | 11671 | ATP | PAT BTS | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11696 | 11696 | ATP | PAT BTS | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11721 | 11721 | ATP | PAT BTS | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11746 | 11746 | ATP | PAT BTS | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11771 | 11771 | ATP | PAT BTS | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11796 | 11796 | ATP | PAT BTS | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11821 | 11821 | ATP | PAT BTS | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11846 | 11846 | ATP | PAT BTS | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11871 | 11871 | ATP | PAT BTS | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11896 | 11896 | ATP | PAT BTS | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11921 | 11921 | ATP | PAT BTS | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11946 | 11946 | ATP | PAT BTS | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11971 | 11971 | ATP | PAT BTS | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11996 | 11996 | ATP | PAT BTS | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12021 | 12021 | ATP | PAT BTS | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12046 | 12046 | ATP | PAT BTS | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12071 | 12071 | ATP | PAT BTS | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12096 | 12096 | ATP | PAT BTS | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-12-03 |  | 4 | Pending
12146 | 12146 | ATP | PAT BTS | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12171 | 12171 | ATP | PAT BTS | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12196 | 12196 | ATP | PAT BTS | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12221 | 12221 | ATP | PAT BTS | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12296 | 12296 | ATP | PAT BTS | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12321 | 12321 | ATP | PAT BTS | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12346 | 12346 | ATP | PAT BTS | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12371 | 12371 | ATP | PAT BTS | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12396 | 12396 | ATP | PAT BTS | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12446 | 12446 | ATP | PAT BTS | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12471 | 12471 | ATP | PAT BTS | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
12521 | 12521 | ATP | PAT BTS | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
12621 | 12621 | ATP | PAT BTS | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12646 | 12646 | ATP | PAT BTS | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12671 | 12671 | ATP | PAT BTS | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12696 | 12696 | ATP | PAT BTS | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12721 | 12721 | ATP | PAT BTS | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12746 | 12746 | ATP | PAT BTS | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12767 | 12767 | ATP | PAT BTS | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-16 |  | 1 | Pending
12792 | 12792 | ATP | PAT BTS | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-17 |  | 1 | Pending
12817 | 12817 | ATP | PAT BTS | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-17 |  | 1 | Pending
12842 | 12842 | ATP | PAT BTS | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
12867 | 12867 | ATP | PAT BTS | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12892 | 12892 | ATP | PAT BTS | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12917 | 12917 | ATP | PAT BTS | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12942 | 12942 | ATP | PAT BTS | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12967 | 12967 | ATP | PAT BTS | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12992 | 12992 | ATP | PAT BTS | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
13017 | 13017 | ATP | PAT BTS | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
13042 | 13042 | ATP | PAT BTS | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
13067 | 13067 | ATP | PAT BTS | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13092 | 13092 | ATP | PAT BTS | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13117 | 13117 | ATP | PAT BTS | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13142 | 13142 | ATP | PAT BTS | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13167 | 13167 | ATP | PAT BTS | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13192 | 13192 | ATP | PAT BTS | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13217 | 13217 | ATP | PAT BTS | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-11-28 |  | 4 | Pending
13242 | 13242 | ATP | PAT BTS | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13267 | 13267 | ATP | PAT BTS | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13292 | 13292 | ATP | PAT BTS | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13317 | 13317 | ATP | PAT BTS | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13342 | 13342 | ATP | PAT BTS | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13367 | 13367 | ATP | PAT BTS | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13392 | 13392 | ATP | PAT BTS | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13417 | 13417 | ATP | PAT BTS | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
13442 | 13442 | ATP | PAT BTS | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13467 | 13467 | ATP | PAT BTS | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13492 | 13492 | ATP | PAT BTS | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13517 | 13517 | ATP | PAT BTS | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13542 | 13542 | ATP | PAT BTS | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13567 | 13567 | ATP | PAT BTS | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13592 | 13592 | ATP | PAT BTS | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13617 | 13617 | ATP | PAT BTS | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13642 | 13642 | ATP | PAT BTS | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13667 | 13667 | ATP | PAT BTS | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13692 | 13692 | ATP | PAT BTS | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13717 | 13717 | ATP | PAT BTS | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13742 | 13742 | ATP | PAT BTS | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13767 | 13767 | ATP | PAT BTS | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13792 | 13792 | ATP | PAT BTS | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13817 | 13817 | ATP | PAT BTS | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13842 | 13842 | ATP | PAT BTS | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13867 | 13867 | ATP | PAT BTS | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13892 | 13892 | ATP | PAT BTS | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13917 | 13917 | ATP | PAT BTS | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13942 | 13942 | ATP | PAT BTS | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
13967 | 13967 | ATP | PAT BTS | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-12-23 |  | 4 | Pending
13992 | 13992 | ATP | PAT BTS | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-12-02 |  | 4 | Pending
14017 | 14017 | ATP | PAT BTS | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-12-02 |  | 4 | Pending
10019 | 10019 | ATP | PAT Power | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10044 | 10044 | ATP | PAT Power | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-21 |  | 4 | Pending
10069 | 10069 | ATP | PAT Power | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-09-23 |  | 2 | Pending
10119 | 10119 | ATP | PAT Power | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-21 |  | 4 | Pending
10144 | 10144 | ATP | PAT Power | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-23 |  | 2 | Pending
10194 | 10194 | ATP | PAT Power | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-19 |  | 4 | Pending
10219 | 10219 | ATP | PAT Power | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-19 |  | 4 | Pending
10269 | 10269 | ATP | PAT Power | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10294 | 10294 | ATP | PAT Power | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10319 | 10319 | ATP | PAT Power | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-09-05 | 2016-09-19 | 1 | Verify
10344 | 10344 | ATP | PAT Power | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-19 |  | 3 | Pending
10369 | 10369 | ATP | PAT Power | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-20 |  | 4 | Pending
10394 | 10394 | ATP | PAT Power | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-19 |  | 3 | Pending
10419 | 10419 | ATP | PAT Power | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-09-15 |  | 1 | Pending
10444 | 10444 | ATP | PAT Power | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-09-25 |  | 1 | Pending
10544 | 10544 | ATP | PAT Power | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10569 | 10569 | ATP | PAT Power | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-09-23 |  | 2 | Pending
10594 | 10594 | ATP | PAT Power | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-09-23 |  | 2 | Pending
10619 | 10619 | ATP | PAT Power | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-01 |  | 2 | Pending
10644 | 10644 | ATP | PAT Power | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-10-01 |  | 2 | Pending
10669 | 10669 | ATP | PAT Power | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-10-01 |  | 2 | Pending
10694 | 10694 | ATP | PAT Power | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-10-31 |  | 3 | Pending
10719 | 10719 | ATP | PAT Power | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2016-11-02 |  | 3 | Pending
10744 | 10744 | ATP | PAT Power | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-10-01 |  | 2 | Pending
10769 | 10769 | ATP | PAT Power | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2016-11-02 |  | 3 | Pending
10794 | 10794 | ATP | PAT Power | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-02 |  | 3 | Pending
10819 | 10819 | ATP | PAT Power | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-11-02 |  | 3 | Pending
10844 | 10844 | ATP | PAT Power | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2016-11-02 |  | 3 | Pending
10869 | 10869 | ATP | PAT Power | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2016-11-02 |  | 3 | Pending
10894 | 10894 | ATP | PAT Power | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2016-11-02 |  | 3 | Pending
10919 | 10919 | ATP | PAT Power | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2016-11-02 |  | 3 | Pending
10944 | 10944 | ATP | PAT Power | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2016-11-02 |  | 3 | Pending
10969 | 10969 | ATP | PAT Power | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-02 |  | 3 | Pending
10994 | 10994 | ATP | PAT Power | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-11-02 |  | 3 | Pending
11019 | 11019 | ATP | PAT Power | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-11-29 |  | 4 | Pending
11044 | 11044 | ATP | PAT Power | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-29 |  | 3 | Pending
11069 | 11069 | ATP | PAT Power | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-11-12 |  | 4 | Pending
11094 | 11094 | ATP | PAT Power | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-11-29 |  | 4 | Pending
11119 | 11119 | ATP | PAT Power | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-11-02 |  | 3 | Pending
11144 | 11144 | ATP | PAT Power | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-11-02 |  | 3 | Pending
11169 | 11169 | ATP | PAT Power | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-11-02 |  | 3 | Pending
11194 | 11194 | ATP | PAT Power | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-11-02 |  | 3 | Pending
11219 | 11219 | ATP | PAT Power | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-11-02 |  | 3 | Pending
11244 | 11244 | ATP | PAT Power | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-16 |  | 3 | Pending
11269 | 11269 | ATP | PAT Power | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-16 |  | 3 | Pending
11294 | 11294 | ATP | PAT Power | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-11-02 |  | 3 | Pending
11319 | 11319 | ATP | PAT Power | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-11-02 |  | 3 | Pending
11344 | 11344 | ATP | PAT Power | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-11-02 |  | 3 | Pending
11369 | 11369 | ATP | PAT Power | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-11-02 |  | 3 | Pending
11394 | 11394 | ATP | PAT Power | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-11-02 |  | 3 | Pending
11419 | 11419 | ATP | PAT Power | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-11-02 |  | 3 | Pending
11444 | 11444 | ATP | PAT Power | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-11-02 |  | 3 | Pending
11469 | 11469 | ATP | PAT Power | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-11-02 |  | 3 | Pending
11494 | 11494 | ATP | PAT Power | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-11-02 |  | 3 | Pending
11519 | 11519 | ATP | PAT Power | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-11-16 |  | 4 | Pending
11544 | 11544 | ATP | PAT Power | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-09-06 |  | 2 | Pending
11569 | 11569 | ATP | PAT Power | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-09-06 |  | 2 | Pending
11594 | 11594 | ATP | PAT Power | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-09-06 |  | 2 | Pending
11619 | 11619 | ATP | PAT Power | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-09-06 |  | 2 | Pending
11644 | 11644 | ATP | PAT Power | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-09-06 |  | 2 | Pending
11669 | 11669 | ATP | PAT Power | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-09-27 |  | 2 | Pending
11694 | 11694 | ATP | PAT Power | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-09-27 |  | 2 | Pending
11719 | 11719 | ATP | PAT Power | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-09-27 |  | 2 | Pending
11744 | 11744 | ATP | PAT Power | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-09-27 |  | 2 | Pending
11769 | 11769 | ATP | PAT Power | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-09-27 |  | 2 | Pending
11794 | 11794 | ATP | PAT Power | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-09-27 |  | 2 | Pending
11819 | 11819 | ATP | PAT Power | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-09-27 |  | 2 | Pending
11844 | 11844 | ATP | PAT Power | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-11-02 |  | 3 | Pending
11869 | 11869 | ATP | PAT Power | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-11-02 |  | 3 | Pending
11894 | 11894 | ATP | PAT Power | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-11-02 |  | 3 | Pending
11919 | 11919 | ATP | PAT Power | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-11-02 |  | 3 | Pending
11944 | 11944 | ATP | PAT Power | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-11-02 |  | 3 | Pending
11969 | 11969 | ATP | PAT Power | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-02 |  | 3 | Pending
11994 | 11994 | ATP | PAT Power | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-02 |  | 3 | Pending
12019 | 12019 | ATP | PAT Power | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-02 |  | 3 | Pending
12044 | 12044 | ATP | PAT Power | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-02 |  | 3 | Pending
12069 | 12069 | ATP | PAT Power | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-02 |  | 3 | Pending
12094 | 12094 | ATP | PAT Power | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-03 |  | 4 | Pending
12144 | 12144 | ATP | PAT Power | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-02 |  | 3 | Pending
12169 | 12169 | ATP | PAT Power | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-02 |  | 3 | Pending
12194 | 12194 | ATP | PAT Power | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-02 |  | 3 | Pending
12219 | 12219 | ATP | PAT Power | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-02 |  | 3 | Pending
12294 | 12294 | ATP | PAT Power | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-02 |  | 3 | Pending
12319 | 12319 | ATP | PAT Power | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-02 |  | 3 | Pending
12344 | 12344 | ATP | PAT Power | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-02 |  | 3 | Pending
12369 | 12369 | ATP | PAT Power | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-02 |  | 3 | Pending
12394 | 12394 | ATP | PAT Power | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-02 |  | 3 | Pending
12444 | 12444 | ATP | PAT Power | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-02 |  | 3 | Pending
12469 | 12469 | ATP | PAT Power | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-01 |  | 2 | Pending
12519 | 12519 | ATP | PAT Power | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-01 |  | 2 | Pending
12619 | 12619 | ATP | PAT Power | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-02 |  | 3 | Pending
12644 | 12644 | ATP | PAT Power | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-02 |  | 3 | Pending
12669 | 12669 | ATP | PAT Power | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-02 |  | 3 | Pending
12694 | 12694 | ATP | PAT Power | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-02 |  | 3 | Pending
12719 | 12719 | ATP | PAT Power | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-02 |  | 3 | Pending
12744 | 12744 | ATP | PAT Power | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-02 |  | 3 | Pending
12768 | 12768 | ATP | PAT Power | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-16 | 2016-08-16 | 1 | Verify
12793 | 12793 | ATP | PAT Power | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12818 | 12818 | ATP | PAT Power | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12843 | 12843 | ATP | PAT Power | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-09-27 |  | 2 | Pending
12868 | 12868 | ATP | PAT Power | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-10-23 |  | 3 | Pending
12893 | 12893 | ATP | PAT Power | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-10-23 |  | 3 | Pending
12918 | 12918 | ATP | PAT Power | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-10-23 |  | 3 | Pending
12943 | 12943 | ATP | PAT Power | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-10-23 |  | 3 | Pending
12968 | 12968 | ATP | PAT Power | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-23 |  | 3 | Pending
12993 | 12993 | ATP | PAT Power | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-10-23 |  | 3 | Pending
13018 | 13018 | ATP | PAT Power | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-02 |  | 3 | Pending
13043 | 13043 | ATP | PAT Power | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-02 |  | 3 | Pending
13068 | 13068 | ATP | PAT Power | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-10-19 |  | 3 | Pending
13093 | 13093 | ATP | PAT Power | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-10-19 |  | 3 | Pending
13118 | 13118 | ATP | PAT Power | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-10-19 |  | 3 | Pending
13143 | 13143 | ATP | PAT Power | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-10-19 |  | 3 | Pending
13168 | 13168 | ATP | PAT Power | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-10-19 |  | 3 | Pending
13193 | 13193 | ATP | PAT Power | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-10-19 |  | 3 | Pending
13218 | 13218 | ATP | PAT Power | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13243 | 13243 | ATP | PAT Power | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-17 |  | 4 | Pending
13268 | 13268 | ATP | PAT Power | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-17 |  | 4 | Pending
13293 | 13293 | ATP | PAT Power | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-17 |  | 4 | Pending
13318 | 13318 | ATP | PAT Power | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-17 |  | 4 | Pending
13343 | 13343 | ATP | PAT Power | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-17 |  | 4 | Pending
13368 | 13368 | ATP | PAT Power | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13393 | 13393 | ATP | PAT Power | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13418 | 13418 | ATP | PAT Power | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-11-27 |  | 4 | Pending
13443 | 13443 | ATP | PAT Power | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13468 | 13468 | ATP | PAT Power | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13493 | 13493 | ATP | PAT Power | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13518 | 13518 | ATP | PAT Power | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13543 | 13543 | ATP | PAT Power | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13568 | 13568 | ATP | PAT Power | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13593 | 13593 | ATP | PAT Power | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13618 | 13618 | ATP | PAT Power | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13643 | 13643 | ATP | PAT Power | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13668 | 13668 | ATP | PAT Power | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13693 | 13693 | ATP | PAT Power | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13718 | 13718 | ATP | PAT Power | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13743 | 13743 | ATP | PAT Power | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13768 | 13768 | ATP | PAT Power | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13793 | 13793 | ATP | PAT Power | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13818 | 13818 | ATP | PAT Power | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13843 | 13843 | ATP | PAT Power | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13868 | 13868 | ATP | PAT Power | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13893 | 13893 | ATP | PAT Power | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13918 | 13918 | ATP | PAT Power | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13943 | 13943 | ATP | PAT Power | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13968 | 13968 | ATP | PAT Power | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-12-23 |  | 4 | Pending
13993 | 13993 | ATP | PAT Power | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-12-02 |  | 4 | Pending
14018 | 14018 | ATP | PAT Power | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-12-02 |  | 4 | Pending
10018 | 10018 | ATP | PAT Tower | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10043 | 10043 | ATP | PAT Tower | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-21 |  | 4 | Pending
10068 | 10068 | ATP | PAT Tower | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-09-23 |  | 2 | Pending
10118 | 10118 | ATP | PAT Tower | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-21 |  | 4 | Pending
10143 | 10143 | ATP | PAT Tower | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-23 |  | 2 | Pending
10193 | 10193 | ATP | PAT Tower | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-19 |  | 4 | Pending
10218 | 10218 | ATP | PAT Tower | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-19 |  | 4 | Pending
10268 | 10268 | ATP | PAT Tower | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10293 | 10293 | ATP | PAT Tower | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10318 | 10318 | ATP | PAT Tower | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-09-05 | 2016-09-19 | 1 | Verify
10343 | 10343 | ATP | PAT Tower | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-19 |  | 3 | Pending
10368 | 10368 | ATP | PAT Tower | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-20 |  | 4 | Pending
10393 | 10393 | ATP | PAT Tower | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-19 |  | 3 | Pending
10418 | 10418 | ATP | PAT Tower | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-09-15 |  | 1 | Pending
10443 | 10443 | ATP | PAT Tower | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-09-25 |  | 1 | Pending
10543 | 10543 | ATP | PAT Tower | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10568 | 10568 | ATP | PAT Tower | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-09-23 |  | 2 | Pending
10593 | 10593 | ATP | PAT Tower | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-09-23 |  | 2 | Pending
10618 | 10618 | ATP | PAT Tower | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-01 |  | 2 | Pending
10643 | 10643 | ATP | PAT Tower | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-10-01 |  | 2 | Pending
10668 | 10668 | ATP | PAT Tower | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-10-01 |  | 2 | Pending
10693 | 10693 | ATP | PAT Tower | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-10-31 |  | 3 | Pending
10718 | 10718 | ATP | PAT Tower | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2016-11-02 |  | 3 | Pending
10743 | 10743 | ATP | PAT Tower | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-10-01 |  | 2 | Pending
10768 | 10768 | ATP | PAT Tower | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2016-11-02 |  | 3 | Pending
10793 | 10793 | ATP | PAT Tower | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-02 |  | 3 | Pending
10818 | 10818 | ATP | PAT Tower | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-11-02 |  | 3 | Pending
10843 | 10843 | ATP | PAT Tower | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2016-11-02 |  | 3 | Pending
10868 | 10868 | ATP | PAT Tower | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2016-11-02 |  | 3 | Pending
10893 | 10893 | ATP | PAT Tower | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2016-11-02 |  | 3 | Pending
10918 | 10918 | ATP | PAT Tower | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2016-11-02 |  | 3 | Pending
10943 | 10943 | ATP | PAT Tower | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2016-11-02 |  | 3 | Pending
10968 | 10968 | ATP | PAT Tower | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-02 |  | 3 | Pending
10993 | 10993 | ATP | PAT Tower | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-11-02 |  | 3 | Pending
11018 | 11018 | ATP | PAT Tower | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-11-29 |  | 4 | Pending
11043 | 11043 | ATP | PAT Tower | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-29 |  | 3 | Pending
11068 | 11068 | ATP | PAT Tower | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-11-12 |  | 4 | Pending
11093 | 11093 | ATP | PAT Tower | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-11-29 |  | 4 | Pending
11118 | 11118 | ATP | PAT Tower | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-11-02 |  | 3 | Pending
11143 | 11143 | ATP | PAT Tower | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-11-02 |  | 3 | Pending
11168 | 11168 | ATP | PAT Tower | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-11-02 |  | 3 | Pending
11193 | 11193 | ATP | PAT Tower | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-11-02 |  | 3 | Pending
11218 | 11218 | ATP | PAT Tower | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-11-02 |  | 3 | Pending
11243 | 11243 | ATP | PAT Tower | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-16 |  | 3 | Pending
11268 | 11268 | ATP | PAT Tower | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-16 |  | 3 | Pending
11293 | 11293 | ATP | PAT Tower | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-11-02 |  | 3 | Pending
11318 | 11318 | ATP | PAT Tower | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-11-02 |  | 3 | Pending
11343 | 11343 | ATP | PAT Tower | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-11-02 |  | 3 | Pending
11368 | 11368 | ATP | PAT Tower | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-11-02 |  | 3 | Pending
11393 | 11393 | ATP | PAT Tower | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-11-02 |  | 3 | Pending
11418 | 11418 | ATP | PAT Tower | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-11-02 |  | 3 | Pending
11443 | 11443 | ATP | PAT Tower | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-11-02 |  | 3 | Pending
11468 | 11468 | ATP | PAT Tower | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-11-02 |  | 3 | Pending
11493 | 11493 | ATP | PAT Tower | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-11-02 |  | 3 | Pending
11518 | 11518 | ATP | PAT Tower | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-11-16 |  | 4 | Pending
11543 | 11543 | ATP | PAT Tower | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-09-06 |  | 2 | Pending
11568 | 11568 | ATP | PAT Tower | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-09-06 |  | 2 | Pending
11593 | 11593 | ATP | PAT Tower | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-09-06 |  | 2 | Pending
11618 | 11618 | ATP | PAT Tower | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-09-06 |  | 2 | Pending
11643 | 11643 | ATP | PAT Tower | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-09-06 |  | 2 | Pending
11668 | 11668 | ATP | PAT Tower | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-09-27 |  | 2 | Pending
11693 | 11693 | ATP | PAT Tower | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-09-27 |  | 2 | Pending
11718 | 11718 | ATP | PAT Tower | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-09-27 |  | 2 | Pending
11743 | 11743 | ATP | PAT Tower | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-09-27 |  | 2 | Pending
11768 | 11768 | ATP | PAT Tower | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-09-27 |  | 2 | Pending
11793 | 11793 | ATP | PAT Tower | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-09-27 |  | 2 | Pending
11818 | 11818 | ATP | PAT Tower | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-09-27 |  | 2 | Pending
11843 | 11843 | ATP | PAT Tower | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-11-02 |  | 3 | Pending
11868 | 11868 | ATP | PAT Tower | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-11-02 |  | 3 | Pending
11893 | 11893 | ATP | PAT Tower | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-11-02 |  | 3 | Pending
11918 | 11918 | ATP | PAT Tower | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-11-02 |  | 3 | Pending
11943 | 11943 | ATP | PAT Tower | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-11-02 |  | 3 | Pending
11968 | 11968 | ATP | PAT Tower | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-02 |  | 3 | Pending
11993 | 11993 | ATP | PAT Tower | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-02 |  | 3 | Pending
12018 | 12018 | ATP | PAT Tower | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-02 |  | 3 | Pending
12043 | 12043 | ATP | PAT Tower | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-02 |  | 3 | Pending
12068 | 12068 | ATP | PAT Tower | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-02 |  | 3 | Pending
12093 | 12093 | ATP | PAT Tower | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-03 |  | 4 | Pending
12143 | 12143 | ATP | PAT Tower | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-02 |  | 3 | Pending
12168 | 12168 | ATP | PAT Tower | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-02 |  | 3 | Pending
12193 | 12193 | ATP | PAT Tower | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-02 |  | 3 | Pending
12218 | 12218 | ATP | PAT Tower | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-02 |  | 3 | Pending
12293 | 12293 | ATP | PAT Tower | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-02 |  | 3 | Pending
12318 | 12318 | ATP | PAT Tower | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-02 |  | 3 | Pending
12343 | 12343 | ATP | PAT Tower | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-02 |  | 3 | Pending
12368 | 12368 | ATP | PAT Tower | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-02 |  | 3 | Pending
12393 | 12393 | ATP | PAT Tower | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-02 |  | 3 | Pending
12443 | 12443 | ATP | PAT Tower | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-02 |  | 3 | Pending
12468 | 12468 | ATP | PAT Tower | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-01 |  | 2 | Pending
12518 | 12518 | ATP | PAT Tower | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-01 |  | 2 | Pending
12618 | 12618 | ATP | PAT Tower | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-02 |  | 3 | Pending
12643 | 12643 | ATP | PAT Tower | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-02 |  | 3 | Pending
12668 | 12668 | ATP | PAT Tower | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-02 |  | 3 | Pending
12693 | 12693 | ATP | PAT Tower | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-02 |  | 3 | Pending
12718 | 12718 | ATP | PAT Tower | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-02 |  | 3 | Pending
12743 | 12743 | ATP | PAT Tower | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-02 |  | 3 | Pending
12769 | 12769 | ATP | PAT Tower | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-16 | 2016-08-16 | 1 | Verify
12794 | 12794 | ATP | PAT Tower | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12819 | 12819 | ATP | PAT Tower | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12844 | 12844 | ATP | PAT Tower | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-09-27 |  | 2 | Pending
12869 | 12869 | ATP | PAT Tower | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-10-23 |  | 3 | Pending
12894 | 12894 | ATP | PAT Tower | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-10-23 |  | 3 | Pending
12919 | 12919 | ATP | PAT Tower | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-10-23 |  | 3 | Pending
12944 | 12944 | ATP | PAT Tower | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-10-23 |  | 3 | Pending
12969 | 12969 | ATP | PAT Tower | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-23 |  | 3 | Pending
12994 | 12994 | ATP | PAT Tower | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-10-23 |  | 3 | Pending
13019 | 13019 | ATP | PAT Tower | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-02 |  | 3 | Pending
13044 | 13044 | ATP | PAT Tower | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-02 |  | 3 | Pending
13069 | 13069 | ATP | PAT Tower | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-10-19 |  | 3 | Pending
13094 | 13094 | ATP | PAT Tower | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-10-19 |  | 3 | Pending
13119 | 13119 | ATP | PAT Tower | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-10-19 |  | 3 | Pending
13144 | 13144 | ATP | PAT Tower | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-10-19 |  | 3 | Pending
13169 | 13169 | ATP | PAT Tower | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-10-19 |  | 3 | Pending
13194 | 13194 | ATP | PAT Tower | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-10-19 |  | 3 | Pending
13219 | 13219 | ATP | PAT Tower | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13244 | 13244 | ATP | PAT Tower | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-17 |  | 4 | Pending
13269 | 13269 | ATP | PAT Tower | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-17 |  | 4 | Pending
13294 | 13294 | ATP | PAT Tower | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-17 |  | 4 | Pending
13319 | 13319 | ATP | PAT Tower | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-17 |  | 4 | Pending
13344 | 13344 | ATP | PAT Tower | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-17 |  | 4 | Pending
13369 | 13369 | ATP | PAT Tower | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13394 | 13394 | ATP | PAT Tower | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13419 | 13419 | ATP | PAT Tower | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-11-27 |  | 4 | Pending
13444 | 13444 | ATP | PAT Tower | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13469 | 13469 | ATP | PAT Tower | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13494 | 13494 | ATP | PAT Tower | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13519 | 13519 | ATP | PAT Tower | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13544 | 13544 | ATP | PAT Tower | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13569 | 13569 | ATP | PAT Tower | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13594 | 13594 | ATP | PAT Tower | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13619 | 13619 | ATP | PAT Tower | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13644 | 13644 | ATP | PAT Tower | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13669 | 13669 | ATP | PAT Tower | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13694 | 13694 | ATP | PAT Tower | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13719 | 13719 | ATP | PAT Tower | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13744 | 13744 | ATP | PAT Tower | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13769 | 13769 | ATP | PAT Tower | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13794 | 13794 | ATP | PAT Tower | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13819 | 13819 | ATP | PAT Tower | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13844 | 13844 | ATP | PAT Tower | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13869 | 13869 | ATP | PAT Tower | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13894 | 13894 | ATP | PAT Tower | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13919 | 13919 | ATP | PAT Tower | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13944 | 13944 | ATP | PAT Tower | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13969 | 13969 | ATP | PAT Tower | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-12-23 |  | 4 | Pending
13994 | 13994 | ATP | PAT Tower | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-12-02 |  | 4 | Pending
14019 | 14019 | ATP | PAT Tower | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-12-02 |  | 4 | Pending
10020 | 10020 | ATP | PAT VSAT | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | AJN | 2016-09-23 |  | 2 | Pending
10045 | 10045 | ATP | PAT VSAT | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | LA | 2016-11-21 |  | 4 | Pending
10070 | 10070 | ATP | PAT VSAT | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | AJN | 2016-09-23 |  | 2 | Pending
10120 | 10120 | ATP | PAT VSAT | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | LA | 2016-11-21 |  | 4 | Pending
10145 | 10145 | ATP | PAT VSAT | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | AJN | 2016-09-23 |  | 2 | Pending
10195 | 10195 | ATP | PAT VSAT | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | AJN | 2016-11-19 |  | 4 | Pending
10220 | 10220 | ATP | PAT VSAT | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | AJN | 2016-11-19 |  | 4 | Pending
10270 | 10270 | ATP | PAT VSAT | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | DTP | 2016-08-27 | 2016-09-19 | 1 | Verify
10295 | 10295 | ATP | PAT VSAT | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | DTP | 2016-08-27 | 2016-09-19 | 1 | Verify
10320 | 10320 | ATP | PAT VSAT | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | AJN | 2016-09-05 | 2016-09-19 | 1 | Verify
10345 | 10345 | ATP | PAT VSAT | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | AJN | 2016-10-19 |  | 3 | Pending
10370 | 10370 | ATP | PAT VSAT | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | AJN | 2016-11-20 |  | 4 | Pending
10395 | 10395 | ATP | PAT VSAT | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | AJN | 2016-10-19 |  | 3 | Pending
10420 | 10420 | ATP | PAT VSAT | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | AJN | 2016-09-15 |  | 1 | Pending
10445 | 10445 | ATP | PAT VSAT | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | AJN | 2016-09-25 |  | 1 | Pending
10545 | 10545 | ATP | PAT VSAT | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | AJN | 2016-09-23 |  | 2 | Pending
10570 | 10570 | ATP | PAT VSAT | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | AJN | 2016-09-23 |  | 2 | Pending
10595 | 10595 | ATP | PAT VSAT | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | AJN | 2016-09-23 |  | 2 | Pending
10620 | 10620 | ATP | PAT VSAT | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOM | 2016-10-01 |  | 2 | Pending
10645 | 10645 | ATP | PAT VSAT | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOM | 2016-10-01 |  | 2 | Pending
10670 | 10670 | ATP | PAT VSAT | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOM | 2016-10-01 |  | 2 | Pending
10695 | 10695 | ATP | PAT VSAT | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | IPT | 2016-10-31 |  | 3 | Pending
10720 | 10720 | ATP | PAT VSAT | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | LA | 2016-11-02 |  | 3 | Pending
10745 | 10745 | ATP | PAT VSAT | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOM | 2016-10-01 |  | 2 | Pending
10770 | 10770 | ATP | PAT VSAT | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | LA | 2016-11-02 |  | 3 | Pending
10795 | 10795 | ATP | PAT VSAT | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | IPT | 2016-11-02 |  | 3 | Pending
10820 | 10820 | ATP | PAT VSAT | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | IPT | 2016-11-02 |  | 3 | Pending
10845 | 10845 | ATP | PAT VSAT | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | LA | 2016-11-02 |  | 3 | Pending
10870 | 10870 | ATP | PAT VSAT | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | LA | 2016-11-02 |  | 3 | Pending
10895 | 10895 | ATP | PAT VSAT | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | LA | 2016-11-02 |  | 3 | Pending
10920 | 10920 | ATP | PAT VSAT | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | LA | 2016-11-02 |  | 3 | Pending
10945 | 10945 | ATP | PAT VSAT | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | LA | 2016-11-02 |  | 3 | Pending
10970 | 10970 | ATP | PAT VSAT | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | IPT | 2016-11-02 |  | 3 | Pending
10995 | 10995 | ATP | PAT VSAT | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | LA | 2016-11-02 |  | 3 | Pending
11020 | 11020 | ATP | PAT VSAT | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | LA | 2016-11-29 |  | 4 | Pending
11045 | 11045 | ATP | PAT VSAT | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | LA | 2016-11-29 |  | 3 | Pending
11070 | 11070 | ATP | PAT VSAT | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | IPT | 2016-11-12 |  | 4 | Pending
11095 | 11095 | ATP | PAT VSAT | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | IPT | 2016-11-29 |  | 4 | Pending
11120 | 11120 | ATP | PAT VSAT | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | IPT | 2016-11-02 |  | 3 | Pending
11145 | 11145 | ATP | PAT VSAT | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | AJN | 2016-11-02 |  | 3 | Pending
11170 | 11170 | ATP | PAT VSAT | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | AJN | 2016-11-02 |  | 3 | Pending
11195 | 11195 | ATP | PAT VSAT | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | IPT | 2016-11-02 |  | 3 | Pending
11220 | 11220 | ATP | PAT VSAT | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | IPT | 2016-11-02 |  | 3 | Pending
11245 | 11245 | ATP | PAT VSAT | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | IPT | 2016-11-16 |  | 3 | Pending
11270 | 11270 | ATP | PAT VSAT | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | IPT | 2016-11-16 |  | 3 | Pending
11295 | 11295 | ATP | PAT VSAT | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | AJN | 2016-11-02 |  | 3 | Pending
11320 | 11320 | ATP | PAT VSAT | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | AJN | 2016-11-02 |  | 3 | Pending
11345 | 11345 | ATP | PAT VSAT | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | AJN | 2016-11-02 |  | 3 | Pending
11370 | 11370 | ATP | PAT VSAT | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | AJN | 2016-11-02 |  | 3 | Pending
11395 | 11395 | ATP | PAT VSAT | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | IPT | 2016-11-02 |  | 3 | Pending
11420 | 11420 | ATP | PAT VSAT | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | IPT | 2016-11-02 |  | 3 | Pending
11445 | 11445 | ATP | PAT VSAT | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | IPT | 2016-11-02 |  | 3 | Pending
11470 | 11470 | ATP | PAT VSAT | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | AJN | 2016-11-02 |  | 3 | Pending
11495 | 11495 | ATP | PAT VSAT | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | MMP | 2016-11-02 |  | 3 | Pending
11520 | 11520 | ATP | PAT VSAT | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | MMP | 2016-11-16 |  | 4 | Pending
11545 | 11545 | ATP | PAT VSAT | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | AJN | 2016-09-06 |  | 2 | Pending
11570 | 11570 | ATP | PAT VSAT | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | AJN | 2016-09-06 |  | 2 | Pending
11595 | 11595 | ATP | PAT VSAT | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | AJN | 2016-09-06 |  | 2 | Pending
11620 | 11620 | ATP | PAT VSAT | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | AJN | 2016-09-06 |  | 2 | Pending
11645 | 11645 | ATP | PAT VSAT | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | AJN | 2016-09-06 |  | 2 | Pending
11670 | 11670 | ATP | PAT VSAT | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOM | 2016-09-27 |  | 2 | Pending
11695 | 11695 | ATP | PAT VSAT | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | IPT | 2016-09-27 |  | 2 | Pending
11720 | 11720 | ATP | PAT VSAT | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOM | 2016-09-27 |  | 2 | Pending
11745 | 11745 | ATP | PAT VSAT | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | IPT | 2016-09-27 |  | 2 | Pending
11770 | 11770 | ATP | PAT VSAT | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | IPT | 2016-09-27 |  | 2 | Pending
11795 | 11795 | ATP | PAT VSAT | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | IPT | 2016-09-27 |  | 2 | Pending
11820 | 11820 | ATP | PAT VSAT | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | IPT | 2016-09-27 |  | 2 | Pending
11845 | 11845 | ATP | PAT VSAT | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | MMP | 2016-11-02 |  | 3 | Pending
11870 | 11870 | ATP | PAT VSAT | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | MMP | 2016-11-02 |  | 3 | Pending
11895 | 11895 | ATP | PAT VSAT | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | MMP | 2016-11-02 |  | 3 | Pending
11920 | 11920 | ATP | PAT VSAT | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | MMP | 2016-11-02 |  | 3 | Pending
11945 | 11945 | ATP | PAT VSAT | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | MMP | 2016-11-02 |  | 3 | Pending
11970 | 11970 | ATP | PAT VSAT | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | IPT | 2016-11-02 |  | 3 | Pending
11995 | 11995 | ATP | PAT VSAT | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | IPT | 2016-11-02 |  | 3 | Pending
12020 | 12020 | ATP | PAT VSAT | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | AJN | 2016-11-02 |  | 3 | Pending
12045 | 12045 | ATP | PAT VSAT | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | AJN | 2016-11-02 |  | 3 | Pending
12070 | 12070 | ATP | PAT VSAT | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | AJN | 2016-11-02 |  | 3 | Pending
12095 | 12095 | ATP | PAT VSAT | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | AJN | 2016-12-03 |  | 4 | Pending
12145 | 12145 | ATP | PAT VSAT | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | IPT | 2016-11-02 |  | 3 | Pending
12170 | 12170 | ATP | PAT VSAT | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | IPT | 2016-11-02 |  | 3 | Pending
12195 | 12195 | ATP | PAT VSAT | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | IPT | 2016-11-02 |  | 3 | Pending
12220 | 12220 | ATP | PAT VSAT | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | IPT | 2016-11-02 |  | 3 | Pending
12295 | 12295 | ATP | PAT VSAT | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | AJN | 2016-11-02 |  | 3 | Pending
12320 | 12320 | ATP | PAT VSAT | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | AJN | 2016-11-02 |  | 3 | Pending
12345 | 12345 | ATP | PAT VSAT | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | AJN | 2016-11-02 |  | 3 | Pending
12370 | 12370 | ATP | PAT VSAT | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | AJN | 2016-11-02 |  | 3 | Pending
12395 | 12395 | ATP | PAT VSAT | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | AJN | 2016-11-02 |  | 3 | Pending
12445 | 12445 | ATP | PAT VSAT | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | AJN | 2016-11-02 |  | 3 | Pending
12470 | 12470 | ATP | PAT VSAT | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOM | 2016-10-01 |  | 2 | Pending
12520 | 12520 | ATP | PAT VSAT | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOM | 2016-10-01 |  | 2 | Pending
12620 | 12620 | ATP | PAT VSAT | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | MMP | 2016-11-02 |  | 3 | Pending
12645 | 12645 | ATP | PAT VSAT | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | MMP | 2016-11-02 |  | 3 | Pending
12670 | 12670 | ATP | PAT VSAT | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | MMP | 2016-11-02 |  | 3 | Pending
12695 | 12695 | ATP | PAT VSAT | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | MMP | 2016-11-02 |  | 3 | Pending
12720 | 12720 | ATP | PAT VSAT | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | MMP | 2016-11-02 |  | 3 | Pending
12745 | 12745 | ATP | PAT VSAT | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | MMP | 2016-11-02 |  | 3 | Pending
12770 | 12770 | ATP | PAT VSAT | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | MMP | 2016-08-16 |  | 1 | Pending
12795 | 12795 | ATP | PAT VSAT | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | MMP | 2016-08-17 |  | 1 | Pending
12820 | 12820 | ATP | PAT VSAT | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | MMP | 2016-08-17 |  | 1 | Pending
12845 | 12845 | ATP | PAT VSAT | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | AJN | 2016-09-27 |  | 2 | Pending
12870 | 12870 | ATP | PAT VSAT | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | MMP | 2016-10-23 |  | 3 | Pending
12895 | 12895 | ATP | PAT VSAT | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | MMP | 2016-10-23 |  | 3 | Pending
12920 | 12920 | ATP | PAT VSAT | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | MMP | 2016-10-23 |  | 3 | Pending
12945 | 12945 | ATP | PAT VSAT | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | MMP | 2016-10-23 |  | 3 | Pending
12970 | 12970 | ATP | PAT VSAT | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | IPT | 2016-10-23 |  | 3 | Pending
12995 | 12995 | ATP | PAT VSAT | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | MMP | 2016-10-23 |  | 3 | Pending
13020 | 13020 | ATP | PAT VSAT | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | MMP | 2016-11-02 |  | 3 | Pending
13045 | 13045 | ATP | PAT VSAT | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | MMP | 2016-11-02 |  | 3 | Pending
13070 | 13070 | ATP | PAT VSAT | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | MMP | 2016-10-19 |  | 3 | Pending
13095 | 13095 | ATP | PAT VSAT | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | MMP | 2016-10-19 |  | 3 | Pending
13120 | 13120 | ATP | PAT VSAT | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | MMP | 2016-10-19 |  | 3 | Pending
13145 | 13145 | ATP | PAT VSAT | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | MMP | 2016-10-19 |  | 3 | Pending
13170 | 13170 | ATP | PAT VSAT | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | MMP | 2016-10-19 |  | 3 | Pending
13195 | 13195 | ATP | PAT VSAT | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | MMP | 2016-10-19 |  | 3 | Pending
13220 | 13220 | ATP | PAT VSAT | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-11-28 |  | 4 | Pending
13245 | 13245 | ATP | PAT VSAT | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | MMP | 2016-12-17 |  | 4 | Pending
13270 | 13270 | ATP | PAT VSAT | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | MMP | 2016-12-17 |  | 4 | Pending
13295 | 13295 | ATP | PAT VSAT | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | MMP | 2016-12-17 |  | 4 | Pending
13320 | 13320 | ATP | PAT VSAT | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | MMP | 2016-12-17 |  | 4 | Pending
13345 | 13345 | ATP | PAT VSAT | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | MMP | 2016-12-17 |  | 4 | Pending
13370 | 13370 | ATP | PAT VSAT | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13395 | 13395 | ATP | PAT VSAT | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13420 | 13420 | ATP | PAT VSAT | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-11-27 |  | 4 | Pending
13445 | 13445 | ATP | PAT VSAT | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13470 | 13470 | ATP | PAT VSAT | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13495 | 13495 | ATP | PAT VSAT | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13520 | 13520 | ATP | PAT VSAT | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13545 | 13545 | ATP | PAT VSAT | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13570 | 13570 | ATP | PAT VSAT | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13595 | 13595 | ATP | PAT VSAT | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13620 | 13620 | ATP | PAT VSAT | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13645 | 13645 | ATP | PAT VSAT | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13670 | 13670 | ATP | PAT VSAT | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13695 | 13695 | ATP | PAT VSAT | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13720 | 13720 | ATP | PAT VSAT | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13745 | 13745 | ATP | PAT VSAT | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13770 | 13770 | ATP | PAT VSAT | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13795 | 13795 | ATP | PAT VSAT | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13820 | 13820 | ATP | PAT VSAT | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13845 | 13845 | ATP | PAT VSAT | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13870 | 13870 | ATP | PAT VSAT | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13895 | 13895 | ATP | PAT VSAT | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13920 | 13920 | ATP | PAT VSAT | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13945 | 13945 | ATP | PAT VSAT | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-11-27 |  | 4 | Pending
13970 | 13970 | ATP | PAT VSAT | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-12-23 |  | 4 | Pending
13995 | 13995 | ATP | PAT VSAT | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-12-02 |  | 4 | Pending
14020 | 14020 | ATP | PAT VSAT | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-12-02 |  | 4 | Pending
10025 | 10025 | ATP | SIR BTS | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10050 | 10050 | ATP | SIR BTS | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
10075 | 10075 | ATP | SIR BTS | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10125 | 10125 | ATP | SIR BTS | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
10150 | 10150 | ATP | SIR BTS | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10200 | 10200 | ATP | SIR BTS | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | TELKOMSEL | 2016-11-19 |  | 4 | Pending
10225 | 10225 | ATP | SIR BTS | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | TELKOMSEL | 2016-11-19 |  | 4 | Pending
10275 | 10275 | ATP | SIR BTS | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | TELKOMSEL | 2016-08-27 | 2016-09-19 | 1 | Verify
10300 | 10300 | ATP | SIR BTS | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | TELKOMSEL | 2016-08-27 | 2016-09-19 | 1 | Verify
10325 | 10325 | ATP | SIR BTS | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | TELKOMSEL | 2016-09-05 | 2016-09-19 | 1 | Verify
10350 | 10350 | ATP | SIR BTS | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
10375 | 10375 | ATP | SIR BTS | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
10400 | 10400 | ATP | SIR BTS | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
10425 | 10425 | ATP | SIR BTS | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | TELKOMSEL | 2016-09-15 |  | 1 | Pending
10450 | 10450 | ATP | SIR BTS | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | TELKOMSEL | 2016-09-25 |  | 1 | Pending
10550 | 10550 | ATP | SIR BTS | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10575 | 10575 | ATP | SIR BTS | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10600 | 10600 | ATP | SIR BTS | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | TELKOMSEL | 2016-09-23 |  | 2 | Pending
10625 | 10625 | ATP | SIR BTS | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10650 | 10650 | ATP | SIR BTS | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10675 | 10675 | ATP | SIR BTS | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10700 | 10700 | ATP | SIR BTS | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | TELKOMSEL | 2016-10-31 |  | 3 | Pending
10725 | 10725 | ATP | SIR BTS | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10750 | 10750 | ATP | SIR BTS | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
10775 | 10775 | ATP | SIR BTS | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10800 | 10800 | ATP | SIR BTS | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10825 | 10825 | ATP | SIR BTS | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10850 | 10850 | ATP | SIR BTS | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10875 | 10875 | ATP | SIR BTS | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10900 | 10900 | ATP | SIR BTS | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10925 | 10925 | ATP | SIR BTS | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10950 | 10950 | ATP | SIR BTS | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
10975 | 10975 | ATP | SIR BTS | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11000 | 11000 | ATP | SIR BTS | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11025 | 11025 | ATP | SIR BTS | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
11050 | 11050 | ATP | SIR BTS | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | TELKOMSEL | 2016-11-29 |  | 3 | Pending
11075 | 11075 | ATP | SIR BTS | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | TELKOMSEL | 2016-11-12 |  | 4 | Pending
11100 | 11100 | ATP | SIR BTS | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
11125 | 11125 | ATP | SIR BTS | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11150 | 11150 | ATP | SIR BTS | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11175 | 11175 | ATP | SIR BTS | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11200 | 11200 | ATP | SIR BTS | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11225 | 11225 | ATP | SIR BTS | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11250 | 11250 | ATP | SIR BTS | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | TELKOMSEL | 2016-11-16 |  | 3 | Pending
11275 | 11275 | ATP | SIR BTS | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | TELKOMSEL | 2016-11-16 |  | 3 | Pending
11300 | 11300 | ATP | SIR BTS | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11325 | 11325 | ATP | SIR BTS | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11350 | 11350 | ATP | SIR BTS | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11375 | 11375 | ATP | SIR BTS | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11400 | 11400 | ATP | SIR BTS | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11425 | 11425 | ATP | SIR BTS | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11450 | 11450 | ATP | SIR BTS | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11475 | 11475 | ATP | SIR BTS | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11500 | 11500 | ATP | SIR BTS | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11525 | 11525 | ATP | SIR BTS | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | TELKOMSEL | 2016-11-16 |  | 4 | Pending
11550 | 11550 | ATP | SIR BTS | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11575 | 11575 | ATP | SIR BTS | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11600 | 11600 | ATP | SIR BTS | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11625 | 11625 | ATP | SIR BTS | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11650 | 11650 | ATP | SIR BTS | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | TELKOMSEL | 2016-09-06 |  | 2 | Pending
11675 | 11675 | ATP | SIR BTS | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11700 | 11700 | ATP | SIR BTS | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11725 | 11725 | ATP | SIR BTS | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11750 | 11750 | ATP | SIR BTS | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11775 | 11775 | ATP | SIR BTS | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11800 | 11800 | ATP | SIR BTS | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11825 | 11825 | ATP | SIR BTS | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
11850 | 11850 | ATP | SIR BTS | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11875 | 11875 | ATP | SIR BTS | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11900 | 11900 | ATP | SIR BTS | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11925 | 11925 | ATP | SIR BTS | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11950 | 11950 | ATP | SIR BTS | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
11975 | 11975 | ATP | SIR BTS | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12000 | 12000 | ATP | SIR BTS | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12025 | 12025 | ATP | SIR BTS | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12050 | 12050 | ATP | SIR BTS | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12075 | 12075 | ATP | SIR BTS | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12100 | 12100 | ATP | SIR BTS | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | TELKOMSEL | 2016-12-03 |  | 4 | Pending
12150 | 12150 | ATP | SIR BTS | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12175 | 12175 | ATP | SIR BTS | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12200 | 12200 | ATP | SIR BTS | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12225 | 12225 | ATP | SIR BTS | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12300 | 12300 | ATP | SIR BTS | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12325 | 12325 | ATP | SIR BTS | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12350 | 12350 | ATP | SIR BTS | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12375 | 12375 | ATP | SIR BTS | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12400 | 12400 | ATP | SIR BTS | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12450 | 12450 | ATP | SIR BTS | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12475 | 12475 | ATP | SIR BTS | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
12525 | 12525 | ATP | SIR BTS | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOMSEL | 2016-10-01 |  | 2 | Pending
12625 | 12625 | ATP | SIR BTS | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12650 | 12650 | ATP | SIR BTS | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12675 | 12675 | ATP | SIR BTS | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12700 | 12700 | ATP | SIR BTS | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12725 | 12725 | ATP | SIR BTS | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12750 | 12750 | ATP | SIR BTS | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
12771 | 12771 | ATP | SIR BTS | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | TELKOMSEL | 2016-08-16 |  | 1 | Pending
12796 | 12796 | ATP | SIR BTS | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | TELKOMSEL | 2016-08-17 |  | 1 | Pending
12821 | 12821 | ATP | SIR BTS | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | TELKOMSEL | 2016-08-17 |  | 1 | Pending
12846 | 12846 | ATP | SIR BTS | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | TELKOMSEL | 2016-09-27 |  | 2 | Pending
12871 | 12871 | ATP | SIR BTS | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12896 | 12896 | ATP | SIR BTS | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12921 | 12921 | ATP | SIR BTS | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12946 | 12946 | ATP | SIR BTS | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12971 | 12971 | ATP | SIR BTS | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
12996 | 12996 | ATP | SIR BTS | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | TELKOMSEL | 2016-10-23 |  | 3 | Pending
13021 | 13021 | ATP | SIR BTS | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
13046 | 13046 | ATP | SIR BTS | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | TELKOMSEL | 2016-11-02 |  | 3 | Pending
13071 | 13071 | ATP | SIR BTS | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13096 | 13096 | ATP | SIR BTS | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13121 | 13121 | ATP | SIR BTS | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13146 | 13146 | ATP | SIR BTS | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13171 | 13171 | ATP | SIR BTS | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13196 | 13196 | ATP | SIR BTS | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | TELKOMSEL | 2016-10-19 |  | 3 | Pending
13221 | 13221 | ATP | SIR BTS | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | TELKOMSEL | 2016-11-28 |  | 4 | Pending
13246 | 13246 | ATP | SIR BTS | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13271 | 13271 | ATP | SIR BTS | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13296 | 13296 | ATP | SIR BTS | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13321 | 13321 | ATP | SIR BTS | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13346 | 13346 | ATP | SIR BTS | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | TELKOMSEL | 2016-12-17 |  | 4 | Pending
13371 | 13371 | ATP | SIR BTS | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13396 | 13396 | ATP | SIR BTS | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | TELKOMSEL | 2016-11-20 |  | 4 | Pending
13421 | 13421 | ATP | SIR BTS | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
13446 | 13446 | ATP | SIR BTS | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13471 | 13471 | ATP | SIR BTS | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13496 | 13496 | ATP | SIR BTS | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13521 | 13521 | ATP | SIR BTS | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13546 | 13546 | ATP | SIR BTS | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | TELKOMSEL | 2016-11-21 |  | 4 | Pending
13571 | 13571 | ATP | SIR BTS | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13596 | 13596 | ATP | SIR BTS | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13621 | 13621 | ATP | SIR BTS | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13646 | 13646 | ATP | SIR BTS | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13671 | 13671 | ATP | SIR BTS | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13696 | 13696 | ATP | SIR BTS | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | TELKOMSEL | 2016-11-22 |  | 4 | Pending
13721 | 13721 | ATP | SIR BTS | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13746 | 13746 | ATP | SIR BTS | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13771 | 13771 | ATP | SIR BTS | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13796 | 13796 | ATP | SIR BTS | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13821 | 13821 | ATP | SIR BTS | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13846 | 13846 | ATP | SIR BTS | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13871 | 13871 | ATP | SIR BTS | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13896 | 13896 | ATP | SIR BTS | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13921 | 13921 | ATP | SIR BTS | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | TELKOMSEL | 2016-11-29 |  | 4 | Pending
13946 | 13946 | ATP | SIR BTS | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | TELKOMSEL | 2016-11-27 |  | 4 | Pending
13971 | 13971 | ATP | SIR BTS | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | TELKOMSEL | 2016-12-23 |  | 4 | Pending
13996 | 13996 | ATP | SIR BTS | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | TELKOMSEL | 2016-12-02 |  | 4 | Pending
14021 | 14021 | ATP | SIR BTS | Maluku | UZZ51x | Desa Wemala | 0 | 0 | TELKOMSEL | 2016-12-02 |  | 4 | Pending
10023 | 10023 | ATP | SIR Sps | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10048 | 10048 | ATP | SIR Sps | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-21 |  | 4 | Pending
10073 | 10073 | ATP | SIR Sps | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-09-23 |  | 2 | Pending
10123 | 10123 | ATP | SIR Sps | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-21 |  | 4 | Pending
10148 | 10148 | ATP | SIR Sps | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-23 |  | 2 | Pending
10198 | 10198 | ATP | SIR Sps | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-19 |  | 4 | Pending
10223 | 10223 | ATP | SIR Sps | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-19 |  | 4 | Pending
10273 | 10273 | ATP | SIR Sps | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10298 | 10298 | ATP | SIR Sps | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10323 | 10323 | ATP | SIR Sps | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-09-05 | 2016-09-19 | 1 | Verify
10348 | 10348 | ATP | SIR Sps | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-19 |  | 3 | Pending
10373 | 10373 | ATP | SIR Sps | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-20 |  | 4 | Pending
10398 | 10398 | ATP | SIR Sps | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-19 |  | 3 | Pending
10423 | 10423 | ATP | SIR Sps | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-09-15 |  | 1 | Pending
10448 | 10448 | ATP | SIR Sps | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-09-25 |  | 1 | Pending
10548 | 10548 | ATP | SIR Sps | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10573 | 10573 | ATP | SIR Sps | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-09-23 |  | 2 | Pending
10598 | 10598 | ATP | SIR Sps | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-09-23 |  | 2 | Pending
10623 | 10623 | ATP | SIR Sps | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-01 |  | 2 | Pending
10648 | 10648 | ATP | SIR Sps | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-10-01 |  | 2 | Pending
10673 | 10673 | ATP | SIR Sps | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-10-01 |  | 2 | Pending
10698 | 10698 | ATP | SIR Sps | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-10-31 |  | 3 | Pending
10723 | 10723 | ATP | SIR Sps | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2016-11-02 |  | 3 | Pending
10748 | 10748 | ATP | SIR Sps | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-10-01 |  | 2 | Pending
10773 | 10773 | ATP | SIR Sps | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2016-11-02 |  | 3 | Pending
10798 | 10798 | ATP | SIR Sps | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-02 |  | 3 | Pending
10823 | 10823 | ATP | SIR Sps | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-11-02 |  | 3 | Pending
10848 | 10848 | ATP | SIR Sps | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2016-11-02 |  | 3 | Pending
10873 | 10873 | ATP | SIR Sps | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2016-11-02 |  | 3 | Pending
10898 | 10898 | ATP | SIR Sps | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2016-11-02 |  | 3 | Pending
10923 | 10923 | ATP | SIR Sps | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2016-11-02 |  | 3 | Pending
10948 | 10948 | ATP | SIR Sps | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2016-11-02 |  | 3 | Pending
10973 | 10973 | ATP | SIR Sps | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-02 |  | 3 | Pending
10998 | 10998 | ATP | SIR Sps | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-11-02 |  | 3 | Pending
11023 | 11023 | ATP | SIR Sps | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-11-29 |  | 4 | Pending
11048 | 11048 | ATP | SIR Sps | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-29 |  | 3 | Pending
11073 | 11073 | ATP | SIR Sps | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-11-12 |  | 4 | Pending
11098 | 11098 | ATP | SIR Sps | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-11-29 |  | 4 | Pending
11123 | 11123 | ATP | SIR Sps | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-11-02 |  | 3 | Pending
11148 | 11148 | ATP | SIR Sps | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-11-02 |  | 3 | Pending
11173 | 11173 | ATP | SIR Sps | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-11-02 |  | 3 | Pending
11198 | 11198 | ATP | SIR Sps | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-11-02 |  | 3 | Pending
11223 | 11223 | ATP | SIR Sps | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-11-02 |  | 3 | Pending
11248 | 11248 | ATP | SIR Sps | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-16 |  | 3 | Pending
11273 | 11273 | ATP | SIR Sps | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-16 |  | 3 | Pending
11298 | 11298 | ATP | SIR Sps | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-11-02 |  | 3 | Pending
11323 | 11323 | ATP | SIR Sps | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-11-02 |  | 3 | Pending
11348 | 11348 | ATP | SIR Sps | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-11-02 |  | 3 | Pending
11373 | 11373 | ATP | SIR Sps | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-11-02 |  | 3 | Pending
11398 | 11398 | ATP | SIR Sps | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-11-02 |  | 3 | Pending
11423 | 11423 | ATP | SIR Sps | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-11-02 |  | 3 | Pending
11448 | 11448 | ATP | SIR Sps | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-11-02 |  | 3 | Pending
11473 | 11473 | ATP | SIR Sps | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-11-02 |  | 3 | Pending
11498 | 11498 | ATP | SIR Sps | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-11-02 |  | 3 | Pending
11523 | 11523 | ATP | SIR Sps | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-11-16 |  | 4 | Pending
11548 | 11548 | ATP | SIR Sps | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-09-06 |  | 2 | Pending
11573 | 11573 | ATP | SIR Sps | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-09-06 |  | 2 | Pending
11598 | 11598 | ATP | SIR Sps | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-09-06 |  | 2 | Pending
11623 | 11623 | ATP | SIR Sps | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-09-06 |  | 2 | Pending
11648 | 11648 | ATP | SIR Sps | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-09-06 |  | 2 | Pending
11673 | 11673 | ATP | SIR Sps | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-09-27 |  | 2 | Pending
11698 | 11698 | ATP | SIR Sps | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-09-27 |  | 2 | Pending
11723 | 11723 | ATP | SIR Sps | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-09-27 |  | 2 | Pending
11748 | 11748 | ATP | SIR Sps | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-09-27 |  | 2 | Pending
11773 | 11773 | ATP | SIR Sps | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-09-27 |  | 2 | Pending
11798 | 11798 | ATP | SIR Sps | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-09-27 |  | 2 | Pending
11823 | 11823 | ATP | SIR Sps | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-09-27 |  | 2 | Pending
11848 | 11848 | ATP | SIR Sps | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-11-02 |  | 3 | Pending
11873 | 11873 | ATP | SIR Sps | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-11-02 |  | 3 | Pending
11898 | 11898 | ATP | SIR Sps | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-11-02 |  | 3 | Pending
11923 | 11923 | ATP | SIR Sps | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-11-02 |  | 3 | Pending
11948 | 11948 | ATP | SIR Sps | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-11-02 |  | 3 | Pending
11973 | 11973 | ATP | SIR Sps | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-02 |  | 3 | Pending
11998 | 11998 | ATP | SIR Sps | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-02 |  | 3 | Pending
12023 | 12023 | ATP | SIR Sps | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-02 |  | 3 | Pending
12048 | 12048 | ATP | SIR Sps | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-02 |  | 3 | Pending
12073 | 12073 | ATP | SIR Sps | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-02 |  | 3 | Pending
12098 | 12098 | ATP | SIR Sps | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-03 |  | 4 | Pending
12148 | 12148 | ATP | SIR Sps | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-02 |  | 3 | Pending
12173 | 12173 | ATP | SIR Sps | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-02 |  | 3 | Pending
12198 | 12198 | ATP | SIR Sps | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-02 |  | 3 | Pending
12223 | 12223 | ATP | SIR Sps | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-02 |  | 3 | Pending
12298 | 12298 | ATP | SIR Sps | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-02 |  | 3 | Pending
12323 | 12323 | ATP | SIR Sps | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-02 |  | 3 | Pending
12348 | 12348 | ATP | SIR Sps | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-02 |  | 3 | Pending
12373 | 12373 | ATP | SIR Sps | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-02 |  | 3 | Pending
12398 | 12398 | ATP | SIR Sps | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-02 |  | 3 | Pending
12448 | 12448 | ATP | SIR Sps | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-02 |  | 3 | Pending
12473 | 12473 | ATP | SIR Sps | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-01 |  | 2 | Pending
12523 | 12523 | ATP | SIR Sps | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-01 |  | 2 | Pending
12623 | 12623 | ATP | SIR Sps | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-02 |  | 3 | Pending
12648 | 12648 | ATP | SIR Sps | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-02 |  | 3 | Pending
12673 | 12673 | ATP | SIR Sps | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-02 |  | 3 | Pending
12698 | 12698 | ATP | SIR Sps | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-02 |  | 3 | Pending
12723 | 12723 | ATP | SIR Sps | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-02 |  | 3 | Pending
12748 | 12748 | ATP | SIR Sps | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-02 |  | 3 | Pending
12772 | 12772 | ATP | SIR Sps | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-16 | 2016-08-16 | 1 | Verify
12797 | 12797 | ATP | SIR Sps | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12822 | 12822 | ATP | SIR Sps | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12847 | 12847 | ATP | SIR Sps | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-09-27 |  | 2 | Pending
12872 | 12872 | ATP | SIR Sps | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-10-23 |  | 3 | Pending
12897 | 12897 | ATP | SIR Sps | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-10-23 |  | 3 | Pending
12922 | 12922 | ATP | SIR Sps | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-10-23 |  | 3 | Pending
12947 | 12947 | ATP | SIR Sps | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-10-23 |  | 3 | Pending
12972 | 12972 | ATP | SIR Sps | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-23 |  | 3 | Pending
12997 | 12997 | ATP | SIR Sps | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-10-23 |  | 3 | Pending
13022 | 13022 | ATP | SIR Sps | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-02 |  | 3 | Pending
13047 | 13047 | ATP | SIR Sps | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-02 |  | 3 | Pending
13072 | 13072 | ATP | SIR Sps | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-10-19 |  | 3 | Pending
13097 | 13097 | ATP | SIR Sps | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-10-19 |  | 3 | Pending
13122 | 13122 | ATP | SIR Sps | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-10-19 |  | 3 | Pending
13147 | 13147 | ATP | SIR Sps | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-10-19 |  | 3 | Pending
13172 | 13172 | ATP | SIR Sps | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-10-19 |  | 3 | Pending
13197 | 13197 | ATP | SIR Sps | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-10-19 |  | 3 | Pending
13222 | 13222 | ATP | SIR Sps | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13247 | 13247 | ATP | SIR Sps | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-17 |  | 4 | Pending
13272 | 13272 | ATP | SIR Sps | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-17 |  | 4 | Pending
13297 | 13297 | ATP | SIR Sps | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-17 |  | 4 | Pending
13322 | 13322 | ATP | SIR Sps | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-17 |  | 4 | Pending
13347 | 13347 | ATP | SIR Sps | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-17 |  | 4 | Pending
13372 | 13372 | ATP | SIR Sps | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13397 | 13397 | ATP | SIR Sps | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13422 | 13422 | ATP | SIR Sps | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-11-27 |  | 4 | Pending
13447 | 13447 | ATP | SIR Sps | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13472 | 13472 | ATP | SIR Sps | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13497 | 13497 | ATP | SIR Sps | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13522 | 13522 | ATP | SIR Sps | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13547 | 13547 | ATP | SIR Sps | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13572 | 13572 | ATP | SIR Sps | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13597 | 13597 | ATP | SIR Sps | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13622 | 13622 | ATP | SIR Sps | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13647 | 13647 | ATP | SIR Sps | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13672 | 13672 | ATP | SIR Sps | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13697 | 13697 | ATP | SIR Sps | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13722 | 13722 | ATP | SIR Sps | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13747 | 13747 | ATP | SIR Sps | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13772 | 13772 | ATP | SIR Sps | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13797 | 13797 | ATP | SIR Sps | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13822 | 13822 | ATP | SIR Sps | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13847 | 13847 | ATP | SIR Sps | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13872 | 13872 | ATP | SIR Sps | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13897 | 13897 | ATP | SIR Sps | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13922 | 13922 | ATP | SIR Sps | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13947 | 13947 | ATP | SIR Sps | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13972 | 13972 | ATP | SIR Sps | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-12-23 |  | 4 | Pending
13997 | 13997 | ATP | SIR Sps | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-12-02 |  | 4 | Pending
14022 | 14022 | ATP | SIR Sps | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-12-02 |  | 4 | Pending
10022 | 10022 | ATP | SIR Tower | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10047 | 10047 | ATP | SIR Tower | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | SEI | 2016-11-21 |  | 4 | Pending
10072 | 10072 | ATP | SIR Tower | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | SEI | 2016-09-23 |  | 2 | Pending
10122 | 10122 | ATP | SIR Tower | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | SEI | 2016-11-21 |  | 4 | Pending
10147 | 10147 | ATP | SIR Tower | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | SEI | 2016-09-23 |  | 2 | Pending
10197 | 10197 | ATP | SIR Tower | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | SEI | 2016-11-19 |  | 4 | Pending
10222 | 10222 | ATP | SIR Tower | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | SEI | 2016-11-19 |  | 4 | Pending
10272 | 10272 | ATP | SIR Tower | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10297 | 10297 | ATP | SIR Tower | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | SEI | 2016-08-27 | 2016-09-19 | 1 | Verify
10322 | 10322 | ATP | SIR Tower | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | SEI | 2016-09-05 | 2016-09-19 | 1 | Verify
10347 | 10347 | ATP | SIR Tower | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | SEI | 2016-10-19 |  | 3 | Pending
10372 | 10372 | ATP | SIR Tower | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | SEI | 2016-11-20 |  | 4 | Pending
10397 | 10397 | ATP | SIR Tower | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | SEI | 2016-10-19 |  | 3 | Pending
10422 | 10422 | ATP | SIR Tower | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | SEI | 2016-09-15 |  | 1 | Pending
10447 | 10447 | ATP | SIR Tower | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | SEI | 2016-09-25 |  | 1 | Pending
10547 | 10547 | ATP | SIR Tower | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | SEI | 2016-09-23 |  | 2 | Pending
10572 | 10572 | ATP | SIR Tower | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | SEI | 2016-09-23 |  | 2 | Pending
10597 | 10597 | ATP | SIR Tower | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | SEI | 2016-09-23 |  | 2 | Pending
10622 | 10622 | ATP | SIR Tower | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | SEI | 2016-10-01 |  | 2 | Pending
10647 | 10647 | ATP | SIR Tower | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | SEI | 2016-10-01 |  | 2 | Pending
10672 | 10672 | ATP | SIR Tower | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | SEI | 2016-10-01 |  | 2 | Pending
10697 | 10697 | ATP | SIR Tower | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | SEI | 2016-10-31 |  | 3 | Pending
10722 | 10722 | ATP | SIR Tower | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | SEI | 2016-11-02 |  | 3 | Pending
10747 | 10747 | ATP | SIR Tower | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | SEI | 2016-10-01 |  | 2 | Pending
10772 | 10772 | ATP | SIR Tower | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | SEI | 2016-11-02 |  | 3 | Pending
10797 | 10797 | ATP | SIR Tower | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | SEI | 2016-11-02 |  | 3 | Pending
10822 | 10822 | ATP | SIR Tower | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | SEI | 2016-11-02 |  | 3 | Pending
10847 | 10847 | ATP | SIR Tower | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | SEI | 2016-11-02 |  | 3 | Pending
10872 | 10872 | ATP | SIR Tower | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | SEI | 2016-11-02 |  | 3 | Pending
10897 | 10897 | ATP | SIR Tower | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | SEI | 2016-11-02 |  | 3 | Pending
10922 | 10922 | ATP | SIR Tower | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | SEI | 2016-11-02 |  | 3 | Pending
10947 | 10947 | ATP | SIR Tower | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | SEI | 2016-11-02 |  | 3 | Pending
10972 | 10972 | ATP | SIR Tower | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | SEI | 2016-11-02 |  | 3 | Pending
10997 | 10997 | ATP | SIR Tower | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | SEI | 2016-11-02 |  | 3 | Pending
11022 | 11022 | ATP | SIR Tower | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | SEI | 2016-11-29 |  | 4 | Pending
11047 | 11047 | ATP | SIR Tower | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | SEI | 2016-11-29 |  | 3 | Pending
11072 | 11072 | ATP | SIR Tower | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | SEI | 2016-11-12 |  | 4 | Pending
11097 | 11097 | ATP | SIR Tower | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | SEI | 2016-11-29 |  | 4 | Pending
11122 | 11122 | ATP | SIR Tower | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | SEI | 2016-11-02 |  | 3 | Pending
11147 | 11147 | ATP | SIR Tower | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | SEI | 2016-11-02 |  | 3 | Pending
11172 | 11172 | ATP | SIR Tower | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | SEI | 2016-11-02 |  | 3 | Pending
11197 | 11197 | ATP | SIR Tower | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | SEI | 2016-11-02 |  | 3 | Pending
11222 | 11222 | ATP | SIR Tower | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | SEI | 2016-11-02 |  | 3 | Pending
11247 | 11247 | ATP | SIR Tower | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | SEI | 2016-11-16 |  | 3 | Pending
11272 | 11272 | ATP | SIR Tower | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | SEI | 2016-11-16 |  | 3 | Pending
11297 | 11297 | ATP | SIR Tower | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | SEI | 2016-11-02 |  | 3 | Pending
11322 | 11322 | ATP | SIR Tower | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | SEI | 2016-11-02 |  | 3 | Pending
11347 | 11347 | ATP | SIR Tower | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | SEI | 2016-11-02 |  | 3 | Pending
11372 | 11372 | ATP | SIR Tower | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | SEI | 2016-11-02 |  | 3 | Pending
11397 | 11397 | ATP | SIR Tower | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | SEI | 2016-11-02 |  | 3 | Pending
11422 | 11422 | ATP | SIR Tower | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | SEI | 2016-11-02 |  | 3 | Pending
11447 | 11447 | ATP | SIR Tower | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | SEI | 2016-11-02 |  | 3 | Pending
11472 | 11472 | ATP | SIR Tower | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | SEI | 2016-11-02 |  | 3 | Pending
11497 | 11497 | ATP | SIR Tower | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | SEI | 2016-11-02 |  | 3 | Pending
11522 | 11522 | ATP | SIR Tower | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | BIN | 2016-11-16 |  | 4 | Pending
11547 | 11547 | ATP | SIR Tower | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | SEI | 2016-09-06 |  | 2 | Pending
11572 | 11572 | ATP | SIR Tower | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | SEI | 2016-09-06 |  | 2 | Pending
11597 | 11597 | ATP | SIR Tower | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | SEI | 2016-09-06 |  | 2 | Pending
11622 | 11622 | ATP | SIR Tower | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | SEI | 2016-09-06 |  | 2 | Pending
11647 | 11647 | ATP | SIR Tower | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | SEI | 2016-09-06 |  | 2 | Pending
11672 | 11672 | ATP | SIR Tower | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | SEI | 2016-09-27 |  | 2 | Pending
11697 | 11697 | ATP | SIR Tower | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | SEI | 2016-09-27 |  | 2 | Pending
11722 | 11722 | ATP | SIR Tower | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | SEI | 2016-09-27 |  | 2 | Pending
11747 | 11747 | ATP | SIR Tower | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | SEI | 2016-09-27 |  | 2 | Pending
11772 | 11772 | ATP | SIR Tower | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | SEI | 2016-09-27 |  | 2 | Pending
11797 | 11797 | ATP | SIR Tower | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | SEI | 2016-09-27 |  | 2 | Pending
11822 | 11822 | ATP | SIR Tower | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | SEI | 2016-09-27 |  | 2 | Pending
11847 | 11847 | ATP | SIR Tower | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | SEI | 2016-11-02 |  | 3 | Pending
11872 | 11872 | ATP | SIR Tower | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | SEI | 2016-11-02 |  | 3 | Pending
11897 | 11897 | ATP | SIR Tower | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | SEI | 2016-11-02 |  | 3 | Pending
11922 | 11922 | ATP | SIR Tower | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | SEI | 2016-11-02 |  | 3 | Pending
11947 | 11947 | ATP | SIR Tower | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | SEI | 2016-11-02 |  | 3 | Pending
11972 | 11972 | ATP | SIR Tower | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | SEI | 2016-11-02 |  | 3 | Pending
11997 | 11997 | ATP | SIR Tower | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | SEI | 2016-11-02 |  | 3 | Pending
12022 | 12022 | ATP | SIR Tower | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | SEI | 2016-11-02 |  | 3 | Pending
12047 | 12047 | ATP | SIR Tower | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | SEI | 2016-11-02 |  | 3 | Pending
12072 | 12072 | ATP | SIR Tower | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | SEI | 2016-11-02 |  | 3 | Pending
12097 | 12097 | ATP | SIR Tower | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | SEI | 2016-12-03 |  | 4 | Pending
12147 | 12147 | ATP | SIR Tower | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | SEI | 2016-11-02 |  | 3 | Pending
12172 | 12172 | ATP | SIR Tower | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | SEI | 2016-11-02 |  | 3 | Pending
12197 | 12197 | ATP | SIR Tower | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | SEI | 2016-11-02 |  | 3 | Pending
12222 | 12222 | ATP | SIR Tower | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | SEI | 2016-11-02 |  | 3 | Pending
12297 | 12297 | ATP | SIR Tower | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | SEI | 2016-11-02 |  | 3 | Pending
12322 | 12322 | ATP | SIR Tower | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | SEI | 2016-11-02 |  | 3 | Pending
12347 | 12347 | ATP | SIR Tower | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | SEI | 2016-11-02 |  | 3 | Pending
12372 | 12372 | ATP | SIR Tower | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | SEI | 2016-11-02 |  | 3 | Pending
12397 | 12397 | ATP | SIR Tower | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | SEI | 2016-11-02 |  | 3 | Pending
12447 | 12447 | ATP | SIR Tower | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | SEI | 2016-11-02 |  | 3 | Pending
12472 | 12472 | ATP | SIR Tower | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | SEI | 2016-10-01 |  | 2 | Pending
12522 | 12522 | ATP | SIR Tower | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | SEI | 2016-10-01 |  | 2 | Pending
12622 | 12622 | ATP | SIR Tower | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | SEI | 2016-11-02 |  | 3 | Pending
12647 | 12647 | ATP | SIR Tower | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | SEI | 2016-11-02 |  | 3 | Pending
12672 | 12672 | ATP | SIR Tower | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | SEI | 2016-11-02 |  | 3 | Pending
12697 | 12697 | ATP | SIR Tower | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | SEI | 2016-11-02 |  | 3 | Pending
12722 | 12722 | ATP | SIR Tower | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | SEI | 2016-11-02 |  | 3 | Pending
12747 | 12747 | ATP | SIR Tower | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | SEI | 2016-11-02 |  | 3 | Pending
12773 | 12773 | ATP | SIR Tower | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | PEMDA | 2016-08-16 | 2016-08-16 | 1 | Verify
12798 | 12798 | ATP | SIR Tower | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12823 | 12823 | ATP | SIR Tower | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | PEMDA | 2016-08-17 | 2016-08-17 | 1 | Verify
12848 | 12848 | ATP | SIR Tower | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | SEI | 2016-09-27 |  | 2 | Pending
12873 | 12873 | ATP | SIR Tower | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | SEI | 2016-10-23 |  | 3 | Pending
12898 | 12898 | ATP | SIR Tower | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | SEI | 2016-10-23 |  | 3 | Pending
12923 | 12923 | ATP | SIR Tower | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | SEI | 2016-10-23 |  | 3 | Pending
12948 | 12948 | ATP | SIR Tower | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | SEI | 2016-10-23 |  | 3 | Pending
12973 | 12973 | ATP | SIR Tower | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | SEI | 2016-10-23 |  | 3 | Pending
12998 | 12998 | ATP | SIR Tower | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | SEI | 2016-10-23 |  | 3 | Pending
13023 | 13023 | ATP | SIR Tower | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | SEI | 2016-11-02 |  | 3 | Pending
13048 | 13048 | ATP | SIR Tower | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | SEI | 2016-11-02 |  | 3 | Pending
13073 | 13073 | ATP | SIR Tower | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | SEI | 2016-10-19 |  | 3 | Pending
13098 | 13098 | ATP | SIR Tower | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | SEI | 2016-10-19 |  | 3 | Pending
13123 | 13123 | ATP | SIR Tower | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | SEI | 2016-10-19 |  | 3 | Pending
13148 | 13148 | ATP | SIR Tower | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | SEI | 2016-10-19 |  | 3 | Pending
13173 | 13173 | ATP | SIR Tower | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | SEI | 2016-10-19 |  | 3 | Pending
13198 | 13198 | ATP | SIR Tower | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | SEI | 2016-10-19 |  | 3 | Pending
13223 | 13223 | ATP | SIR Tower | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | SEI | 2016-11-28 |  | 4 | Pending
13248 | 13248 | ATP | SIR Tower | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | SEI | 2016-12-17 |  | 4 | Pending
13273 | 13273 | ATP | SIR Tower | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | SEI | 2016-12-17 |  | 4 | Pending
13298 | 13298 | ATP | SIR Tower | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | SEI | 2016-12-17 |  | 4 | Pending
13323 | 13323 | ATP | SIR Tower | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | SEI | 2016-12-17 |  | 4 | Pending
13348 | 13348 | ATP | SIR Tower | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | SEI | 2016-12-17 |  | 4 | Pending
13373 | 13373 | ATP | SIR Tower | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13398 | 13398 | ATP | SIR Tower | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | BIN | 2016-11-20 |  | 4 | Pending
13423 | 13423 | ATP | SIR Tower | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | PEMDA | 2016-11-27 |  | 4 | Pending
13448 | 13448 | ATP | SIR Tower | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13473 | 13473 | ATP | SIR Tower | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13498 | 13498 | ATP | SIR Tower | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13523 | 13523 | ATP | SIR Tower | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13548 | 13548 | ATP | SIR Tower | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | SEI | 2016-11-21 |  | 4 | Pending
13573 | 13573 | ATP | SIR Tower | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13598 | 13598 | ATP | SIR Tower | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13623 | 13623 | ATP | SIR Tower | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13648 | 13648 | ATP | SIR Tower | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13673 | 13673 | ATP | SIR Tower | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13698 | 13698 | ATP | SIR Tower | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | SEI | 2016-11-22 |  | 4 | Pending
13723 | 13723 | ATP | SIR Tower | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13748 | 13748 | ATP | SIR Tower | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13773 | 13773 | ATP | SIR Tower | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13798 | 13798 | ATP | SIR Tower | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13823 | 13823 | ATP | SIR Tower | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13848 | 13848 | ATP | SIR Tower | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13873 | 13873 | ATP | SIR Tower | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13898 | 13898 | ATP | SIR Tower | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13923 | 13923 | ATP | SIR Tower | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | SEI | 2016-11-29 |  | 4 | Pending
13948 | 13948 | ATP | SIR Tower | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | SEI | 2016-11-27 |  | 4 | Pending
13973 | 13973 | ATP | SIR Tower | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | SEI | 2016-12-23 |  | 4 | Pending
13998 | 13998 | ATP | SIR Tower | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | SEI | 2016-12-02 |  | 4 | Pending
14023 | 14023 | ATP | SIR Tower | Maluku | UZZ51x | Desa Wemala | 0 | 0 | SEI | 2016-12-02 |  | 4 | Pending
10024 | 10024 | ATP | SIR VSAT | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | AJN | 2016-09-23 |  | 2 | Pending
10049 | 10049 | ATP | SIR VSAT | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | LA | 2016-11-21 |  | 4 | Pending
10074 | 10074 | ATP | SIR VSAT | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | AJN | 2016-09-23 |  | 2 | Pending
10124 | 10124 | ATP | SIR VSAT | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | LA | 2016-11-21 |  | 4 | Pending
10149 | 10149 | ATP | SIR VSAT | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | AJN | 2016-09-23 |  | 2 | Pending
10199 | 10199 | ATP | SIR VSAT | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | AJN | 2016-11-19 |  | 4 | Pending
10224 | 10224 | ATP | SIR VSAT | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | AJN | 2016-11-19 |  | 4 | Pending
10274 | 10274 | ATP | SIR VSAT | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | DTP | 2016-08-27 | 2016-09-19 | 1 | Verify
10299 | 10299 | ATP | SIR VSAT | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | DTP | 2016-08-27 | 2016-09-19 | 1 | Verify
10324 | 10324 | ATP | SIR VSAT | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | AJN | 2016-09-05 | 2016-09-19 | 1 | Verify
10349 | 10349 | ATP | SIR VSAT | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | AJN | 2016-10-19 |  | 3 | Pending
10374 | 10374 | ATP | SIR VSAT | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | AJN | 2016-11-20 |  | 4 | Pending
10399 | 10399 | ATP | SIR VSAT | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | AJN | 2016-10-19 |  | 3 | Pending
10424 | 10424 | ATP | SIR VSAT | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | AJN | 2016-09-15 |  | 1 | Pending
10449 | 10449 | ATP | SIR VSAT | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | AJN | 2016-09-25 |  | 1 | Pending
10549 | 10549 | ATP | SIR VSAT | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | AJN | 2016-09-23 |  | 2 | Pending
10574 | 10574 | ATP | SIR VSAT | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | AJN | 2016-09-23 |  | 2 | Pending
10599 | 10599 | ATP | SIR VSAT | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | AJN | 2016-09-23 |  | 2 | Pending
10624 | 10624 | ATP | SIR VSAT | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | TELKOM | 2016-10-01 |  | 2 | Pending
10649 | 10649 | ATP | SIR VSAT | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | TELKOM | 2016-10-01 |  | 2 | Pending
10674 | 10674 | ATP | SIR VSAT | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | TELKOM | 2016-10-01 |  | 2 | Pending
10699 | 10699 | ATP | SIR VSAT | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | IPT | 2016-10-31 |  | 3 | Pending
10724 | 10724 | ATP | SIR VSAT | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | LA | 2016-11-02 |  | 3 | Pending
10749 | 10749 | ATP | SIR VSAT | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | TELKOM | 2016-10-01 |  | 2 | Pending
10774 | 10774 | ATP | SIR VSAT | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | LA | 2016-11-02 |  | 3 | Pending
10799 | 10799 | ATP | SIR VSAT | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | IPT | 2016-11-02 |  | 3 | Pending
10824 | 10824 | ATP | SIR VSAT | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | IPT | 2016-11-02 |  | 3 | Pending
10849 | 10849 | ATP | SIR VSAT | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | LA | 2016-11-02 |  | 3 | Pending
10874 | 10874 | ATP | SIR VSAT | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | LA | 2016-11-02 |  | 3 | Pending
10899 | 10899 | ATP | SIR VSAT | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | LA | 2016-11-02 |  | 3 | Pending
10924 | 10924 | ATP | SIR VSAT | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | LA | 2016-11-02 |  | 3 | Pending
10949 | 10949 | ATP | SIR VSAT | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | LA | 2016-11-02 |  | 3 | Pending
10974 | 10974 | ATP | SIR VSAT | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | IPT | 2016-11-02 |  | 3 | Pending
10999 | 10999 | ATP | SIR VSAT | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | LA | 2016-11-02 |  | 3 | Pending
11024 | 11024 | ATP | SIR VSAT | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | LA | 2016-11-29 |  | 4 | Pending
11049 | 11049 | ATP | SIR VSAT | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | LA | 2016-11-29 |  | 3 | Pending
11074 | 11074 | ATP | SIR VSAT | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | IPT | 2016-11-12 |  | 4 | Pending
11099 | 11099 | ATP | SIR VSAT | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | IPT | 2016-11-29 |  | 4 | Pending
11124 | 11124 | ATP | SIR VSAT | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | IPT | 2016-11-02 |  | 3 | Pending
11149 | 11149 | ATP | SIR VSAT | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | AJN | 2016-11-02 |  | 3 | Pending
11174 | 11174 | ATP | SIR VSAT | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | AJN | 2016-11-02 |  | 3 | Pending
11199 | 11199 | ATP | SIR VSAT | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | IPT | 2016-11-02 |  | 3 | Pending
11224 | 11224 | ATP | SIR VSAT | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | IPT | 2016-11-02 |  | 3 | Pending
11249 | 11249 | ATP | SIR VSAT | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | IPT | 2016-11-16 |  | 3 | Pending
11274 | 11274 | ATP | SIR VSAT | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | IPT | 2016-11-16 |  | 3 | Pending
11299 | 11299 | ATP | SIR VSAT | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | AJN | 2016-11-02 |  | 3 | Pending
11324 | 11324 | ATP | SIR VSAT | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | AJN | 2016-11-02 |  | 3 | Pending
11349 | 11349 | ATP | SIR VSAT | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | AJN | 2016-11-02 |  | 3 | Pending
11374 | 11374 | ATP | SIR VSAT | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | AJN | 2016-11-02 |  | 3 | Pending
11399 | 11399 | ATP | SIR VSAT | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | IPT | 2016-11-02 |  | 3 | Pending
11424 | 11424 | ATP | SIR VSAT | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | IPT | 2016-11-02 |  | 3 | Pending
11449 | 11449 | ATP | SIR VSAT | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | IPT | 2016-11-02 |  | 3 | Pending
11474 | 11474 | ATP | SIR VSAT | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | AJN | 2016-11-02 |  | 3 | Pending
11499 | 11499 | ATP | SIR VSAT | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | MMP | 2016-11-02 |  | 3 | Pending
11524 | 11524 | ATP | SIR VSAT | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | MMP | 2016-11-16 |  | 4 | Pending
11549 | 11549 | ATP | SIR VSAT | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | AJN | 2016-09-06 |  | 2 | Pending
11574 | 11574 | ATP | SIR VSAT | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | AJN | 2016-09-06 |  | 2 | Pending
11599 | 11599 | ATP | SIR VSAT | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | AJN | 2016-09-06 |  | 2 | Pending
11624 | 11624 | ATP | SIR VSAT | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | AJN | 2016-09-06 |  | 2 | Pending
11649 | 11649 | ATP | SIR VSAT | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | AJN | 2016-09-06 |  | 2 | Pending
11674 | 11674 | ATP | SIR VSAT | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | TELKOM | 2016-09-27 |  | 2 | Pending
11699 | 11699 | ATP | SIR VSAT | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | IPT | 2016-09-27 |  | 2 | Pending
11724 | 11724 | ATP | SIR VSAT | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | TELKOM | 2016-09-27 |  | 2 | Pending
11749 | 11749 | ATP | SIR VSAT | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | IPT | 2016-09-27 |  | 2 | Pending
11774 | 11774 | ATP | SIR VSAT | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | IPT | 2016-09-27 |  | 2 | Pending
11799 | 11799 | ATP | SIR VSAT | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | IPT | 2016-09-27 |  | 2 | Pending
11824 | 11824 | ATP | SIR VSAT | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | IPT | 2016-09-27 |  | 2 | Pending
11849 | 11849 | ATP | SIR VSAT | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | MMP | 2016-11-02 |  | 3 | Pending
11874 | 11874 | ATP | SIR VSAT | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | MMP | 2016-11-02 |  | 3 | Pending
11899 | 11899 | ATP | SIR VSAT | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | MMP | 2016-11-02 |  | 3 | Pending
11924 | 11924 | ATP | SIR VSAT | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | MMP | 2016-11-02 |  | 3 | Pending
11949 | 11949 | ATP | SIR VSAT | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | MMP | 2016-11-02 |  | 3 | Pending
11974 | 11974 | ATP | SIR VSAT | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | IPT | 2016-11-02 |  | 3 | Pending
11999 | 11999 | ATP | SIR VSAT | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | IPT | 2016-11-02 |  | 3 | Pending
12024 | 12024 | ATP | SIR VSAT | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | AJN | 2016-11-02 |  | 3 | Pending
12049 | 12049 | ATP | SIR VSAT | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | AJN | 2016-11-02 |  | 3 | Pending
12074 | 12074 | ATP | SIR VSAT | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | AJN | 2016-11-02 |  | 3 | Pending
12099 | 12099 | ATP | SIR VSAT | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | AJN | 2016-12-03 |  | 4 | Pending
12149 | 12149 | ATP | SIR VSAT | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | IPT | 2016-11-02 |  | 3 | Pending
12174 | 12174 | ATP | SIR VSAT | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | IPT | 2016-11-02 |  | 3 | Pending
12199 | 12199 | ATP | SIR VSAT | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | IPT | 2016-11-02 |  | 3 | Pending
12224 | 12224 | ATP | SIR VSAT | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | IPT | 2016-11-02 |  | 3 | Pending
12299 | 12299 | ATP | SIR VSAT | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | AJN | 2016-11-02 |  | 3 | Pending
12324 | 12324 | ATP | SIR VSAT | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | AJN | 2016-11-02 |  | 3 | Pending
12349 | 12349 | ATP | SIR VSAT | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | AJN | 2016-11-02 |  | 3 | Pending
12374 | 12374 | ATP | SIR VSAT | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | AJN | 2016-11-02 |  | 3 | Pending
12399 | 12399 | ATP | SIR VSAT | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | AJN | 2016-11-02 |  | 3 | Pending
12449 | 12449 | ATP | SIR VSAT | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | AJN | 2016-11-02 |  | 3 | Pending
12474 | 12474 | ATP | SIR VSAT | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | TELKOM | 2016-10-01 |  | 2 | Pending
12524 | 12524 | ATP | SIR VSAT | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | TELKOM | 2016-10-01 |  | 2 | Pending
12624 | 12624 | ATP | SIR VSAT | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | MMP | 2016-11-02 |  | 3 | Pending
12649 | 12649 | ATP | SIR VSAT | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | MMP | 2016-11-02 |  | 3 | Pending
12674 | 12674 | ATP | SIR VSAT | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | MMP | 2016-11-02 |  | 3 | Pending
12699 | 12699 | ATP | SIR VSAT | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | MMP | 2016-11-02 |  | 3 | Pending
12724 | 12724 | ATP | SIR VSAT | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | MMP | 2016-11-02 |  | 3 | Pending
12749 | 12749 | ATP | SIR VSAT | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | MMP | 2016-11-02 |  | 3 | Pending
12774 | 12774 | ATP | SIR VSAT | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | MMP | 2016-08-16 |  | 1 | Pending
12799 | 12799 | ATP | SIR VSAT | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | MMP | 2016-08-17 |  | 1 | Pending
12824 | 12824 | ATP | SIR VSAT | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | MMP | 2016-08-17 |  | 1 | Pending
12849 | 12849 | ATP | SIR VSAT | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | AJN | 2016-09-27 |  | 2 | Pending
12874 | 12874 | ATP | SIR VSAT | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | MMP | 2016-10-23 |  | 3 | Pending
12899 | 12899 | ATP | SIR VSAT | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | MMP | 2016-10-23 |  | 3 | Pending
12924 | 12924 | ATP | SIR VSAT | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | MMP | 2016-10-23 |  | 3 | Pending
12949 | 12949 | ATP | SIR VSAT | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | MMP | 2016-10-23 |  | 3 | Pending
12974 | 12974 | ATP | SIR VSAT | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | IPT | 2016-10-23 |  | 3 | Pending
12999 | 12999 | ATP | SIR VSAT | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | MMP | 2016-10-23 |  | 3 | Pending
13024 | 13024 | ATP | SIR VSAT | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | MMP | 2016-11-02 |  | 3 | Pending
13049 | 13049 | ATP | SIR VSAT | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | MMP | 2016-11-02 |  | 3 | Pending
13074 | 13074 | ATP | SIR VSAT | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | MMP | 2016-10-19 |  | 3 | Pending
13099 | 13099 | ATP | SIR VSAT | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | MMP | 2016-10-19 |  | 3 | Pending
13124 | 13124 | ATP | SIR VSAT | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | MMP | 2016-10-19 |  | 3 | Pending
13149 | 13149 | ATP | SIR VSAT | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | MMP | 2016-10-19 |  | 3 | Pending
13174 | 13174 | ATP | SIR VSAT | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | MMP | 2016-10-19 |  | 3 | Pending
13199 | 13199 | ATP | SIR VSAT | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | MMP | 2016-10-19 |  | 3 | Pending
13224 | 13224 | ATP | SIR VSAT | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-11-28 |  | 4 | Pending
13249 | 13249 | ATP | SIR VSAT | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | MMP | 2016-12-17 |  | 4 | Pending
13274 | 13274 | ATP | SIR VSAT | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | MMP | 2016-12-17 |  | 4 | Pending
13299 | 13299 | ATP | SIR VSAT | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | MMP | 2016-12-17 |  | 4 | Pending
13324 | 13324 | ATP | SIR VSAT | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | MMP | 2016-12-17 |  | 4 | Pending
13349 | 13349 | ATP | SIR VSAT | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | MMP | 2016-12-17 |  | 4 | Pending
13374 | 13374 | ATP | SIR VSAT | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13399 | 13399 | ATP | SIR VSAT | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-11-20 |  | 4 | Pending
13424 | 13424 | ATP | SIR VSAT | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-11-27 |  | 4 | Pending
13449 | 13449 | ATP | SIR VSAT | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13474 | 13474 | ATP | SIR VSAT | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13499 | 13499 | ATP | SIR VSAT | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13524 | 13524 | ATP | SIR VSAT | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13549 | 13549 | ATP | SIR VSAT | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-11-21 |  | 4 | Pending
13574 | 13574 | ATP | SIR VSAT | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13599 | 13599 | ATP | SIR VSAT | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13624 | 13624 | ATP | SIR VSAT | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13649 | 13649 | ATP | SIR VSAT | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13674 | 13674 | ATP | SIR VSAT | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13699 | 13699 | ATP | SIR VSAT | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-11-22 |  | 4 | Pending
13724 | 13724 | ATP | SIR VSAT | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13749 | 13749 | ATP | SIR VSAT | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13774 | 13774 | ATP | SIR VSAT | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13799 | 13799 | ATP | SIR VSAT | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13824 | 13824 | ATP | SIR VSAT | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13849 | 13849 | ATP | SIR VSAT | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13874 | 13874 | ATP | SIR VSAT | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13899 | 13899 | ATP | SIR VSAT | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13924 | 13924 | ATP | SIR VSAT | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-11-29 |  | 4 | Pending
13949 | 13949 | ATP | SIR VSAT | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-11-27 |  | 4 | Pending
13974 | 13974 | ATP | SIR VSAT | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-12-23 |  | 4 | Pending
13999 | 13999 | ATP | SIR VSAT | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-12-02 |  | 4 | Pending
14024 | 14024 | ATP | SIR VSAT | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-12-02 |  | 4 | Pending
10001 | 10001 | Survey | SSR Investigation | Kalimantan Barat | UXB043 | Sungai Uluk Paling | 112.7772 | 1.0432 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10026 | 10026 | Survey | SSR Investigation | Kalimantan Barat | UXB044 | Desa Sei Balacan | 109.3855 | 1.938 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
10051 | 10051 | Survey | SSR Investigation | Kalimantan Barat | UXB045 | Desa Lauk | 112.6618 | 1.1246 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10101 | 10101 | Survey | SSR Investigation | Kalimantan Barat | UXB047 | Desa Temajuk, Dusun Sempadan | 109.6195 | 2.0075 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
10126 | 10126 | Survey | SSR Investigation | Kalimantan Barat | UXB048 | Desa rantau Prapat | 112.6061 | 1.1307 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10176 | 10176 | Survey | SSR Investigation | Kalimantan Barat | UXB053 | Site Asuasang | 109.4618 | 1.7788 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
10201 | 10201 | Survey | SSR Investigation | Kalimantan Barat | UXB054 | Site Sungai Bening / Dusun air Bening | 109.5776 | 1.7469 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
10251 | 10251 | Survey | SSR Investigation | Kalimantan Barat | UXB056 | Dusun Mangkau (Pala Pasang) | 110.2266 | 1.0332 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
10276 | 10276 | Survey | SSR Investigation | Kalimantan Barat | UXB057 | Dusun Pala Pasang | 110.2197 | 1.0753 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
10301 | 10301 | Survey | SSR Investigation | Kalimantan Barat | UXB058 | Dusun Suruh Engkadok | 110.1984 | 1.0546 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
10326 | 10326 | Survey | SSR Investigation | Kalimantan Barat | UXB059 | Desa Sepiluk | 110.9273 | 0.79072 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10351 | 10351 | Survey | SSR Investigation | Kalimantan Barat | UXB060 | Desa Tangguh | 110.0063 | 1.1901 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
10376 | 10376 | Survey | SSR Investigation | Kalimantan Barat | UXB061 | Desa Muakan Petinggi | 110.9423 | 0.90738 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10401 | 10401 | Survey | SSR Investigation | Kalimantan Barat | UXB062 | Dusun Gita Jaya | 110.1444 | 1.0514 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
10426 | 10426 | Survey | SSR Investigation | Kalimantan Barat | UXB063 | Dusun Gun Jemak | 110.1664 | 1.1355 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
10526 | 10526 | Survey | SSR Investigation | Kalimantan Barat | UXB067 | Ulak Pauk | 112.4925 | 1.0432 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10551 | 10551 | Survey | SSR Investigation | Kalimantan Barat | UXB068 | Bungan Jaya | 113.6111 | 0.96792 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10576 | 10576 | Survey | SSR Investigation | Kalimantan Barat | UXB069 | Kareho | 113.3667 | 0.76568 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10601 | 10601 | Survey | SSR Investigation | Kalimantan Timur | UXJ852 | Desa Rantau Buta | 115.961 | -1.7433 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10626 | 10626 | Survey | SSR Investigation | Kalimantan Timur | UXJ855 | Desa Long Tuyoq | 114.7589 | 0.99236 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10651 | 10651 | Survey | SSR Investigation | Kalimantan Utara | UXL003 | Punan Bengalun | 116.6565 | 3.4076 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10676 | 10676 | Survey | SSR Investigation | Kalimantan Utara | UXL004 | Tanjung Nanga | 116.4583 | 3.07 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10701 | 10701 | Survey | SSR Investigation | Kalimantan Utara | UXL005 | Pa Upan | 115.7469 | 3.569 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10726 | 10726 | Survey | SSR Investigation | Kalimantan Utara | UXL006 | Desa Long Rungan | 115.8434 | 3.5984 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
10751 | 10751 | Survey | SSR Investigation | Kalimantan Utara | UXL007 | Long Padi | 115.8487 | 3.7152 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10776 | 10776 | Survey | SSR Investigation | Kalimantan Utara | UXL008 | desa ba'lik | 115.8473 | 3.7934 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10801 | 10801 | Survey | SSR Investigation | Kalimantan Utara | UXL009 | Long Pada | 116.1437 | 3.0564 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10826 | 10826 | Survey | SSR Investigation | Kalimantan Utara | UXL010 | desa long puak | 115.7138 | 3.7914 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10851 | 10851 | Survey | SSR Investigation | Kalimantan Utara | UXL011 | Desa Pa' Padi | 115.7532 | 3.8149 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10876 | 10876 | Survey | SSR Investigation | Kalimantan Utara | UXL012 | Desa Lembudud | 115.6447 | 3.8065 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10901 | 10901 | Survey | SSR Investigation | Kalimantan Utara | UXL013 | Long Midang, Desa Pa' Rupai | 115.6148 | 3.923 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10926 | 10926 | Survey | SSR Investigation | Kalimantan Utara | UXL014 | Desa Long Umung | 115.7659 | 3.9627 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10951 | 10951 | Survey | SSR Investigation | Kalimantan Utara | UXL015 | Tang Paye Desa lembada | 115.6454 | 3.8673 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
10976 | 10976 | Survey | SSR Investigation | Kalimantan Utara | UXL016 | Terang Baru | 115.7284 | 3.9007 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11001 | 11001 | Survey | SSR Investigation | Kalimantan Utara | UXL017 | Desa Long Metun | 115.07 | 1.9394 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
11026 | 11026 | Survey | SSR Investigation | Kalimantan Utara | UXL018 | Desa Sai Anai | 115.0371 | 1.9223 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11051 | 11051 | Survey | SSR Investigation | Kalimantan Utara | UXL019 | Desa Long Payau | 114.9492 | 1.8032 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
11076 | 11076 | Survey | SSR Investigation | Kalimantan Utara | UXL020 | Desa Lidung Payau | 115.016 | 1.6785 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
11101 | 11101 | Survey | SSR Investigation | Kalimantan Utara | UXL021 | Desa Tinampak | 116.9725 | 4.1578 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11126 | 11126 | Survey | SSR Investigation | Kalimantan Utara | UXL023 | Desa Ubol | 116.6111 | 3.9178 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11151 | 11151 | Survey | SSR Investigation | Kalimantan Utara | UXL025 | Suman Tobol | 116.5022 | 4.2177 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11176 | 11176 | Survey | SSR Investigation | Kalimantan Utara | UXL026 | Desa Labang | 116.4137 | 4.2915 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11201 | 11201 | Survey | SSR Investigation | Kalimantan Utara | UXL027 | Desa Panas | 116.3072 | 4.2953 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11226 | 11226 | Survey | SSR Investigation | Kalimantan Utara | UXL028 | Apau Ping | 115.8175 | 3.1024 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11251 | 11251 | Survey | SSR Investigation | Kalimantan Utara | UXL029 | Long Berini | 115.8579 | 3.0484 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11276 | 11276 | Survey | SSR Investigation | Kalimantan Utara | UXL030 | Long Paliran | 115.7849 | 2.705 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11301 | 11301 | Survey | SSR Investigation | Kalimantan Utara | UXL031 | Long Jelet | 115.6381 | 2.4819 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11326 | 11326 | Survey | SSR Investigation | Kalimantan Utara | UXL032 | Long Bena | 115.5787 | 2.7976 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11351 | 11351 | Survey | SSR Investigation | Kalimantan Utara | UXL033 | Long Belaka Pitau | 115.7281 | 2.6903 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11376 | 11376 | Survey | SSR Investigation | Kalimantan Utara | UXL034 | LONG ARAN | 115.8183 | 2.5435 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11401 | 11401 | Survey | SSR Investigation | Kalimantan Utara | UXL035 | LONG PUA | 115.671 | 2.5457 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11426 | 11426 | Survey | SSR Investigation | Kalimantan Utara | UXL036 | Long Ketaman | 115.7576 | 2.5536 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11451 | 11451 | Survey | SSR Investigation | Kalimantan Utara | UXL054 | Desa Suka Maju | 116.5678 | 3.9293 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11476 | 11476 | Survey | SSR Investigation | NTT | UXQ076 | Amfoang Timur Desa Nunuanah | 123.9442 | -9.4129 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11501 | 11501 | Survey | SSR Investigation | NTT | UXQ077 | Amfoang Timur Desa Netemnanu Utara | 124.0359 | -9.3562 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
11526 | 11526 | Survey | SSR Investigation | NTT | UXQ078 | Desa Sunsea - Naibenu | 124.4676 | -9.3359 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11551 | 11551 | Survey | SSR Investigation | NTT | UXQ079 | Desa Bakitolas-Naibenu | 124.502 | -9.2996 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11576 | 11576 | Survey | SSR Investigation | NTT | UXQ080 | Desa Benus-Naibenu | 124.5031 | -9.2742 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11601 | 11601 | Survey | SSR Investigation | NTT | UXQ081 | Desa Tasinifu Kec. Mutis | 124.2529 | -9.4258 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11626 | 11626 | Survey | SSR Investigation | NTT | UXQ082 | Desa naikake a- kec.mutis | 124.2103 | -9.4266 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11651 | 11651 | Survey | SSR Investigation | NTT | UXQ083 | Desa Tude | 124.0542 | -8.4481 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11676 | 11676 | Survey | SSR Investigation | NTT | UXQ084 | Desa Nule | 124.24 | -8.3735 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11701 | 11701 | Survey | SSR Investigation | NTT | UXQ085 | Desa Langkuru Utara | 124.8246 | -8.3347 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11726 | 11726 | Survey | SSR Investigation | NTT | UXQ086 | Desa Langkuru | 124.8331 | -8.3836 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11751 | 11751 | Survey | SSR Investigation | NTT | UXQ087 | Desa Kailesa | 124.8556 | -8.3478 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11776 | 11776 | Survey | SSR Investigation | NTT | UXQ088 | Desa Purnama | 124.8938 | -8.363 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11801 | 11801 | Survey | SSR Investigation | NTT | UXQ089 | Desa Tanglapui | 124.9501 | -8.2691 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
11826 | 11826 | Survey | SSR Investigation | NTT | UXQ090 | Desa Lakatuli | 124.6655 | -8.3858 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11851 | 11851 | Survey | SSR Investigation | NTT | UXQ091 | Desa Maikang | 124.725 | -8.3626 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11876 | 11876 | Survey | SSR Investigation | NTT | UXQ092 | Desa Pintu Mas / Lewokoli | 124.5159 | -8.3217 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11901 | 11901 | Survey | SSR Investigation | NTT | UXQ093 | Kuifana / Desa Tribur | 124.5568 | -8.3945 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11926 | 11926 | Survey | SSR Investigation | NTT | UXQ094 | Desa Kamaifui | 124.6705 | -8.3432 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11951 | 11951 | Survey | SSR Investigation | Maluku | UXX026 | Ambalau Desa Ulima | 127.1823 | -3.8261 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
11976 | 11976 | Survey | SSR Investigation | Maluku | UXX027 | Desa Waemulang | 126.1832 | -3.6074 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12001 | 12001 | Survey | SSR Investigation | Maluku | UXX028 | Desa Oki baru | 126.8421 | -3.7917 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12026 | 12026 | Survey | SSR Investigation | Maluku | UXX029 | Desa Wamsisi | 126.9529 | -3.7686 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12051 | 12051 | Survey | SSR Investigation | Maluku | UXX030 | Desa Fogi | 126.0186 | -3.3364 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12076 | 12076 | Survey | SSR Investigation | Maluku | UXY018 | Rumah Lewang Besar Ex Tepa | 129.5261 | -7.88 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
12126 | 12126 | Survey | SSR Investigation | Maluku | UXY020 | Desa Latalola Besar | 129.8746 | -8.1235 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12151 | 12151 | Survey | SSR Investigation | Maluku | UXY021 | Desa Sila | 128.0957 | -8.2082 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12176 | 12176 | Survey | SSR Investigation | Maluku | UXY022 | Desa Lelang | 128.9484 | -8.2239 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12201 | 12201 | Survey | SSR Investigation | Maluku | UXY023 | Desa Watuwei | 130.0401 | -7.7599 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12276 | 12276 | Survey | SSR Investigation | Maluku | UXY026 | kelaan, ex Wowonda | 131.9162 | -7.1046 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12301 | 12301 | Survey | SSR Investigation | Maluku | UXY027 | Adobe fordata Yaru | 131.9753 | -7.0002 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12326 | 12326 | Survey | SSR Investigation | Maluku | UXY028 | waturu nirunmas Mtb | 131.6614 | -7.5167 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12351 | 12351 | Survey | SSR Investigation | Maluku | UXY029 | meyano bab kormomalin Mtb | 131.6152 | -7.6429 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12376 | 12376 | Survey | SSR Investigation | Maluku | UXY030 | Fursui Selaru Mtb | 130.8199 | -8.3234 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12426 | 12426 | Survey | SSR Investigation | Maluku | UXY032 | alusi bajas.kormomalin. mtb | 131.5802 | -7.6691 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12451 | 12451 | Survey | SSR Investigation | Maluku | UXY033 | Desa Jambu Air | 134.8367 | -6.4872 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
12501 | 12501 | Survey | SSR Investigation | Maluku | UXY035 | Desa Mestiang | 134.7559 | -6.6287 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
12601 | 12601 | Survey | SSR Investigation | Papua | UYO025 | Desa Gurage | 138.0614 | -3.6983 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12626 | 12626 | Survey | SSR Investigation | Papua | UYO026 | Desa Kalome | 138.1239 | -3.7024 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12651 | 12651 | Survey | SSR Investigation | Papua | UYO027 | Kampung Trikora | 137.9617 | -3.6981 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12676 | 12676 | Survey | SSR Investigation | Papua | UYO028 | Puncak Senyum | 138.022 | -3.7182 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12701 | 12701 | Survey | SSR Investigation | Papua | UYO029 | Desa Tinggi Nambut | 138.0941 | -3.7063 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12726 | 12726 | Survey | SSR Investigation | Papua | UYO030 | Desa Yambi | 137.9255 | -3.7254 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12775 | 12775 | Survey | SSR Investigation | Papua Barat | UZZ01x | Distrik Anggi | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
12800 | 12800 | Survey | SSR Investigation | Papua Barat | UZZ02x | Minyambouw | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
12825 | 12825 | Survey | SSR Investigation | Papua Barat | UZZ03x | Ero Wero | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 1 | Verify
12850 | 12850 | Survey | SSR Investigation | Sulawesi Utara | UZZ04x | Kawaluso | 125.3192 | 4.2332 | VENDOR | 2016-08-01 | 2016-08-01 | 2 | Verify
12875 | 12875 | Survey | SSR Investigation | Maluku Utara | UZZ05x | Peod | 127.4083 | 1.2078 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12900 | 12900 | Survey | SSR Investigation | Maluku Utara | UZZ06x | Sasur | 127.4215 | 1.2559 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12925 | 12925 | Survey | SSR Investigation | Maluku Utara | UZZ07x | Pumadada | 127.7014 | 1.9157 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12950 | 12950 | Survey | SSR Investigation | Maluku Utara | UZZ08x | Togoreba | 127.6909 | 1.4857 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
12975 | 12975 | Survey | SSR Investigation | Maluku Utara | UZZ09x | Nuku | 127.7008 | 0.01298 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13000 | 13000 | Survey | SSR Investigation | Maluku Utara | UZZ10x | Desa Adu | 127.4908 | 1.375 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13025 | 13025 | Survey | SSR Investigation | Papua | UZZ11x | Desa Wuyuneri | 137.9695 | -3.7183 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13050 | 13050 | Survey | SSR Investigation | Papua | UZZ12x | Desa Fawi | 137.7276 | -3.2305 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13075 | 13075 | Survey | SSR Investigation | Papua Barat | UZZ13x | Sawendui | 136.6393 | -1.7284 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13100 | 13100 | Survey | SSR Investigation | Papua Barat | UZZ14x | Desa Kamanap | 136.0496 | -1.8284 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13125 | 13125 | Survey | SSR Investigation | Papua Barat | UZZ15x | kampung Ansus | 135.8189 | -1.7311 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13150 | 13150 | Survey | SSR Investigation | Papua Barat | UZZ16x | Desa Windesi | 135.9087 | -1.6369 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13175 | 13175 | Survey | SSR Investigation | Papua Barat | UZZ17x | Desa Rembai | 135.5121 | -1.6815 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13200 | 13200 | Survey | SSR Investigation | Papua Barat | UZZ18x | Desa Poom | 135.6917 | -1.6271 | VENDOR | 2016-08-01 | 2016-08-01 | 3 | Verify
13225 | 13225 | Survey | SSR Investigation | Kalimantan Timur | UZZ19x | Merasa, Desa Merasa | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13250 | 13250 | Survey | SSR Investigation | Papua | UZZ20x | Waropko | 140.8267 | -5.6327 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13275 | 13275 | Survey | SSR Investigation | Papua | UZZ21x | Mokbiran | 140.8446 | -5.8641 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13300 | 13300 | Survey | SSR Investigation | Papua | UZZ22x | Desa Ni Nati | 140.9206 | -5.692 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13325 | 13325 | Survey | SSR Investigation | Papua | UZZ23x | INYANDIT | 140.582 | -5.8785 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13350 | 13350 | Survey | SSR Investigation | Papua | UZZ24x | kampung sesnukt | -6.1999 | 140.7606 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13375 | 13375 | Survey | SSR Investigation | Kalimantan Barat | UZZ25x | Pamtas Siding | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13400 | 13400 | Survey | SSR Investigation | Maluku | UZZ26x | Desa Ilwaki | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13425 | 13425 | Survey | SSR Investigation | Papua Barat | UZZ27x | Kampung Lebau | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13450 | 13450 | Survey | SSR Investigation | Kalimantan Barat | UZZ28x | MENSIAU | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13475 | 13475 | Survey | SSR Investigation | Kalimantan Barat | UZZ29x | SUNGAI SENUNUK | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13500 | 13500 | Survey | SSR Investigation | Kalimantan Barat | UZZ30x | SETULANG | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13525 | 13525 | Survey | SSR Investigation | Kalimantan Barat | UZZ31x | KANTUK ASAM | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13550 | 13550 | Survey | SSR Investigation | Kalimantan Barat | UZZ32x | Pamtas Kantuk Asam | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13575 | 13575 | Survey | SSR Investigation | Kalimantan Barat | UZZ33x | Pamtas Gun Tembawang | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13600 | 13600 | Survey | SSR Investigation | Kalimantan Barat | UZZ34x | NANGA BAYAN | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13625 | 13625 | Survey | SSR Investigation | Kalimantan Barat | UZZ35x | Pamtas Enteli | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13650 | 13650 | Survey | SSR Investigation | Kalimantan Barat | UZZ36x | MUNGGUK GELOMBANG | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13675 | 13675 | Survey | SSR Investigation | Kalimantan Barat | UZZ37x | NANGA KELAPAN | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13700 | 13700 | Survey | SSR Investigation | Kalimantan Barat | UZZ38x | Pamtas Semareh | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13725 | 13725 | Survey | SSR Investigation | Kalimantan Timur | UZZ39x | Naha Silat | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13750 | 13750 | Survey | SSR Investigation | Kalimantan Utara | UZZ40x | Pamtas Long Metun | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13775 | 13775 | Survey | SSR Investigation | Kalimantan Utara | UZZ41x | Pamtas Long Nawang | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13800 | 13800 | Survey | SSR Investigation | Kalimantan Utara | UZZ42x | Pamtas Simantipal | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13825 | 13825 | Survey | SSR Investigation | Kalimantan Utara | UZZ43x | Pa Raye | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13850 | 13850 | Survey | SSR Investigation | Kalimantan Utara | UZZ44x | Pamtas Simanggaris Baru | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13875 | 13875 | Survey | SSR Investigation | Kalimantan Utara | UZZ45x | Pamtas Gabma simanggaris | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13900 | 13900 | Survey | SSR Investigation | Kalimantan Utara | UZZ46x | Pamtas Simanggaris Lama | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13925 | 13925 | Survey | SSR Investigation | Kalimantan Utara | UZZ47x | Pamtas Simantobol | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13950 | 13950 | Survey | SSR Investigation | Sulawesi Utara | UZZ48x | Marore | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
13975 | 13975 | Survey | SSR Investigation | Maluku | UZZ49x | Desa Waeken | -3.6748 | 126.4433 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
14000 | 14000 | Survey | SSR Investigation | Maluku | UZZ50x | Desa Waekeka | -3.1464 | 126.0597 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify
14025 | 14025 | Survey | SSR Investigation | Maluku | UZZ51x | Desa Wemala | 0 | 0 | VENDOR | 2016-08-01 | 2016-08-01 | 4 | Verify